## Sheet1
Process/Action | Approx. Processing Time | Responsibility
Agency RFP Preparation
Documentation prepared & finalized for submission as O5 requisition to SPB | 3-9 months or more, depending on complexity | Agency
If proposed contract is anticipated to be in excess of $15,000,000, Agency submits to Materiel Division a Proof-of-Need Analysis as required, unless exempt per statute | As soon as anticipated | Agency
Materiel Division provides a letter to the submitting Agency Director and point of contact acknowledging receipt of Proof-of-Need Analysis | Within 3 business days | SPB
Materiel Division provides a letter to the submitting Agency either certifying the Proof-of-Need Analysis is complete or requesting additional information | Within 30 business days of receipt | SPB
Agency must file the proposed contract, Proof-of-Need Analysis, and Materiel Division's Certification with the Legislative Fiscal Analyst | Within 5 business days | Agency
Steps Prior to Release of RFP | Goal is within 60 business days
Agency submits requisition and draft RFP and the Evaluation Criteria and Scoring Tool to SPB for review - goes through approval routing in PFC (E1) | Within 1 business day | Agency
SPB conducts initial review of RFP & has Initial Meeting with Agency | Within 15 business days | SPB/Agency
Agency revises RFP based on recommendations/discussions with SPB | Within 10 business days | Agency
SPB and Agency may hold additional meetings depending on the complexity of the RFP | Within 10 business days after revisions made by Agency | SPB/Agency
Agency submits finalized RFP technical specifications, cost sheet(s), and evaluation criteria to SPB for final review | Within 7 business days | Agency
SPB & Agency develop Schedule of Events | Within 3 business days | SPB/Agency
All documents are submitted to Agency for final approval | Within 5 business days | SPB
SPB processes documentation for internal review/approvals | Within 2 business days | SPB
Procurement Manager reviews and signs off on documentation | Within 3 business days | SPB
Documentation finalized and submitted to Procurement Technician for processing | Within 1 business day | SPB
SPB processes RFP for release, posting to website, milestone reviews, etc. | Within 3 business days | SPB
Steps After Release of RFP
Last day to submit "Notification of Intent to Attend Pre-Proposal Conference" (Optional Event) | Minimum 10 business days after release of RFP | Vendor
Last day to submit written questions (Agencies may elect 2 rounds of questions which will increase timeline) | Minimum 15 business days after release of RFP | Vendor
Mandatory Pre-Proposal Conference (Optional Event) | Minimum 10-15 business days after release of RFP | SPB/Agency/Vendor
Last day for Vendor to submit written questions to SPB after Pre-Proposal Conference | Minimum 1 business day after Pre-Proposal Conference | Vendor
Agency develops responses to Vendor questions | Within 10 business days after questions due | Agency/SPB
SPB Review of Agency's responses to Vendor questions | Within 5 business days after receipt from Agency | SPB
SPB & Agency meet to review Vendor questions/responses, if necessary | Within 5 business days after SPB initial review of responses | SPB/Agency
State responds to written questions through Addendum and/or Amendment | Minimum 10 business days after receipt of questions, depending on complexity of RFP | SPB
Last day for Vendor to submit "Notification of Intent to Bid," if required by RFP | Within 5 business days after posting responses to questions | Vendor
Proposal Opening | Minimum 15 business days after posting responses to questions | SPB
Evaluation Period
Review for conformance of mandatory requirements | Within 1 business day | SPB
Evaluation Period | Within 15 business days after Proposal Opening | Agency
Preparation of Oral Interview Letters, if required | Within 5 business days after initial evaluation | SPB
Oral Interviews/Presentations and/or Demonstrations (if required) | Within 10 business days after evaluation period | SPB/Agency/Vendor
At request of Agency, SPB prepares Best and Final Offer documents and sends to bidders (if required) | Within 2 business days | SPB
Best and Final Offering Opening (if required) | Within 5 business days after request | SPB/Agency/Vendor
Submit Final Scoring document along with Intent to Award recommendation | Within 5 business days after completion of evaluation | Agency
Steps after Award Recommendation (Award Process) | Goal is within 30 business days
SPB verifies scoring received from Agency | Within 5 business days after receipt from Agency | SPB
Post "Letter of Intent to Contract" to internet | Within 2 business days after submission of final scoring document | SPB
Performance bond submission, if applicable | Within 10 business days after notification of Intent to Contract | SPB/Intended Contractor
Certificate of Insurance submission | Within 10 business days after notification of Intent to Contract | SPB/Intended Contractor
Secretary of State Registration, if applicable | Within 10 business days after notification of Intent to Contract | SPB/Intended Contractor
Finalization of Terms and Conditions, if applicable | Within 10 business days after notification of Intent to Contract | SPB/Legal/Intended Contractor/Agency
SPB PCO processes documentation for submission to Procurement Technician to complete the contract | Within 3 business days | SPB
Procurement Technician creates contract | Within 2 business days | SPB
SPB PCO reviews and makes changes, if necessary; sends through for signature | Within 2 business days | SPB
Procurement Manager reviews and initials contract | Within 2 business days | SPB
Materiel Administrator signs contract | Within 2 business days | SPB
SPB e-mails copy of contract to Agency, sends copy to Contractor, and posts contract to website | Within 2 business days | SPB