## ITB Timeline
ITB Process Timeline
Disclaimer: All processing times listed below are estimated. The overall complexity and submission quality of the ITB will ultimately determine the total processing time.
Agency ITB Development Average is 180+ Calendar Days
Process/Action | Processing Time | Responsibility
Agency develops ITB and all associated documents following ITB Submission Requirements | 6 months or more depending on complexity | Agency
ITB Preparation Average 30 Business Days
Process/Action | Processing Time | Responsibility
Agency submits appropriate requisition to SPB for review - Requisition will proceed through document approval routing in PFC (E1) | Within 1 business day | Agency
SPB conducts initial review of ITB and conducts kickoff meeting with Agency | Within 15 business days | SPB
Agency revises ITB based on recommendations/discussions with SPB | Within 15 business days | Agency
Agency submits finalized ITB documents to SPB for final review | Within 7 business days | Agency
SPB collaborates with DAS Legal for approval on any changes to standard terms and conditions requested by agency | Within 5 business days | SPB
SPB and Agency develop Schedule of Events | Within 3 business days | SPB/Agency
All documents are submitted to Agency for final approval | Within 5 business days | SPB
SPB finalizes all documents and completes final review for release and posting to website. | Within 5 business days | SPB
Solicitation Process Average 30 Business Days
Process/Action | Processing Time | Responsibility
Last day to submit "Intent to Attend Solicitation Conference" (Optional Event) | Minimum 5 business days after release of ITB | Vendor
Last day to submit written questions | Minimum 5 business days after release of ITB | Vendor
Solicitation Conference (Optional Event) | Minimum 10 business days after release of ITB | SPB/Agency/Vendor
Last day for Vendor to submit written questions to SPB after Solicitation Conference | Minimum 1 business day after Solicitation Conference | Vendor
Agency develops responses to Vendor questions | Within 5 business days after questions due | Agency/SPB
SPB Review of Agency's responses to Vendor questions | Within 2 business days after receipt from Agency | SPB
SPB & Agency meet to review Vendor questions/responses, if necessary | Within 2 business days after receipt from Agency | SPB/Agency
State formally responds to written questions by posting Addendum | Within 2 business days after receipt from Agency | SPB
Bid Opening | Minimum 15 calendar days after ITB posted to website | SPB
Evaluation Process Average 15 Business Days
Process/Action | Processing Time | Responsibility
SPB reviews and clarifies solicitation responses as needed for solicitation compliance | Within 5 business days after Bid Opening | SPB
Bid Tabulation with responsive bids created by SPB for agency review | Within 3 business days after compliance review | SPB
Bid Tabulation and Bid Responses sent to Agency for review and evaluation | Within 2 business days after completion of bid tab | SPB
At request of Agency, SPB prepares Best and Final Offer documents and sends to bidders, if applicable | Within 2 business days of receiving request from Agency | SPB
Best and Final Offer Opening, if applicable | Within 5 business days after bidders are notified | SPB/Agency/Vendor
Agency submits award recommendation | Within 10 business days after receipt of bids for review | Agency
Award Process Average 40 Business Days
Process/Action | Processing Time | Responsibility
SPB reviews and validates agency award recommendation | Within 3 business days after receipt of award recommendation | SPB
SPB posts Notification of Intent to Award, Solicitation Responses, List of Respondents, and Final Evaluation Doc, starting the mandatory 10 business day protest period | Within 5 business days after receipt of award recommendation | SPB
SPB requests clarification and/or documents as required (i.e. vendor registration, insurance, licenses, performance bond, etc.) | Within 10 business days from posting of Notification of Intent to Award | SPB/Intended Vendor
Vendor completes Secretary of State Registration, if applicable | Within 10 business days from posting of Notification of Intent to Award | SPB/Intended Vendor
SPB facilitates contract award negotiations for any term and condition exceptions and clarifications, if applicable | Within 20 business days from posting of Notification of Intent to Award | SPB/Agency/Vendor
SPB generates award documents | Within 3 business days after conclusion of protest period and any negotiations, if applicable | SPB
SPB reviews and finalizes all documents and sends for signature | Within 5 business days after conclusion of protest period and any negotiations, if applicable | SPB
Materiel Administrator signs Purchase Orders over $50,000 and/or all contracts | Within 5 business days after contract documents sent for signature | SPB