## RFP Timeline
SPB Led RFP Process Timeline
Disclaimer: All processing times listed below are estimated. The overall complexity and submission quality of the RFP will ultimately determine the total processing time.
Agency RFP Development Average 270 Calendar Days
Process/Action | Processing Time | Responsibility
Agency develops RFP and all associated documents following RFP Submission Requirements | 6 months or more depending on complexity | Agency
RFP Preparation Average 40 business days
Process/Action | Processing Time | Responsibility
Agency submits appropriate requisition to SPB for review - Requisition will proceed through document approval routing in PFC (E1) | Within 3 business days | Agency
SPB conducts initial review of RFP and conducts kickoff meeting with Agency | Within 15 business days | SPB
Agency revises RFP based on recommendations/discussions with SPB and submits updated documents to SPB for final review | Within 20 business days | Agency
SPB reviews updated RFP and associated documents from Agency | Within 10 business days | SPB
SPB collaborates with DAS Legal for approval on any changes to standard terms and conditions requested by Agency | Within 5 business days | SPB
SPB and Agency develop Schedule of Events | Within 3 business days | SPB/Agency
All documents are submitted to Agency for final approval | Within 5 business days | SPB
SPB finalizes all documents and completes final review for release and posting to website. | Within 5 business days | SPB
Solicitation Process Average 40 Business Days
Process/Action | Processing Time | Responsibility
Last day to submit "Intent to Attend Solicitation Conference" (Optional Event) | Minimum 5 business days after release of RFP | Vendor
Last day to submit written questions | Minimum 5 business days after release of RFP | Vendor
Solicitation Conference (Optional Event) | Minimum 10 business days after release of RFP | SPB/Agency/Vendor
Last day for Vendor to submit written questions to SPB after Solicitation Conference, if applicable | Minimum 1 business day after Solicitation Conference | Vendor
SPB formats vendor questions and sends to Agency to develop responses | Within 1 business day after questions due | SPB
Agency develops responses to Vendor questions | Within 5 business days after questions due | Agency
SPB develops responses to Vendor questions related to procurement process | Within 5 business days after questions due | SPB
SPB reviews Agency's responses to Vendor questions | Within 2 business days after receipt from Agency | SPB
SPB & Agency meet to review Vendor questions/responses, if necessary | Within 2 business days after receipt from Agency | SPB/Agency
State formally responds to written questions by posting Addendum | Within 2 business days after receipt from Agency | SPB
Bid Opening | Minimum 15 calendar days after RFP posted to website | SPB
Evaluation Process Average 25 Business Days
Process/Action | Processing Time | Responsibility
SPB reviews and clarifies solicitation responses as needed for solicitation compliance | Within 5 business days after Bid Opening | SPB
SPB sends compliant vendor solicitation responses to Agency for review and evaluation | Within 2 business days after compliance review | SPB
Agency Evaluation Period | Within 15 business days after receiving responses from SPB | Agency
Preparation of Vendor Demonstration Letters, if applicable | Within 5 business days after initial evaluation | SPB
Vendor Demonstrations, if applicable | Within 15 business days after evaluation period | SPB/Agency/Vendor
At request of Agency, SPB prepares Best and Final Offer documents and sends to bidders, if applicable | Within 2 business days of receiving request from Agency | SPB
Best and Final Offer Opening, if applicable | Within 5 business days after bidders are notified | SPB/Agency/Vendor
Agency submits Final Scoring document and vendor evaluation scoring sheets to SPB along with Intent to Award recommendation | Within 5 business days after completion of evaluation | Agency
Award Process Average 40 business days
Process/Action | Processing Time | Responsibility
SPB reviews and validates Agency award recommendation | Within 3 business days after receipt of award recommendation | SPB
SPB posts Notification of Intent to Award, Solicitation Responses, List of Respondents, and Final Evaluation Doc, starting the mandatory 10 business day protest period | Within 5 business days after receipt of award recommendation | SPB
If proposed contract is anticipated to be in excess of $15,000,000, Agency completes and submits to Materiel Division a Proof-of-Need Analysis as required, unless exempt per statute, following proof of need guide | Within 15 business days after receipt of award recommendation | Agency
SPB* requests clarification and/or documents as required (i.e. vendor registration, insurance, licenses, performance bond, etc.) | Within 10 business days from posting of Notification of Intent to Award | SPB*/Intended Vendor
Vendor completes Secretary of State Registration, if applicable | Within 10 business days from posting of Notification of Intent to Award | SPB*/Intended Vendor
SPB* facilitates contract award negotiations for any term and condition exceptions and clarifications, if applicable | Within 20 business days from posting of Notification of Intent to Award | SPB*/Agency/Vendor
Materiel Administrator provides a Certification of Receipt for Proof of Need Analysis, if applicable | Within 10 business days of receipt | SPB
SPB* generates award documents | Within 3 business days after conclusion of protest period and any negotiations, if applicable | SPB*
SPB* reviews and finalizes all documents and sends for signature | Within 5 business days after conclusion of protest period and any negotiations, if applicable | SPB*
Final executing authority signs contract documents | Within 5 business days after contract documents sent for signature | SPB*
* If resulting contract will be Agency specific, these steps will be conducted by the managing Agency per SPB Contract Responsibility and Negotiations Policy