## Sheet1
Process/Action | Approx. Processing Time | Responsibility
Agency ITB Preparation
Agency develops ITB specifications and cost sheet(s) | Up to 6 months or more depending on complexity | Agency
Steps Prior to Release of ITB | Goal is within 45 business days
Agency submits requisition with specifications and cost sheet(s), as needed, to SPB for review - goes through approval routing in PFC (E1) | Within 1 business day | Agency
SPB conducts initial review of ITB & has Initial Meeting with Agency | Within 15 business days | SPB
Agency revises ITB based on recommendations/discussions with SPB | Within 5 business days | Agency
Agency submits finalized ITB specifications and cost sheet(s) to SPB for final review | Within 7 business days | Agency
SPB and Agency develop Schedule of Events | Within 3 business days | SPB/Agency
All documents are submitted to Agency for final approval | Within 5 business days | SPB
SPB processes documentation for internal review/approvals | Within 2 business days | SPB
Procurement Manager reviews and signs off on documentation | Within 3 business days | SPB
Documentation finalized and submitted to Procurement Technician for processing | Within 1 business day | SPB
SPB processes ITB for release, posting to website, milestone reviews, etc. | Within 3 business days | SPB
Steps After Release of ITB
Last day to submit "Notification of Intent to Attend Pre-Bid Conference" (Optional Event) | Minimum 7 business days after release of ITB | Vendor
Last day to submit written questions | 7 business days after release of ITB | Vendor
Mandatory Pre-Bid Conference (Optional Event) | Minimum 10 business days after release of ITB | SPB/Agency/Vendor
Last day for Vendor to submit written questions to SPB after Pre-Bid Conference | Minimum 1 business day after Pre-Bid Conference | Vendor
Agency develops responses to Vendor questions | Minimum 1-3 business days after questions due | Agency/SPB
SPB Review of Agency's responses to Vendor questions | Within 2 business days after receipt from Agency | SPB
SPB & Agency meet to review Vendor questions/responses, if necessary | Within 2 business days after receipt from Agency | SPB/Agency
State responds to written questions through Addendum and/or Amendment | Within 2 business days after receipt from Agency | SPB
Bid Opening | Minimum 15 calendar days after ITB posted to website | SPB
Evaluation Period
Review for bid compliance | Within 1 business day | SPB
Bid Tabulation created by SPB | Within 3 business days after Bid Opening | SPB
Initial Bid Tabulation is posted to the website | Within 2 business days after completion of Bid Tab | SPB
Bid Tabulation and Bid Responses sent to Agency for review and evaluation | Within 2 business days after completion of Bid Tab | SPB
Agency submits award recommendation | Within 10 business days after receipt of bids for review | Agency
Steps After Award Recommendation (Award Process) | Goal is 30 business days
SPB reviews Agency award recommendation and completes Award of Bid, if necessary | Within 4 business days after receipt of award recommendation | SPB
SPB requests clarification and/or documents as required (i.e. insurance, drawings or license) | Within 10 business days after award recommendation | SPB/Intended Contractor
Secretary of State Registration, if applicable | Within 10 business days after award recommendation | SPB/Intended Contractor
SPB PCO processes documents for submission to Procurement Technician to complete the Contract/Purchase Order | Within 4 business days | SPB
Procurement Technician creates Contract/Purchase Order | Within 3 business days | SPB
SPB PCO reviews/peer reviews and makes changes, if necessary; sends through for signature | Within 3 business days | SPB
Procurement Manager reviews and initials Contract/Purchase Order | Within 2 business days | SPB
Materiel Administrator signs Purchase Orders over $25,000 and/or all Contracts | Within 2 business days | SPB
SPB e-mails copy of Contract/Purchase Order to Agency, copy to Contractor, and posts Contract to website | Within 2 business days | SPB