## Development Activities
RFP 124065 O5 – ONE RED Ag Data Bank and Grants Program - Incite AgPro LLC (“incite.ag”) - Itemized Development Activities By Deliverable
Deliverable | Cost ID | Cost Item | Sub Cost ID | Activity | Resources | Hours | Description
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.01 | Project kickoff, scope decomposition, preliminary architecture, and requirements elaboration (Data Bank) with NDWEE sponsors | Project Manager; Business Analyst; Solution Architect | 300 | Translate 1.1 requirements into an implementable backlog (user stories + acceptance criteria), identify dependencies with 1.2-1.7, and confirm beta-critical workflows. Supports: ASP uploads, producer access to scores/history, and scalable storage
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.02 | Release planning and delivery roadmap (beta + 3-year evolution) | Project Manager; Solution Architect | 110 | Define phased releases (beta in 2026 → GA hardening → feature expansion), align milestones to NDWEE stakeholder checkpoints, and maintain integrated roadmap across deliverables.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.03 | Target architecture and non-functional design (scalability, resiliency, modularity) | Solution Architect; Cloud Architect; DevOps Engineer | 240 | Produce/maintain architecture decisions for private-network deployment, service boundaries, scaling model, and failure modes. Align with data-flow diagrams for auth + data plane endpoints.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.04 | Solution design workshops and diagram refinement (end-to-end Data Bank flow) | Solution Architect; Project Manager | 120 | Run stakeholder design reviews to validate user journeys: producer login, ASP delegated authorization,cCrop data & CI score submission, and producer dashboard consumption. Update data-flow diagrams as requirements evolve.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.05 | Core data model & domain schema design (scopes, users, fields, CI score) | Data Architect; Backend Engineer | 180 | Design transactional schema for producer accounts, fields, CI scores, and immutable history; define versioning/idempotency strategy for repeated submissions.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.06 | API spec/contract design (OpenAPI) for Data Bank user & ASP integrations | Backend Engineer; Solution Architect | 190 | Define/maintain REST API contracts / spec for CI score upload/retrieval, field resources, and user-scoped access patterns; publish OpenAPI spec and example requests. Example Python & NodeJS application workflows published to Github
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.07 | ASP delegated authorization flows (OAuth 2.0) + token issuance foundations for Data Bank | Backend Engineer; Solution Architect | 260 | Implement OAuth 2.0 authorization endpoints and token issuance behavior required for ASP access to producer-scoped APIs (per diagrammed OIDC+OAuth flow). Includes app registration metadata handling for ASP clients (non-payment).
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.08 | Versioned CI Score microservice (core engine supporting score validation & scenario modeling) | Backend Engineer; Solution Architect; Agronomy SME | 340 | Codification of USDA FD-CIC latest release to scalable runtime (FastAPI, ExpressJs server). Categorical emissions breakdown using proprietary CI calculation knowledge; USDA grounded nutrient budget determination. Variable change requirement based on unanounced (yet expected) USDA model release schedule.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.09 | CI score ingestion service (ASP upload → validation → persistence → audit trail) | Backend Engineer; Data Engineer | 400 | Build ingestion pipeline to accept verified CI scores from ASPs, validate payloads, enforce schema/version rules, handle retries/idempotency, and write to transactional store with audit metadata.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.10 | Producer portal UI shell (navigation, account context, score dashboard scaffolding) | Frontend Engineer; UX/UI Designer | 440 | Design and implement producer-facing portal foundation and IA (information architecture) enabling access to CI scores, payment status placeholders, and historical data views. Design mockups produced in Figma/Miro, and validated with NDWEE stakeholders.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.11 | Producer CI score experience (score views, history timeline, discrepancy handling, status tracking, CI scenario modeling environment) | Frontend Engineer; Backend Engineer | 440 | Implement end-user features: view current/previous CI scores, track statuses, and browse immutable history with drilldowns, experiment with scenario modeling differentials from current crop profile.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.12 | Admin search & filtering capabilities (baseline) for CI score data | Backend Engineer; Frontend Engineer; Data Engineer | 360 | Deliver baseline search/filter over CI score and field history (time range, geography, program, status). Advanced analytics/reporting deepening is costed under 1.6.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.13 | Producer exports (baseline CSV/PDF) for personal records and downstream workflows | Backend Engineer; Frontend Engineer | 160 | Provide basic exports for producer-facing records (score history summaries) and supportability. Complex program analytics and NDWEE reporting are covered in 1.6.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.14 | AI Driven Producer Property Ownership Validation | Backend Engineer; Solution Architect | 480 | Develop AI orchestration for extraction of property ownership from FSA 578 (or equivalent supporting records), and validation against producer provided crop data, with failsafes resulting in human escalation. Regular model testing to mitigate model drift & reincorporate new training data for enhanced model learning.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.15 | NDWEE reviewer/admin views (Data Bank): flagged items & manual resolution workflows (foundation) | Frontend Engineer; Backend Engineer | 230 | Implement initial admin/reviewer UI + APIs needed to inspect flagged producer/field/score anomalies for Data Bank operations (e.g. crop-field mismatch, invalid submissions). Full QA/security/support are covered in other cost IDs.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.16 | Document intake touchpoints for Data Bank (uploads + metadata; non-security implementation) | Backend Engineer; Frontend Engineer | 200 | Build user-facing upload workflows and metadata persistence for documents supporting CI records (e.g., validation artifacts). Malware scanning/security controls are costed under 1.2; QA under 1.4.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.17 | ASP integration sandbox + test harness (developer experience) | Backend Engineer; DevOps Engineer | 160 | Provide sandbox environment/config and automated harness for ASPs to validate OAuth and CI score upload integration during onboarding; includes seeded test data and example scripts.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.18 | Technical documentation for Data Bank architecture + APIs (non-training) | Technical Writer; Solution Architect; Backend Engineer | 130 | Maintain architecture overview, developer onboarding, OpenAPI usage notes, and integration guidance for NDWEE and ASP API integration stakeholders. End-user training materials are costed under 1.5.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.19 | Performance engineering for beta (query design, caching strategy, scale testing readiness) | Backend Engineer; DevOps Engineer | 140 | Optimize core read paths (score/history/search) for responsive UX and prepare for peak-load conditions; coordinate with formal QA validation in 1.4.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.20 | Accessibility + responsive UX hardening for producer portal (baseline) | Frontend Engineer; UX/UI Designer | 120 | Ensure UI components meet accessibility and responsive requirements for common devices/browsers; incorporate feedback loops prior to beta.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.21 | Operational readiness features needed by core platform (health endpoints, structured logs, feature flags) | Backend Engineer; DevOps Engineer | 160 | Implement baseline platform operability needed for beta: health/ready endpoints, request correlation IDs, feature-flag wiring for incremental releases. Full monitoring/SLA operations are costed under 1.7.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.22 | Enhancement backlog delivery (Years 2–3): feature expansion & UX iteration for Data Bank | Frontend Engineer; Backend Engineer; Solution Architect; Project Manager | 1300 | Ongoing enhancements after beta: improved workflows, additional producer dashboard capabilities, iterative UX improvements, and support for evolving program needs (excluding dedicated maintenance/SLA in 1.7)
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.23 | Evolving data standards + schema evolution support (e.g., ADAPT payload changes) | Data Engineer; Backend Engineer | 300 | Maintain compatibility with evolving field/crop data standards used by ASPs; manage schema migrations, version negotiation, and backward-compatible transformations.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.24 | Dashboard visualization integration points (optional connectors / embedding scaffolding) | Frontend Engineer; Backend Engineer | 120 | Implement scaffolding for integration with third-party dashboards (e.g. Power BI) or internal dashboards to surface CI score summaries. Deeper analytics/reporting is costed under 1.6.
CI Data Bank Platform | 1.1 | System Design and Development | 1.1.25 | Environment setup + infrastructure-as-code (IaC) baseline for Data Bank applications | DevOps Engineer; Cloud Architect | 290 | Provision dev/test/prod environments for Data Bank services with repeatable IaC, including deployment automation hooks and configuration management. Detailed security hardening is costed under 1.2; ongoing ops under 1.7.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.01 | Security program kickoff + threat modeling for Data Bank | Security Architect; Solution Architect; Project Manager | 140 | Establish security objectives, data classification (PII/crown-jewel), threat models for producer/ASP/admin flows, written information security plan (WISP), and security backlog aligned to 1.2.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.02 | Network isolation architecture (VNet, subnets, no-public-endpoint posture, NAT & VPN gateway) | Cloud Security Engineer; DevOps Engineer; Cloud Architect | 270 | Design/implement private-network boundary for apps and data-plane services, including subnet segmentation and deny-by-default ingress/egress patterns.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.03 | Private endpoints/PrivateLink + private DNS configuration for data stores | Cloud Security Engineer; DevOps Engineer | 210 | Implement private endpoints for CosmosDB/Storage/Key Vault (and other dependencies), private DNS zones, and routing validation to ensure no public data-plane exposure.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.04 | Edge ingress hardening (WAF / reverse proxy policy, TLS posture) | Cloud Security Engineer; DevOps Engineer | 170 | Configure controlled ingress, WAF rules, rate-limits, bot protections, and enforce TLS 1.2+ end-to-end for client→edge→app gateway→service traffic.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.05 | Identity & access controls (IAM, managed identity, RBAC, least privilege, JIT elevation) | Security Engineer; DevOps Engineer; Backend Engineer | 350 | Implement managed identity patterns for services, least-privilege RBAC on apps/databases, and JIT elevation workflow for developers/admins (time-bound access).
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.06 | Key management (Key Vault), secret/cert rotation policies, and signing key governance | Security Engineer; DevOps Engineer | 290 | Implement centralized key management (Key Vault), automate certificate and secret rotation, key versioning, and strict RBAC on key operations (sign/decrypt).
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.07 | Encryption in transit + at rest (platform-wide implementation + validation) | Security Engineer; DevOps Engineer; Data Engineer | 220 | Configure/enforce encryption at rest for CosmosDB, Blob/DFS, backups and queues; validate transport encryption for all endpoints and internal calls, including automated tests/alerts for regressions.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.08 | Application-layer envelope encryption for crown-jewel fields (PII, identity artifacts, payment tokens) | Security Engineer; Backend Engineer | 300 | Design and implement envelope encryption (e.g. RSA wrapped AES-GCM data keys protected by Key Vault/HSM keys) for sensitive fields and documents; include key rotation and re-encryption strategy.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.09 | Secure software supply chain (dependency scanning, container scanning, Software Bill of Materials (SBOM) ) | DevOps Engineer; Security Engineer | 260 | Implement CI/CD security controls: dependency and base-image scanning, SBOM generation, secrets scanning, and policy gates for promotion to UAT/prod.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.10 | SAST/DAST + penetration testing program (automation + vendor coordination) | Security Engineer; QA Security Tester; Project Manager | 360 | Operationalize SAST/DAST pipelines, schedule annual (and pre-GA) penetration tests, track findings through remediation verification.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.11 | Security logging & audit trails surfacing (end-to-end request lifecycle, access logging) | Backend Engineer; DevOps Engineer; Security Engineer | 300 | Implement structured immutable logs, request correlation IDs, and tamper-evident audit logs for producer/ASP/admin actions; define retention for security logs and evidence collection.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.12 | API security hardening (OWASP, injection defenses, rate limits, abuse controls) | Backend Engineer; Security Engineer | 270 | Implement OWASP-aligned controls: input validation, parameterized SDK queries, authZ enforcement (Entra ID, JWTs), request size limits, throttling, and abuse detection for CI score uploads and portal APIs.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.13 | Data privacy compliance design (policy mapping, data minimization, consent boundaries) | Privacy/Compliance Lead; Security Architect; Business Analyst | 210 | Map applicable federal/state requirements and NDWEE policies to platform controls; define data minimization rules and access scope boundaries (producer vs ASP vs admin).
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.14 | Retention, deletion, and records management workflows for PII and confidential data | Privacy/Compliance Lead; Backend Engineer; Data Engineer | 330 | Define and implement retention schedules, deletion workflows, and legal hold/recordkeeping constraints for identity artifacts, ownership documents, crop-year submissions, and payment metadata.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.15 | Data access reviews + periodic RBAC recertification (operational control) | Security Engineer; Compliance Lead | 140 | Run quarterly access reviews for privileged roles, recertify RBAC assignments, validate JIT process effectiveness, and archive evidence for audits.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.16 | ASP verification & authentication controls (approved vendor registry + allowlists) | Security Engineer; Backend Engineer; Program Manager | 250 | Implement controls ensuring only approved/verified ASPs can upload CI scores: vendor registry, client credential lifecycle, redirect URI allowlists, environment separation (UAT vs prod), and scope-limited consent policies.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.17 | Producer identity verification integration security posture (ID.me flow hardening) | Security Engineer; Backend Engineer | 140 | Harden and validate producer identity verification flows (token handling, redirect safety, session integrity, replay protection) and logging for producer auth events.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.18 | Document malware scanning + quarantine workflow (event-driven security control) | DevOps Engineer; Backend Engineer; Security Engineer | 210 | Implement file upload scanning pipeline (issue short-lived SAS URL → blob created event → malware scan → review status update), including quarantine and reviewer notification.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.19 | Incident response plan + tabletop exercises + runbooks (security operations) | Security Engineer; DevOps Engineer; Project Manager | 210 | Create IR plan, severity matrix, on-call/security escalation runbooks, and perform annual tabletop exercises; store evidence and improve procedures over 3 years.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.20 | Continuous posture management (Defender/SIEM signals, config drift detection, hardening backlog) | Security Engineer; DevOps Engineer | 380 | Enroll infra in posture management, monitor vulnerability/configuration signals, manage remediation backlog and drift detection, and produce periodic security posture reports.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.21 | Annual cybersecurity & privacy audit execution + reporting (CISA/CISM/CISSP team) | Security Engineer; Compliance Lead; External Auditor (CISA/CISM/CISSP) | 360 | Plan, support, and report annual audits (SOC 2/ISO 27001/NIST-aligned scrutiny), including evidence preparation (logs, access reviews, diagrams, policies) and remediation tracking.
CI Data Bank Platform | 1.2 | Data Security and Privacy | 1.2.22 | Security + privacy documentation (policies, data handling standards, evidence packages) | Technical Writer; Compliance Lead; Security Architect | 170 | Maintain security & privacy documentation sets: data handling standards, retention/deletion policy docs, audit evidence templates, and architecture/security posture updates as system evolves.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.02 | CI score validity confirmation service (re-scoring + delta detection gate) | Data Engineer; Backend Engineer | 290 | Implement automated CI re-scoring validation using the codified FD-CIC model; detect deltas vs submitted score and route to 'In Review' workflow with ASP notification prior to disbursement.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.03 | Payment calculation engine (business logic defined config) | Backend Engineer; Data Engineer | 40 | Build rules engine to compute incentive amounts once CI score is confirmed (config-driven parameters, versioning, auditability). Includes rule simulation for admins and reproducible calculations stored with each payment record.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.04 | Payment provider selection support + integration architecture (ACH, digital wallets, direct deposit) | Solution Architect; Payment Integration Engineer; Compliance Lead | 170 | Translate payment rails needs into provider capabilities; Consider PayPal Hyperwallet and Plaid; Design integration for a third-party payout provider supporting ACH/direct deposit and wallet options. Includes spec/contract/API review and integration plan.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.05 | Producer payout account onboarding (provider OAuth 2.0 + consent redirect flows) | Backend Engineer; Frontend Engineer | 270 | Implement producer OAuth redirect to payment provider for bank connection consent, success/failure callback handling, and UX for 'Connect payout account' and re-auth. Store only tokenized references to banking details (no raw routing/account numbers).
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.06 | Token lifecycle management for payment provider (secure storage, refresh, rotation) | Backend Engineer; Security Engineer | 210 | Implement secure handling of provider-issued access/refresh tokens, rotation, revocation, and scoped usage for payment status checks and payouts. Align token custody with platform security posture.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.07 | Escrow/disbursement account integration (NDWEE-controlled funds release via provider payout APIs) | Payment Integration Engineer; Backend Engineer; Finance Ops Analyst | 300 | Implement payout execution from an Incite.ag/NDWEE-controlled escrow/disbursement account using provider APIs after CI confirmation and rule evaluation. Includes batching strategy and internal authorization workflow for release.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.08 | Event-driven payment state sync (webhooks/callback ingestion) | Backend Engineer; DevOps Engineer | 210 | Build webhook receiver + validation to ingest provider callbacks ('deposit initiated', 'deposit completed', failures/returns/holds) and synchronize payment state into CosmosDB producer metadata for real-time UX and exception workflows.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.09 | Payment ledger & reconciliation data model (CosmosDB source of truth) | Data Architect; Backend Engineer | 90 | Design and implement payment/reconciliation metadata store (amount, program, CI model version, timestamps, status, references) as source of truth for producer + admin reporting. Includes immutable audit records and idempotent write patterns.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.10 | Producer payment UX (real-time status + transaction history) | Frontend Engineer; Backend Engineer | 360 | Expose participant views for payment status lifecycle (Queued → Submitted → Processing → Paid/Failed/In Review) and transaction history drilldowns with timestamps and explanations.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.11 | Admin payment operations portal (batches, exceptions, audit trails, filters) | Frontend Engineer; Backend Engineer; Program Manager | 420 | Deliver admin tooling for disbursement batch review, exception queues, holds/release decisions, resolution notes, and filtering/search by producer/status/program.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.12 | Exception handling workflows (returns, rejected deposits, holds, retries) | Backend Engineer; Finance Ops Analyst | 300 | Implement automated and manual remediation paths for ACH returns, rejected deposits, compliance holds, and retry policies. Includes producer notification hooks and admin resolution tracking.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.13 | Reporting feeds (real-time + periodic): NDWEE status reporting + metrics aggregation | Data Engineer; Backend Engineer | 270 | Build reporting extracts/aggregations for NDWEE oversight: counts by status, payouts by program/crop year, exception rates, and reconciliation summaries. Supports quarterly/weekly automated reporting flows where applicable.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.14 | W-9 and tax-year compilation workflow (event-driven eligibility list + delivery) | Backend Engineer; Data Engineer; Technical Writer | 170 | Implement annual producer W-9 compilation workflow (e.g. February) for producers who received incentives during tax period; generate export packages and automated delivery triggers consistent with event-driven reporting design.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.15 | Provider sandbox + automated integration tests (payout rails + webhook replay) | Payment Integration Engineer; QA Engineer; DevOps Engineer | 220 | Stand up provider sandbox environments, implement end-to-end tests for OAuth onboarding, payout creation, webhook callback replay, and reconciliation consistency.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.16 | Auditability + evidence packaging for payment actions (who/what/why) | Security Engineer; Backend Engineer; Compliance Lead | 180 | Ensure payment actions are fully auditable (approvals, holds, overrides, final settlement outcomes) with immutable logs and evidence exports supporting annual audits and dispute resolution.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.17 | Provider change management (multi-provider support, failover strategy, contract evolution) | Solution Architect; Payment Integration Engineer | 210 | Design for provider substitution and optional multi-provider support (e.g., add second payout provider), including abstraction layer, migration plan, and operational playbooks.
CI Data Bank Platform | 1.3 | Payment Processing Integration | 1.3.18 | Ongoing enhancements (Years 2–3): new programs, additional payout rails, UX iteration | Frontend Engineer; Backend Engineer; Program Manager; Data Engineer | 400 | Post-beta enhancements to support new NDWEE programs, expanded payout rails, improved participant transparency, and iterative admin operations tooling (excluding general platform support/SLA in 1.7).
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.02 | Test environment architecture + data seeding (dev/test/UAT/prod parity) | DevOps Engineer; QA Engineer; Data Engineer | 300 | Provision/maintain test environments and realistic seeded datasets for CI scores, payments, and documents; enable safe replay of flows without touching production PII.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.03 | Automated unit test coverage baseline (backend services) | Backend Engineer; QA Engineer | 330 | Implement/maintain unit tests for API handlers, validation, rules engine boundaries, and error paths; enforce coverage thresholds in CI.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.04 | Automated unit/component test coverage baseline (frontend) | Frontend Engineer; QA Engineer | 300 | Implement UI component tests for producer portal and admin views (e.g. Selenium); verify state transitions, accessibility hooks, and error states.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.05 | Integration test suite (API ↔ DB ↔ storage ↔ auth) | QA Engineer; Backend Engineer; DevOps Engineer | 310 | Build integration tests spanning ID.me login, ASP OAuth, CI score ingestion, document uploads, and payment state sync (mocked provider in test). Include negative tests and idempotency checks.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.06 | End-to-end (E2E) test automation for critical user journeys | QA Automation Engineer; Frontend Engineer; Backend Engineer | 320 | Automate beta-critical journeys: producer onboarding → view scores/history → connect payout account → view payment status; admin review queues; ASP upload flow using sandbox credentials.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.07 | Data validation and integrity checks (schema, referential integrity, versioning) | Data Engineer; QA Engineer | 300 | Implement automated checks for schema conformance, version compatibility, referential integrity (producer↔fields↔scores↔payments), and immutable history guarantees.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.08 | Performance and load testing (read paths + ingestion paths) | Performance Engineer; DevOps Engineer; Backend Engineer | 390 | Define load profiles and execute tests for score/history reads, search/filtering, CI ingestion bursts, and payment webhook spikes. Produce tuning backlog and re-test cycles.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.09 | Resiliency testing (fault injection, retry behavior, partial outage handling) | DevOps Engineer; Backend Engineer; QA Engineer | 250 | Validate retry, backoff, circuit breaking, and degradation behavior across dependencies (storage, DB, auth, payment callbacks). Verify no data loss and correct recovery states.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.10 | Disaster recovery validation, backup/restore drills and RPO (Recovery Point Objective) and RTO (Recovery Time Objective) verification | DevOps Engineer; Data Engineer; QA Lead | 220 | Execute scheduled backup/restore drills for Cosmos/Storage, validate DR runbooks, and measure RPO/RTO against platform objectives; incorporate improvements.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.11 | Accessibility and cross-browser/device validation (producer + admin portals) | QA Engineer; UX/UI Designer | 90 | Validate HTML/W3-aligned accessibility behaviors, keyboard navigation, screen-reader support, and mobile responsiveness for core workflows; track and verify fixes.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.12 | Security QA validation (verification of 1.2 controls + regression checks) | QA Security Tester; Security Engineer | 180 | Verify implementation of security controls from 1.2 (authZ enforcement, encryption settings, scanning pipelines, WAF rules) through repeatable test cases and regression suites.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.13 | Payment integration QA (sandbox payouts, webhook replay, exception scenarios) | QA Engineer; Payment Integration Engineer | 160 | Execute test matrix for payout onboarding, payout execution, webhook ingestion, returns/retries/holds, and participant/admin status consistency. Includes scripted webhook replays and reconciliation assertions.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.14 | ASP integration UAT testing support (partner coordination + certification) | QA Lead; Backend Engineer; Program Manager | 340 | Support ASPs through UAT certification: validate OAuth flows, payload conformance, error handling, and data correctness; issue integration sign-off and manage remediation cycles.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.15 | User acceptance testing (NDWEE) planning + facilitation (beta and post-beta) | QA Lead; Project Manager; UX Researcher | 200 | Plan and facilitate NDWEE UAT sessions, collect feedback, triage defects/enhancements, and verify closure. Includes beta UAT and periodic UAT for major releases.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.16 | Defect triage, root cause analysis, and quality gates (release readiness) | QA Lead; Engineering Lead; Project Manager | 380 | Operate defect triage process, prioritize fixes, enforce release quality gates, and maintain release notes and known-issues logs. Includes ongoing regression cycles during years 2–3.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.17 | Regression testing automation maintenance (suite upkeep across releases) | QA Automation Engineer | 450 | Maintain and extend regression suites as features expand (1.1/1.3/1.6), including flaky test remediation and pipeline optimization.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.18 | Data migration and schema change validation (forward/backward compatibility) | Data Engineer; QA Engineer; Backend Engineer | 220 | Validate schema migrations, backfills, and version upgrades; test backward compatibility for producers/ASPs during transition windows; verify no corruption or loss of history.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.19 | Operational monitoring validation (alerts, dashboards, synthetic checks) | DevOps Engineer; QA Engineer | 210 | Validate monitoring coverage: synthetic checks for login and key API endpoints, alert thresholds, dashboard correctness, and runbook links; revalidate after major releases.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.20 | Documentation validation (testable runbooks + user-facing help correctness) | QA Engineer; Technical Writer | 170 | Validate correctness of operational runbooks, troubleshooting guides, and key user-facing help content as features evolve; ensure documentation matches system behavior.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.21 | Compliance evidence packages from QA (traceability, test results, sign-offs) | QA Lead; Compliance Lead | 210 | Produce evidence artifacts required for audits and NDWEE oversight: traceability matrices, executed test results, UAT sign-off packages, and release approval records.
CI Data Bank Platform | 1.4 | System Validation and Quality Assurance | 1.4.22 | Post-beta quality hardening cycles (Years 2-3): continuous validation of new scope | QA Engineer; QA Automation Engineer; Engineering Lead | 360 | Dedicated QA cycles for post-beta enhancements: new workflows, expanded reporting, new ASP integrations, and new payment/program rules (excluding general maintenance in 1.7).
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.02 | End-user onboarding content (producer): guided tours, quick-starts, FAQs | Technical Writer; UX/UI Designer | 300 | Produce producer-focused quick-start guides for login/ID verification, viewing CI scores/history, connecting payout account, and understanding payment status.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.03 | Help Center / Knowledge Base build-out (searchable articles + versioning) | Technical Writer; Frontend Engineer | 330 | Implement and populate an in-product help center (search, categories, versioning per release) with articles for producers, ASPs, and admins.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.04 | Video tutorials + microlearning modules (producer + admin) | Training Lead; Technical Writer; Multimedia Specialist | 360 | Produce short videos and microlearning modules for core workflows; maintain updated versions for major releases.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.05 | Train-the-trainer program for NDWEE internal support staff | Training Lead; Program Manager | 190 | Develop playbooks and run live sessions to enable NDWEE staff to support producers/ASPs, including escalation paths and common issue diagnostics.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.06 | ASP integration enablement package (docs + samples + webinars) | Developer Advocate; Backend Engineer; Technical Writer | 340 | Provide ASP onboarding materials: OAuth integration guide, payload examples, sandbox usage, error code catalog, and quarterly enablement webinars.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.07 | Support workflow design (ticketing taxonomy, SLAs, escalation, triage) | Support Operations Lead; Project Manager; QA Lead | 210 | Design support processes: ticket categories, response SLAs, escalation criteria (security/payment), and triage playbooks; align with on-call/operations in 1.7.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.08 | In-product contextual help + guided flows (tooltips, checklists, error remediation) | Frontend Engineer; UX/UI Designer | 370 | Implement contextual help components, guided checklists for onboarding, and actionable error messages for common failures (identity verification, payment onboarding, ASP submission issues).
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.09 | Admin/reviewer operations handbook (queues, holds, overrides, audits) | Technical Writer; Program Manager; Compliance Lead | 210 | Create and maintain detailed admin handbook covering review queues, payment holds/releases, evidence collection, and audit-ready workflows.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.10 | Accessibility-friendly documentation + multilingual readiness (baseline) | Technical Writer; Accessibility Specialist | 170 | Ensure training content meets accessibility needs (captions, alt text, readable layouts). Establish translation-ready workflows; produce baseline Spanish versions for high-traffic pages if required.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.11 | Office hours + live onboarding sessions (beta launch + periodic) | Support Specialist; Training Lead; Program Manager | 310 | Run weekly office hours during beta ramp and monthly thereafter; provide live onboarding sessions for ASPs and NDWEE staff at key milestones.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.12 | Release communications + change notes for users (producer/ASP/admin) | Technical Writer; Product Manager | 170 | Publish release notes and change communications per deployment, including “what changed” guidance and any required user actions; align with release management in 1.7.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.13 | Support analytics + continuous improvement loop (top issues, deflection, user satisfaction rating) | Support Operations Lead; Data Analyst | 210 | Track support metrics (volume, time-to-resolution, deflection via help center), identify product fixes that reduce tickets, and report quarterly.
CI Data Bank Platform | 1.5 | User Training and Support Resources | 1.5.14 | Annual training refresh for new features/program rules (Years 2–3) | Training Lead; Technical Writer; Product Manager | 200 | Update curriculum and content annually to reflect new program rules, new reporting, and portal UX changes; retire outdated content and re-record key videos.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.01 | Reporting requirements + KPI framework (NDWEE oversight + program outcomes) | Product Manager; Business Analyst; Data Analyst | 130 | Define KPI taxonomy (participation, payments, CI improvements, exception rates) and reporting cadence (weekly/monthly/quarterly). Map KPIs to data sources and access roles.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.02 | Analytics architecture (lakehouse/warehouse model + data contracts) | Data Architect; Solution Architect; DevOps Engineer | 220 | Design analytics zone(s) separated from transactional stores; define data contracts, partitioning, retention, and governance patterns for reporting workloads.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.03 | ETL/ELT pipelines from transactional systems (scores, payments, docs metadata) | Data Engineer; DevOps Engineer | 280 | Build batch and incremental pipelines to move curated datasets into analytics store; include idempotency, schema evolution handling, and lineage metadata.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.04 | Semantic layer / metrics model (standardized definitions + reusable measures) | Analytics Engineer; Data Analyst | 390 | Create standardized metric definitions (payments, adoption, score deltas), reusable dimensions (program, crop year, geography), and versioning for metric changes.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.05 | NDWEE executive dashboards (participation, payments, program health) | BI Developer; Data Analyst | 440 | Build interactive dashboards for NDWEE oversight: participant counts, CI outcomes, payment throughput, exception/hold queues, and trends. Includes iterative design with stakeholders.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.06 | Operational dashboards (SLA, latency, ingestion throughput, webhook health) | DevOps Engineer; BI Developer | 290 | Create operational dashboards for system health and operations that complement 1.7 monitoring; focus on data-plane metrics and business process flow (ingestion, payments).
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.07 | Self-serve reporting exports (scheduled reports, CSV/PDF, email delivery) | Backend Engineer; Data Engineer; Frontend Engineer | 390 | Implement scheduled report generation, export endpoints, and delivery mechanisms; support NDWEE and producers where applicable with role-based access.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.08 | Geospatial reporting & mapping (county/state views, program coverage, outcomes) | Geospatial Engineer; BI Developer; Data Engineer | 410 | Enable map-based reporting of participation and outcomes by geography (county/state/region) using aggregated data; include privacy-preserving thresholds for small counts.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.09 | Privacy-preserving aggregation + disclosure controls for reporting | Privacy/Compliance Lead; Data Engineer | 260 | Implement reporting suppression rules, k-anonymity style thresholds, and role-based redaction to prevent disclosure of sensitive producer info in aggregated outputs.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.10 | Data quality monitoring for analytics datasets (freshness, completeness, drift) | Data Engineer; QA Engineer | 340 | Build automated checks for dataset freshness/completeness, reconcile totals vs transactional truth, and alert on anomalies; maintain as schemas evolve.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.11 | Audit-ready reporting packs (annual summaries + evidence exports) | Compliance Lead; Data Analyst; Technical Writer | 250 | Generate standardized annual reporting packs for oversight and audits: program summaries, payout totals, exception handling evidence, and methodology notes
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.12 | Advanced analytics: CI improvement attribution + scenario analysis | Data Scientist; Data Analyst | 480 | Develop analytical models and scenario tools to evaluate program effectiveness (practice adoption → CI outcome), including cohort analysis and sensitivity views; iterate with NDWEE.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.13 | Data access layer for analysts (secure query endpoints / notebooks) - foundation | Data Engineer; Security Engineer; DevOps Engineer | 300 | Provide controlled analyst access paths (read-only roles, approved query workspaces) without exposing raw transactional systems; integrate with access controls defined in 1.2
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.14 | API for reporting data products (aggregations + partner feeds) | Backend Engineer; Data Engineer | 340 | Implement APIs for NDWEE reporting data products (aggregated views, status feeds), enabling downstream systems to consume standardized metrics.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.15 | Dashboard governance (certified metrics, access policies, version control) | Analytics Engineer; Compliance Lead | 210 | Establish governance: certified datasets, metric/version change approvals, access policies, and dashboard lifecycle management across years 2–3.
CI Data Bank Platform | 1.6 | Reporting, Data Products, and Analytics | 1.6.16 | Enhancements (Years 2–3): new reports, new dashboards, expanded geographies/programs | BI Developer; Data Engineer; Data Analyst; Product Manager | 960 | Post-beta expansion of reporting catalog: new program reports, deeper drilldowns, expanded geospatial/outcome views, and iterative improvements driven by stakeholder feedback.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.01 | Operations model + SLA definition (support tiers, uptime targets, maintenance windows) | SRE Lead; Project Manager; Program Manager | 210 | Define support tiers and SLAs (response times, availability), maintenance windows, and release governance for 3-year operations period.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.02 | incident response readiness (on-call rotations, escalation, runbooks) | SRE; Backend Engineer; DevOps Engineer | 960 | Operate on-call coverage and incident response readiness, including triage, coordination, and post-incident review cadence.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.03 | Monitoring/observability operations (dashboards, alert tuning, synthetic checks) | SRE; DevOps Engineer | 720 | Maintain monitoring stack: dashboards, alert tuning, synthetic probes for login/API/payment flows, and runbook links; continuous refinement as platform evolves.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.04 | Routine maintenance (patching, dependency updates, OS/container base image upgrades) | DevOps Engineer; Security Engineer; Backend Engineer | 840 | Monthly patch cycles, dependency upgrades, container base image refreshes, and compatibility testing; coordinate with 1.2 vulnerability scanning and 1.4 regression suites.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.05 | Release management & deployment operations (CI/CD, change windows, rollback) | Release Manager; DevOps Engineer; QA Lead | 620 | Operate release cadence: deployment coordination, change approvals, rollback/rollback testing, and release notes packaging; support frequent updates over 3 years.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.06 | Platform capacity planning + performance tuning (scale forecasts, hotspots) | SRE; Performance Engineer; Data Engineer | 480 | Quarterly capacity planning, cost-aware scaling decisions, performance tuning for read/search/ingestion paths, and load test re-runs as usage grows.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.07 | Backup/restore operations + DR posture maintenance (scheduled drills) | DevOps Engineer; Data Engineer | 390 | Maintain backup policies, verify restore points, perform scheduled DR drills, and update runbooks as architecture evolves.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.08 | Security operations support (vuln triage, remediation coordination, posture reporting) | Security Engineer; DevOps Engineer | 560 | Triage vulnerability findings, coordinate remediation releases, manage security exceptions, and produce periodic posture reports; complements 1.2 but represents ongoing operational workload.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.09 | Data operations (pipeline monitoring, backfills, reconciliation support) | Data Engineer; SRE | 560 | Monitor ETL/pipeline runs, execute backfills, reconcile discrepancies between transactional and analytics/reporting outputs, and address data incidents.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.10 | Payment operations support (payout exceptions, provider escalations, reconciliation) | Finance Ops Analyst; Backend Engineer; Support Specialist | 620 | Ongoing support for payout exceptions, provider escalations, reconciliation questions, and participant inquiries tied to payment status.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.11 | ASP partner support (integration issues, version changes, sandbox upkeep) | Developer Advocate; Backend Engineer; Support Specialist | 480 | Support ASP partners through integration issues, version changes to payloads, sandbox stability, and certification renewals.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.12 | User support execution (ticket handling, triage, escalation, knowledge base updates) | Support Specialist; Support Operations Lead | 880 | Operate user support queue, triage issues, escalate to engineering, and keep help content current based on recurring issues.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.13 | Change management + stakeholder communications (maintenance notices, incidents, releases) | Project Manager; Release Manager | 290 | Maintain change calendar, send maintenance notices, coordinate stakeholder communications during incidents, and publish ongoing operational updates.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.14 | Cost management + FinOps (cloud spend monitoring, reserved capacity, optimization) | FinOps Analyst; Cloud Architect; SRE | 80 | Monitor cloud spend, optimize storage/compute, implement budgets/alerts, and evaluate reserved capacity/savings plans; quarterly optimization reviews.
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.15 | Minor enhancements/bug fixes as part of operations (non-feature scope) | Backend Engineer; Frontend Engineer; QA Engineer | 960 | Operational engineering work: bug fixes, small usability improvements, and minor changes required for stability/compliance (distinct from major feature work in 1.1/1.3/1.6).
CI Data Bank Platform | 1.7 | Ongoing Platform Support, Operations, and Maintenance | 1.7.16 | Annual operational readiness review + audit support (runbooks, evidence, controls) | SRE Lead; Compliance Lead; Security Engineer | 310 | Annual review of operational controls, runbooks, SLAs, and evidence required for audits; validate that operational practices meet NDWEE expectations.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.01 | Program discovery & requirements elaboration (PI & CI grants) | Project Manager; Product Manager; Solution Architect | 290 | Facilitate workshops with NDWEE stakeholders to confirm grant program scope, producer/ASP/admin workflows, decision points, eligibility gates, and reporting needs; translate into epics/user stories, acceptance criteria, and beta vs. post-beta backlog for the 3 year delivery plan.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.02 | Architecture refinement for Grant Interface Platform (microservices + data stores) | Solution Architect; Cloud Architect; Backend Engineer | 260 | Refine target architecture for grant application + incentive workflow services (application intake, document handling, review workflow, payment status, notifications) aligned to overall platform patterns; define service boundaries, integration contracts, and data ownership.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.03 | UX research + accessibility baseline | UX/UI Designer; Product Manager | 210 | Design research interviews + journey mapping for producer, ASP, reviewer, and admin personas; produce accessibility-informed IA/navigation patterns (WCAG-oriented) and establish design system components for consistent grant workflows.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.04 | End-user portal UI (producer) ‚ grant application intake | Frontend Engineer; UX/UI Designer; Backend Engineer | 620 | Build responsive producer portal pages for program browsing, eligibility pre-check, application creation/editing, status tracking, task lists, and notifications; integrate with backend APIs and session/auth patterns; include autosave, draft/submit, and attachment management.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.05 | ASP portal + enrollment workflow (service providers) | Frontend Engineer; Backend Engineer; Developer Advocate | 500 | Implement ASP onboarding and enrollment workflow, including organization profile, API client registration, credential issuance/rotation, environment separation (sandbox/prod), and guidance tooling; provide UI for viewing producer-authorized connections and data submissions.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.06 | Admin portal ‚ program configuration + management | Frontend Engineer; Backend Engineer; Product Manager | 670 | Build NDWEE admin interface for configuring grant programs (windows, budgets, eligibility rules, required artifacts, scoring weights), managing cohorts/regions, defining review queues, and generating standardized checklists for reviewers and auditors.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.07 | Reviewer workflow UI (NDWEE/contractor reviewers) | Frontend Engineer; Backend Engineer; QA Engineer | 470 | Implement reviewer dashboards, queue assignment, application detail views, document preview/annotation hooks, decision actions (approve/deny/request info), and auditable notes; include role-based constraints and escalation paths.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.08 | Workflow engine (states, transitions, SLAs) | Backend Engineer; Solution Architect | 390 | Develop workflow/state machine for grant applications and incentive payments: draft submitted, triage review, additional-info, approved/denied, payment prep, payment issued; include SLA timers, reminders, and event emission for analytics/audit.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.09 | Document intake + verification services (ownership proof, forms, etc.) | Backend Engineer; Data Engineer; Security Engineer | 530 | Implement document upload endpoints, metadata capture, virus scanning hooks, file-type validation, immutable storage strategy, and verification workflow integration (e.g. ownership proof verification checks, W9 intake, supporting artifacts).
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.10 | Geospatial/field interface components (field selection, boundary review) | Geospatial Engineer; Frontend Engineer; Backend Engineer | 500 | Develop map-based UX and APIs to associate applications with fields/CLUs (as applicable), enable boundary review/confirmation, and attach geospatial context to grant submissions; optimize for performance and mobile usability.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.11 | Data upload + ingest pipeline (producer/ASP submissions) | Backend Engineer; Data Engineer; DevOps Engineer | 580 | Build scalable upload and ingest pipeline for producer/ASP data submissions (crop/practice data, supporting datasets) using chunked upload patterns, event-driven processing, schema validation, and deterministic idempotency/retry.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.12 | Program rule evaluation service (eligibility + incentive calculation inputs) | Backend Engineer; Data Architect; Product Manager | 160 | Create rules service that evaluates eligibility and required artifacts, supports configurable thresholds, and produces machine-readable eligibility outcomes; store rule versions and evaluation snapshots for audit and change management.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.13 | Incentive calculation orchestration integration (CI/PI computation triggers) | Backend Engineer; Data Engineer; Data Scientist | 450 | Implement orchestration layer to request/track CI/PI computations (internal services or 3p scoring endpoints), manage versioning, record inputs/outputs, handle exceptions, and surface explainability artifacts for admins and producers.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.14 | Notifications + messaging integration (email/SMS/in-app) | Backend Engineer; DevOps Engineer; Support Specialist | 380 | Implement configurable message templates and triggers across application lifecycle (submission confirmations, missing info, approval/denial, payment updates); integrate with transactional email/SMS services and in-app notification center.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.15 | Public content + program discovery pages | Frontend Engineer; UX/UI Designer; Technical Writer | 210 | Create program landing pages, FAQs, eligibility guidance, and "how it works" content; ensure content is versioned per program year and accessible without authentication when appropriate.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.16 | API design + documentation for Grant Interface endpoints | Backend Engineer; Developer Advocate; Technical Writer | 330 | Define REST endpoints for applications, documents, review actions, payment status, notifications, and exports; publish OpenAPI specs, example payloads, error codes, and integration guides for ASPs and internal consumers.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.17 | Integration adapters (grant management software / external registries) | Backend Engineer; Solution Architect; DevOps Engineer | 380 | Build adapter layer for integrating with external grant management/payment/verification systems as required; support polling/webhooks, data mapping, reconciliation, and resilience patterns (circuit breakers, retries, dead-letter queues).
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.18 | Data model + schema design for application + payment metadata (OLTP) | Data Architect; Backend Engineer | 300 | Design transactional schemas for applications, documents, review events, payment metadata, and user/organization objects; include partition strategy, indexing, retention policies, and audit-friendly immutability for critical records.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.19 | Event model + telemetry (OpenTelemetry traces + event bus) | Backend Engineer; DevOps Engineer; SRE | 310 | Instrument services to emit traceable events for every user action and system decision; define event schemas for analytics and compliance; integrate distributed tracing, correlation IDs, and operational dashboards.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.20 | Environment setup (dev/test/prod) + CI/CD pipelines for Grant Interface | DevOps Engineer; Cloud Architect; Backend Engineer | 370 | Provision environments, build/deploy pipelines, IaC templates, secret management, and gated releases for grant interface components; A/B testing deployment patterns and rollback procedures.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.21 | Role-based permissions model (producer/ASP/reviewer/admin) | Security Engineer; Backend Engineer; Solution Architect | 300 | Define and implement RBAC/ABAC scopes for portal and APIs; ensure least-privilege data access across producer, ASP, reviewer, and NDWEE admin roles; implement permission testing harness and policy versioning.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.22 | Beta release hardening (performance, usability, critical path stabilization) | Project Manager; Backend Engineer; Frontend Engineer; QA Engineer | 390 | Stabilize core beta flows (apply ‚ submit ‚ review ‚ decision ‚ payment status) with performance tuning, UX fixes, defect closure, and readiness checklists; coordinate beta launch gates and production readiness.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.23 | Post-beta feature delivery (Year 2‚ 3 roadmap increments) | Product Manager; Backend Engineer; Frontend Engineer; Data Engineer | 750 | Deliver planned Year 2‚ 3 feature increments: expanded program types, multi-year application handling, enhanced reviewer tools, advanced geospatial context, configurable incentive formulas, and extensibility for additional program requirements.
Grant Program Interface Platform | 2.1 | System Design & Development | 2.1.24 | Documentation + handoff for operations and program administration | Technical Writer; Solution Architect; Support Specialist | 220 | Produce runbooks and admin playbooks covering program configuration, queue management, data exports, support escalation, and common operational tasks; align with NDWEE governance and staffing plans.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.01 | Security requirements + threat modeling for Grant Interface | Security Engineer; Solution Architect; Compliance Lead | 270 | Conduct threat modeling for grant application, document, and payment workflows; identify attack surface (auth, upload, review tools, admin actions) and define security controls, logging, and incident response requirements.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.02 | Identity integration hardening (OIDC/OAuth flows, session security) | Security Engineer; Backend Engineer; Frontend Engineer | 330 | Harden authentication flows (OIDC/OAuth), secure cookie/session strategy, CSRF protections, token rotation, and secure redirect handling; validate against common auth vulnerabilities and misconfiguration risks.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.03 | RBAC/least-privilege enforcement + policy engine | Security Engineer; Backend Engineer | 380 | Implement centralized authorization policy evaluation for all grant interface APIs; ensure role-scoped data access for producer/ASP/reviewer/admin; implement auditable policy changes and regression tests for privilege boundaries.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.04 | Data classification + privacy controls (PII, financial, agronomic) | Compliance Lead; Data Architect; Security Engineer | 260 | Define data classification for PII, financial/payment metadata, crop/practice data, documents, and logs; implement masking/redaction rules, access logging, and privacy-by-design constraints (least collection, least retention).
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.05 | Encryption-at-rest and key management (Key Vault/HSM-backed keys) | Cloud Security Engineer; Cloud Architect; DevOps Engineer | 220 | Configure encryption at rest for databases, blobs, queues; define key rotation schedules, separation of duties, and managed identity-based access to keys; validate backups and encryption posture.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.06 | Network security posture (private endpoints, firewalling, egress control) | Cloud Security Engineer; DevOps Engineer; SRE | 300 | Implement network segmentation, private endpoints for data stores, WAF rules, IP allowlists where appropriate, and controlled egress for third-party integrations (payment, identity, messaging); verify with connectivity tests.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.07 | Secure file upload pipeline (malware scanning, content validation) | Security Engineer; Backend Engineer; DevOps Engineer | 300 | Add malware scanning and quarantine workflow; enforce file type/size limits, content-type validation, and signed URL access controls; implement non-repudiation metadata for audit trails.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.08 | Application security testing program (SAST/DAST + dependency scanning) | Security Engineer; DevOps Engineer | 330 | Integrate SAST, dependency/CVE scanning, secrets scanning, container image scanning, and scheduled DAST against deployed environments; define severity thresholds and remediation SLAs.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.09 | Penetration testing + remediation cycles (annual / major releases) | Security Engineer; Project Manager; Backend Engineer | 290 | Plan and execute penetration tests (internal and/or external vendor) around major releases; triage findings, remediate vulnerabilities, and update security baselines; capture evidence for compliance and audit.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.10 | Audit logging + immutable event trail (grant workflow + payments) | Backend Engineer; SRE; Compliance Lead | 390 | Implement immutable audit event logging for user actions, reviewer decisions, admin configuration changes, and payment events; ensure logs are protected, queryable for admins, and retained per NDWEE/EPA requirements.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.11 | Privacy compliance workflow support (requests, retention, data export) | Compliance Lead; Backend Engineer; Support Specialist | 210 | Implement operational processes and tooling for privacy-related requests (data access/export/rectification where applicable), retention controls, and controlled deletion of non-required data while preserving immutable audit records.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.12 | Secure secrets management + rotation (payment keys, API credentials) | Cloud Security Engineer; DevOps Engineer; Backend Engineer | 250 | Centralize secrets in secrets manager / Key Vault; implement rotation for payment gateway keys, API client secrets, SMTP/SMS credentials; restrict access via managed identities and least privilege.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.13 | Incident response playbooks + on-call procedures | SRE; Security Engineer; Support Specialist | 220 | Define and document incident response playbooks for auth compromise, data exfiltration, payment fraud alerts, and service outages; implement paging/alerting thresholds, escalation paths, and postmortem review/remediation process.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.14 | Fraud detection controls (duplicate submissions, anomaly flags) | Backend Engineer; Data Engineer; Security Engineer | 340 | Implement rules and analytics hooks to flag duplicate field submissions, suspicious document patterns, ownership mismatches, and anomalous payment behavior; integrate with reviewer escalation workflows and audit trails.
Grant Program Interface Platform | 2.2 | Data Security and Privacy | 2.2.15 | Security governance over 3-year delivery (policy updates + reviews) | Compliance Lead; Security Engineer; Project Manager | 330 | Ongoing security governance: quarterly risk reviews, policy updates, access reviews, training coordination, and evidence capture for audits; ensure security posture keeps pace with feature delivery and integrations.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.01 | Payment workflow requirements + provider selection support | Finance Ops Analyst; Product Manager; Solution Architect | 170 | Confirm payment lifecycle requirements (approval gates, KYC/W‑9 handling, escrow, payouts, reversals), identify candidate payment providers, and define integration constraints and compliance obligations.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.02 | Payment data model + ledger strategy | Backend Engineer; Data Architect; Finance Ops Analyst | 220 | Define payment metadata schema, idempotent transaction IDs, ledger fields, reconciliation strategy, and audit-friendly snapshotting of payment decisions and disbursements.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.03 | Payment gateway integration (API + auth + webhooks) | Payment Integration Engineer; Backend Engineer; DevOps Engineer | 530 | Integrate selected payment gateway for initiating payouts, verifying payout status, and handling provider callbacks/webhooks; implement secure key storage, webhook signature verification, and retry/dead-letter handling.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.04 | Producer bank verification / payout authorization UX | Frontend Engineer; Backend Engineer; Payment Integration Engineer | 390 | Implement producer-facing flow to connect/verify bank account (as applicable), capture payout authorization, and display payment status history; handle edge cases and re-verification.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.05 | Admin payment approval queue + controls | Frontend Engineer; Backend Engineer; Finance Ops Analyst | 390 | Build NDWEE admin payment queue for approving payments, viewing incentive calculation justification, verifying required documentation, and initiating payouts; include batch actions, holds, and escalation notes.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.06 | Reconciliation + reporting exports (payments, tax season artifacts) | Backend Engineer; Data Engineer; Finance Ops Analyst | 370 | Implement reconciliation jobs and export generation for payment history, disbursement reports, and tax-season support artifacts (e.g. W‑9 collection tracking) with scheduled automation.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.07 | Payment failure handling (retries, reversals, dispute workflows) | Backend Engineer; Support Specialist; Finance Ops Analyst | 300 | Implement robust failure modes: automated retries, payout cancellation/reversal paths, dispute ticket creation, and producer/admin notifications; maintain audit trail for each exception.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.08 | Security/compliance validation for payment integration | Security Engineer; Compliance Lead; Payment Integration Engineer | 220 | Validate payment integration against security and compliance requirements (PII handling, encryption, access controls, least privilege); ensure logging is sufficient for audits without exposing sensitive data.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.09 | Load/performance testing for payout events + peak periods | QA Engineer; SRE; Backend Engineer | 210 | Test payout processing at scale (batch payouts, callback storms, end-of-year reporting); tune queues, database throughput, and alerting thresholds to prevent delays and outages.
Grant Program Interface Platform | 2.3 | Payment Processing Integration | 2.3.10 | Ongoing payment operations support (Year 2–3 enhancements) | Finance Ops Analyst; Backend Engineer; Support Specialist | 370 | Enhance payment ops based on production feedback: improved batching, automation of approvals, richer reconciliation dashboards, provider changes, and rule updates for evolving program requirements.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.01 | QA strategy + test plan aligned to NDWEE QAPP | QA Lead; Project Manager; Solution Architect | 250 | Define QA strategy, coverage, environments, and evidence artifacts; align to NDWEE Quality Assurance Project Plan (QAPP) requirements; establish beta readiness gates and test reporting cadence.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.02 | Automated unit/integration test suite (APIs + UI) | QA Engineer; Backend Engineer; Frontend Engineer | 320 | Implement automated tests for critical grant workflows (apply/submit/review/decision/payment status), API contracts, permissions boundaries, and regression coverage; integrate into CI/CD with fail gates.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.03 | End-to-end test automation (role-based flows) | QA Engineer; QA Lead; SRE | 240 | Create E2E automated scenarios covering producer/ASP/reviewer/admin personas, including file uploads, queue assignment, review actions, and payout initiation; run in nightly pipelines and pre-release gates.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.04 | Data quality validation for reporting and exports | Data Engineer; QA Engineer; Data Analyst | 160 | Validate that transactional events correctly feed analytics/reporting layers; test report accuracy, filtering, aggregation correctness, and export format mappings; implement automated data checks and anomaly alerts.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.05 | Performance + load testing (submissions, uploads, review queues) | QA Engineer; SRE; Backend Engineer | 150 | Conduct load tests for peak events (grant window closing, high-volume uploads, payment runs); tune services, storage, and database throughput; define SLOs and capacity plans.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.06 | Security testing (DAST runs + authZ regression tests) | Security Engineer; QA Engineer; DevOps Engineer | 380 | Execute scheduled DAST, validate security controls, and run regression tests for authorization rules; verify that security patches do not break critical flows and that high-risk findings are triaged and remediated.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.07 | Accessibility testing (WCAG) + remediation | QA Engineer; UX/UI Designer; Frontend Engineer | 250 | Audit accessibility for all platform surfaces (producer, ASP, admin, reviewer) and key flows; remediate issues related to navigation, forms, contrast, and screen readers; maintain regression testing at regular frequency.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.08 | UAT facilitation + defect triage | Project Manager; QA Lead; Product Manager | 330 | Plan and run NDWEE user acceptance testing cycles; coordinate feedback sessions, prioritize defect fixes, and maintain transparent release readiness dashboards and burn-down.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.09 | Release validation + deployment smoke testing | QA Engineer; DevOps Engineer; SRE | 300 | Implement pre/post-deploy smoke tests, rollback validation, and environment health checks; verify telemetry and alerts after releases; maintain stable release process across environments.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.10 | Change readiness for upgrades + future integrations (e.g., carbon markets) | Solution Architect; QA Lead; Backend Engineer | 330 | Validate platform extensibility through upgrade testing, API versioning validation, and integration test harness; ensure new features can be added without destabilizing core grant operations.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.11 | Operational readiness testing (monitoring, backups, DR) | SRE; DevOps Engineer; QA Engineer | 340 | Test monitoring/alerting, backup/restore, disaster recovery runbooks, and failover behavior; verify RPO/RTO objectives and document results for audit evidence.
Grant Program Interface Platform | 2.4 | System Validation and Quality Assurance | 2.4.12 | QA over 3-year delivery (regression + continuous improvement) | QA Lead; QA Engineer; Project Manager | 620 | Sustain QA coverage as features evolve: regression suites, test data management, environment maintenance, and periodic refresh of test plans; support multiple program years and changing requirements.
Grant Program Interface Platform | 2.5 | User Training & Support | 2.5.01 | Training strategy + curriculum design (producer, ASP, admin, reviewer) | Product Manager; Technical Writer; Support Specialist | 170 | Define role-specific training tracks and learning objectives; outline training plan for beta launch and ongoing onboarding for new programs/users across Years 2–3.
Grant Program Interface Platform | 2.5 | User Training & Support | 2.5.02 | User manuals + step-by-step guides (web + PDF) | Technical Writer; UX/UI Designer | 80 | Create and maintain user manuals with screenshots, walkthroughs, and troubleshooting guides for the producer portal, ASP enrollment, admin configuration, and reviewer workflows.
Grant Program Interface Platform | 2.5 | User Training & Support | 2.5.03 | Video tutorials + microlearning clips (hosted via CDN) | Technical Writer; Developer Advocate; Support Specialist | 30 | Produce short tutorial videos and guided demos for common workflows; optimize formats for device playback and host via CDN with versioning per program year.
Grant Program Interface Platform | 2.5 | User Training & Support | 2.5.04 | Help center / knowledge base + FAQs | Support Specialist; Technical Writer; Frontend Engineer | 140 | Build self-service help center with searchable articles, FAQs, and contextual help links embedded in the application; integrate escalation path to support ticket creation.
Grant Program Interface Platform | 2.5 | User Training & Support | 2.5.05 | Support desk setup (email/phone/chat ticketing + triage) | Support Specialist; Backend Engineer; DevOps Engineer | 300 | Implement multi-channel support intake into a single ticketing system with categorization, SLAs, routing by role/issue type, and auditable support metrics; integrate notifications and admin views.
Grant Program Interface Platform | 2.5 | User Training & Support | 2.5.06 | Go-live enablement + onboarding sessions | Project Manager; Support Specialist; Product Manager | 30 | Run live onboarding webinars and office hours for producers/ASPs; coordinate NDWEE admin training and reviewer training sessions; collect feedback to refine documentation and product UX.
Grant Program Interface Platform | 2.5 | User Training & Support | 2.5.07 | Ongoing training refresh (Year 2–3 program updates) | Technical Writer; Support Specialist; Product Manager | 50 | Maintain and refresh training materials and help center content as program rules, features, or integrations evolve; track content gaps and align updates to release cycles.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.01 | Reporting requirements + KPI definition (NDWEE/EPA) | Product Manager; Data Analyst; Compliance Lead | 210 | Define reporting KPIs and dimensions (submissions, cropping trends, approvals, payments, geographies, ASP performance) and align to NDWEE/EPA reporting templates/timelines; establish audit evidence expectations.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.02 | Analytics architecture (OLTP → lakehouse → semantic layer) | Data Architect; Data Engineer; BI Developer | 340 | Design and implement analytical store patterns: ingest transactional events, build bronze/silver/gold datasets, maintain governed semantic models, and support time-versioned snapshots for audit and public recordkeeping.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.03 | ETL/ELT pipelines + data quality checks | Data Engineer; DevOps Engineer; QA Engineer | 530 | Build automated pipelines to mirror/replicate transactional data into analytics environment, transform into curated reporting tables, and run data quality checks; manage schema evolution and backfills.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.04 | Admin reporting dashboards (interactive drilldowns) | BI Developer; Data Analyst; Frontend Engineer | 620 | Create dashboards for program administrators with filters/drilldowns by program, timeframe, geography (town/county/region), ASP, practice categories, review status, and payment issued; support exports and scheduled distribution.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.05 | Custom report builder + templated exports | BI Developer; Data Engineer; Product Manager | 470 | Implement a governed custom reporting capability (parameterized queries, saved views, templated exports) with role-based access controls and schema versioning; map exports to NDWEE/EPA-required formats where applicable.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.06 | Audit trail surfacing + traceable report snapshots | Data Engineer; Compliance Lead; SRE | 420 | Provide tooling to generate traceable report snapshots and link outputs to the underlying immutable event trail (ingestion, scoring, review actions, payments, exports); ensure reproducibility for audits/evaluations.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.07 | Data sharing views for stakeholders (least privilege) | Security Engineer; BI Developer; Data Architect | 300 | Create controlled data-sharing views for EPA/NDWEE stakeholders, including scoped exports and access-controlled dashboards; implement least-privilege roles and monitoring for data access.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.08 | Longitudinal evaluation support (multi-year analysis) | Data Analyst; Data Scientist; Data Engineer | 390 | Enable multi-year cohort analysis and evaluation metrics (practice adoption trends, estimated CI reductions, soil/land outcomes as defined), with versioned methodology and transparent assumptions.
Grant Program Interface Platform | 2.6 | Data Reporting and Analytics | 2.6.09 | Ongoing reporting enhancements (Year 2–3) | BI Developer; Data Engineer; Compliance Lead | 500 | Iterate on dashboards, exports, and data models based on stakeholder feedback; add new KPIs and program types; maintain compatibility with changing guidance and reporting timelines.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.01 | SRE/DevOps runbooks + operational baseline | SRE; DevOps Engineer; Technical Writer | 250 | Create operational runbooks for deployments, incident response, backups/restores, queue draining, and common failure scenarios; establish baseline SLOs and operational KPIs.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.02 | Monitoring + alerting (99.5% uptime target) | SRE; DevOps Engineer; Backend Engineer | 530 | Implement comprehensive monitoring (APM, logs, metrics) and alerting for portal/API services, data pipelines, and third-party integrations; tune alerts for actionable signal and align to 99.5% uptime objectives.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.03 | Patch management + dependency updates (monthly cadence) | DevOps Engineer; Security Engineer; Backend Engineer | 180 | Maintain secure update cadence for OS/container base images, dependencies, and cloud resources; triage CVEs, test patches, and deploy safely with regression validation.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.04 | Continuous security scanning program (SAST/DAST) + evidence capture | Security Engineer; DevOps Engineer; Compliance Lead | 90 | Run ongoing security scans, manage findings, and capture evidence for audits; ensure remediation SLAs are met and high-risk issues are escalated appropriately.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.05 | Release management + change control (PR gates + changelogs) | Project Manager; DevOps Engineer; Technical Lead | 120 | Operate disciplined change control: PR approvals, gated deployments, release notes/changelogs for technical and business stakeholders, and structured deprecation plans for versioned APIs.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.06 | Performance optimization + capacity planning (seasonal peaks) | SRE; Cloud Architect; FinOps Analyst | 60 | Forecast peak demand (grant windows, payment runs, reporting deadlines), tune autoscaling and quotas, and optimize cost/performance; conduct periodic load tests and adjust capacity plans.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.07 | Incident response + postmortems + continuous improvement | SRE; Support Specialist; Security Engineer | 120 | Operate on-call rotation, triage incidents, communicate status to stakeholders, complete postmortems, and drive follow-up fixes; maintain incident metrics and lessons learned.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.08 | Helpdesk operations integration (tickets → backlog) | Support Specialist; Project Manager; Product Manager | 80 | Operationalize support: triage tickets, route to engineering backlog, monitor SLA compliance, and identify recurring UX issues; feed continuous improvement cycle.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.09 | Data governance + schema evolution support | Data Engineer; Data Architect; Compliance Lead | 220 | Manage schema changes across transactional and analytics stores; maintain dataset versioning, migration plans, backfills, and data contract compatibility for ASP integrations and stakeholder reporting.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.10 | Vendor/integration maintenance (payment, identity, messaging) | DevOps Engineer; Backend Engineer; Finance Ops Analyst | 280 | Maintain integrations with external providers (identity, payment gateway, email/SMS); handle provider API changes, credential rotation, rate limit management, and resiliency improvements.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.11 | Feature enhancements based on user feedback (Year 2–3) | Product Manager; Backend Engineer; Frontend Engineer | 200 | Plan and deliver post-launch enhancements and new features driven by user feedback and evolving program requirements; manage prioritization and scope within agreed change budget.
Grant Program Interface Platform | 2.7 | Maintenance and Updates | 2.7.12 | Annual compliance/audit support (evidence, attestations, reviews) | Compliance Lead; Security Engineer; Data Analyst | 390 | Support annual audit/evaluation cycles: evidence collection, access reviews, report reproducibility, documentation updates, and stakeholder coordination; ensure audit readiness remains continuous.
Program Support | 3.1 | System Design & Development | 3.1.01 | Program support operating model + service catalog (tiers, channels, SLAs) | Program Manager; Support Operations Lead; Project Manager | 290 | Define program support services across producer/ASP/admin personas: intake channels, ticket categories, severity levels, SLAs, escalation paths, and handoffs to engineering/finance/compliance. Y1: 420h; Y2: 200h; Y3: 100h.
Program Support | 3.1 | System Design & Development | 3.1.02 | Support tooling architecture (ticketing, knowledge base, CRM-style case management) | Support Operations Lead; Solution Architect; DevOps Engineer | 150 | Select/configure ticketing + case management tooling, SSO integration, role-based views (producer vs ASP vs admin), and automation (routing, macros, templates). Y1: 540h; Y2: 200h; Y3: 120h.
Program Support | 3.1 | System Design & Development | 3.1.03 | Producer intake + eligibility pre-screen assistance workflow design | Program Manager; Business Analyst; Support Specialist | 160 | Design SOPs and scripts for helping producers understand eligibility, required documents, and next steps; define “assisted application” boundaries and audit notes; integrate into case workflows. Y1: 420h; Y2: 220h; Y3: 120h.
Program Support | 3.1 | System Design & Development | 3.1.04 | ASP partner enablement process (onboarding, certification, renewals) | Developer Advocate; Program Manager; Support Specialist | 80 | Define ASP onboarding pipeline: registration, sandbox certification, change notices, annual renewals, and partner scorecards; includes webinar cadence and shared issue tracking. Y1: 460h; Y2: 320h; Y3: 200h.
Program Support | 3.1 | System Design & Development | 3.1.05 | Field/geo support playbooks (field selection, boundary/CLU questions, mapping issues) | Geospatial Specialist; Support Specialist; QA Engineer | 330 | Create SOPs for geospatial issues: field selection, boundary disputes, mapping/UI issues, CLU alignment questions, and data correction requests; define escalation to geospatial engineering. Y1: 380h; Y2: 280h; Y3: 160h.
Program Support | 3.1 | System Design & Development | 3.1.06 | Document review assistance SOPs (missing info, verification queues, producer outreach) | Program Manager; Compliance Lead; Support Specialist | 390 | Create processes for identifying missing/invalid documentation, contacting producers, tracking resubmissions, and documenting decisions; ensure audit-friendly notes and standardized communications. Y1: 420h; Y2: 360h; Y3: 200h.
Program Support | 3.1 | System Design & Development | 3.1.07 | Outreach + communications plan (grant window comms, reminders, adoption campaigns) | Communications Lead; Program Manager; UX Writer | 420 | Develop outreach plan: grant opening/closing campaigns, reminder schedules, targeted outreach to low-participation regions, and ASP communications; maintain template library. Y1: 420h; Y2: 340h; Y3: 280h.
Program Support | 3.1 | System Design & Development | 3.1.08 | Assisted onboarding sessions + office hours (producers/ASPs) | Support Specialist; Training Lead; Program Manager | 120 | Run recurring office hours and assisted onboarding (virtual) during application windows and onboarding waves; track attendance and outcomes; feed UX improvements. Y1: 100h; Y2: 100h; Y3: 100h.
Program Support | 3.1 | System Design & Development | 3.1.09 | Case management automation (routing rules, queues, macros, templates) | Support Operations Lead; DevOps Engineer | 300 | Build automation within ticketing/case tooling: auto-routing, SLA timers, escalation rules, standardized macros, and bulk communications; tune iteratively. Y1: 340h; Y2: 240h; Y3: 160h.
Program Support | 3.1 | System Design & Development | 3.1.10 | Program governance cadence (weekly ops review, risk log, change control) | Project Manager; Program Manager; Compliance Lead | 150 | Operate governance rhythms: weekly operations review, monthly KPI review, risk/issue log maintenance, change requests, and stakeholder reporting across 3 years
Program Support | 3.1 | System Design & Development | 3.1.11 | Integration coordination support (identity/payment/ASP) – cross-team incident triage | Support Operations Lead; SRE; Backend Engineer | 60 | Coordinate issue triage spanning identity verification, ASP submissions, and payment providers; maintain incident checklists and stakeholder comms; drive root cause and prevention tasks
Program Support | 3.1 | System Design & Development | 3.1.12 | Continuous improvement backlog management (support → product feedback loop) | Product Manager; Support Operations Lead; Data Analyst | 110 | Maintain structured feedback loop: tag tickets, analyze top issues, propose product/process changes, validate impact post-release; quarterly prioritization cycles
Program Support | 3.2 | Data Security and Privacy | 3.2.01 | Support data handling policy (PII/financial/agronomic) + staff training | Compliance Lead; Security Engineer; Support Operations Lead | 250 | Define what data support staff may collect/store, approved channels, redaction rules, and retention; run annual security/privacy training for support staff.
Program Support | 3.2 | Data Security and Privacy | 3.2.02 | Role-based access controls for support tools (least privilege + audit) | Security Engineer; DevOps Engineer; Support Operations Lead | 300 | Implement SSO/RBAC for ticketing/CRM tools, enforce least privilege (producer-facing staff vs escalations), and enable audit logs for access and changes.
Program Support | 3.2 | Data Security and Privacy | 3.2.03 | Secure communications standards (email/SMS scripts, PII avoidance, encryption) | Compliance Lead; Communications Lead; Security Engineer | 210 | Create approved message templates and rules for avoiding sensitive data in insecure channels; configure secure forms/attachments where needed; periodic template review.
Program Support | 3.2 | Data Security and Privacy | 3.2.04 | Ticket attachment security (virus scan, quarantines, access controls) | Security Engineer; DevOps Engineer | 220 | Configure safe handling of ticket attachments: malware scanning, quarantine/approval flow, restricted downloads, and data-loss-prevention patterns where supported.
Program Support | 3.2 | Data Security and Privacy | 3.2.05 | Incident response procedures for support org (credential compromise, phishing, fraud) | Security Engineer; SRE; Support Operations Lead | 270 | Define playbooks and drills for support-led security events (phishing reports, suspected account takeover, fraud claims); integrate with core incident response.
Program Support | 3.2 | Data Security and Privacy | 3.2.06 | Periodic access reviews + compliance evidence for support operations | Compliance Lead; Support Operations Lead | 220 | Quarterly access reviews for support tooling, evidence capture, policy attestations, and exception management; align to annual audit cycles.
Program Support | 3.2 | Data Security and Privacy | 3.2.07 | Fraud/abuse safeguards in support workflows (identity/payment disputes) | Security Engineer; Finance Ops Analyst; Support Specialist | 290 | Implement verification steps for sensitive changes (bank updates, payout disputes), add escalation requirements, and ensure tamper-evident notes and approvals.
Program Support | 3.2 | Data Security and Privacy | 3.2.08 | Data retention + deletion workflows for support artifacts | Compliance Lead; DevOps Engineer | 210 | Configure retention for tickets, recordings, chat logs, and attachments; implement deletion workflows for non-required data while preserving audit trails where mandated.
Program Support | 3.3 | Payment Processing Integration | 3.3.01 | Payment support SOPs (status explanations, timelines, holds, retries) | Finance Ops Analyst; Support Specialist; Program Manager | 300 | Create standardized scripts and workflows for payment questions, payout timing, and common failure reasons; define when/why holds occur and how to resolve.
Program Support | 3.3 | Payment Processing Integration | 3.3.02 | Payment exception handling queue (triage + coordination with provider) | Finance Ops Analyst; Backend Engineer; Support Specialist | 530 | Operate triage queue for payment exceptions: failed payouts, returned ACH, KYC issues, bank changes; coordinate with provider support, capture resolution evidence.
Program Support | 3.3 | Payment Processing Integration | 3.3.03 | Reconciliation operations (monthly close, discrepancy resolution, audit pack) | Finance Ops Analyst; Data Analyst; Compliance Lead | 390 | Monthly reconciliation between platform records and payment provider statements; resolve discrepancies, generate summaries, and produce audit-ready evidence packs.
Program Support | 3.3 | Payment Processing Integration | 3.3.04 | Tax-season readiness support (W‑9 tracking, 1099 export validation, inquiries) | Finance Ops Analyst; Compliance Lead; Support Specialist | 160 | Support tax-season operations: ensure W‑9 collection completeness, respond to producer inquiries, and manage corrections
Program Support | 3.3 | Payment Processing Integration | 3.3.05 | Payment policy updates (thresholds, batching, new program rules) | Program Manager; Finance Ops Analyst; Product Manager | 250 | Update payment workflows as program rules evolve (batching cadence, approval thresholds, new incentive types); update training/docs and validate downstream reporting impacts.
Program Support | 3.3 | Payment Processing Integration | 3.3.06 | Dispute and appeals workflow for payments (producer-facing) | Program Manager; Support Specialist; Compliance Lead | 300 | Define and operate dispute/appeal workflows for payment-related issues; track tickets, decision history, and outcomes; ensure fairness and transparency while preserving audit trails.
Program Support | 3.4 | System Validation and Quality Assurance | 3.4.01 | Support quality management program (QA scoring rubric + coaching) | Support Operations Lead; QA Lead | 300 | Define QA rubric for support interactions (accuracy, compliance, empathy, resolution), run sampling and coaching cycles, and maintain continuous improvement actions.
Program Support | 3.4 | System Validation and Quality Assurance | 3.4.02 | Process audits of program operations (application, review, payment SOP adherence) | Compliance Lead; Program Manager; QA Lead | 390 | Quarterly audits of operational processes, verifying SOP adherence, completeness of audit notes, and consistent decisioning; document findings and corrective actions.
Program Support | 3.4 | System Validation and Quality Assurance | 3.4.03 | Data quality assurance for assisted workflows (manual corrections, overrides) | Data Analyst; QA Engineer; Support Specialist | 330 | Validate that manual support interventions (data corrections, overrides, field merges) are accurate, documented, and reversible; implement double-check processes for high-risk changes.
Program Support | 3.4 | System Validation and Quality Assurance | 3.4.04 | Knowledge base QA + content governance (accuracy, versioning) | Technical Writer; Support Operations Lead; Product Manager | 250 | Validate help content accuracy against current system behavior and program rules; manage versioning by program year; retire outdated articles; quarterly refresh cycles.
Program Support | 3.4 | System Validation and Quality Assurance | 3.4.05 | Operational readiness drills (grant window peaks, payment run peaks) | Program Manager; Support Operations Lead; SRE | 300 | Run readiness drills before peak periods: staffing plans, queue routing, scripts, escalation paths, and comms templates; update based on drill outcomes.
Program Support | 3.4 | System Validation and Quality Assurance | 3.4.06 | Customer feedback loops & action planning | UX Researcher; Support Operations Lead; Data Analyst | 270 | Implement customer satisfaction surveys and feedback capture, analyze trends by persona/program, and translate into action plans (process improvements + product backlog).
Program Support | 3.5 | User Training & Support | 3.5.01 | Onboarding kits and checklists (producer + ASP) | Training Lead; Technical Writer; Support Specialist | 300 | Create onboarding kits (checklists, templates, “what to prepare”), tailored for producers and ASPs; update annually by program year and major feature changes.
Program Support | 3.5 | User Training & Support | 3.5.02 | Live training delivery (webinars, office hours, cohort onboarding) | Training Lead; Program Manager; Support Specialist | 120 | Deliver live trainings: grant window kickoff webinars, ASP integration sessions, reviewer trainings, and monthly office hours; record and publish sessions.
Program Support | 3.5 | User Training & Support | 3.5.03 | Help content creation + maintenance (articles, FAQs, troubleshooting) | Technical Writer; Support Operations Lead | 180 | Author and maintain knowledge base articles, FAQs, and troubleshooting guides; incorporate product changes and ticket learnings; ensure accessibility (captions/alt text)
Program Support | 3.5 | User Training & Support | 3.5.04 | Support desk staffing (ticket triage + resolution) | Support Specialist; Support Operations Lead | 2080 | Operate day-to-day support desk: intake, triage, resolution, and escalations across producers/ASPs/admins; includes peak-window staffing and after-hours coverage planning.
Program Support | 3.5 | User Training & Support | 3.5.05 | Reviewer/admin training + refresh cycles | Training Lead; Program Manager; Compliance Lead | 330 | Train NDWEE reviewers/admins on queue management, decision standards, audit notes, and payment controls; conduct refresh sessions for new program years and staff turnover.
Program Support | 3.5 | User Training & Support | 3.5.06 | Change communications + release notes for program support org | Program Manager; Technical Writer; Release Manager | 250 | Produce internal change communications and external user-facing notices for major changes; maintain comms calendar aligned with release and grant window schedules.
Program Support | 3.5 | User Training & Support | 3.5.07 | Community of practice + partner forums (ASPs) | Developer Advocate; Program Manager | 310 | Run quarterly partner forums for ASPs, publish best practices, share integration updates, and collect partner feedback; coordinate issue resolution and roadmap transparency.
Program Support | 3.6 | Data Reporting and Analytics | 3.6.01 | Support KPI dashboarding (volume, SLA, deflection, backlog health) | Data Analyst; Support Operations Lead; BI Developer | 300 | Define and build operational dashboards for program support: ticket volumes by category, SLA compliance, backlog aging, deflection rates, and escalation patterns; monthly review cadence.
Program Support | 3.6 | Data Reporting and Analytics | 3.6.02 | Peak-period forecasting + staffing analytics | Data Analyst; Program Manager | 50 | Model support demand around grant window peaks and payment cycles; recommend staffing/coverage plans; evaluate forecast accuracy and refine
Program Support | 3.6 | Data Reporting and Analytics | 3.6.03 | Root-cause analytics (top issues → product/process fixes) | Data Analyst; Product Manager; Support Operations Lead | 330 | Analyze recurring ticket drivers, quantify impact, propose remediation (UX, docs, automation), and track reduction over time; quarterly OKRs.
Program Support | 3.6 | Data Reporting and Analytics | 3.6.04 | Program participation reporting support (region gaps, ASP performance) | Data Analyst; Program Manager; BI Developer | 300 | Create program ops reports: participation trends, gaps by geography, ASP submission success rates, and bottleneck heatmaps; inform outreach strategies.
Program Support | 3.6 | Data Reporting and Analytics | 3.6.05 | Payment ops analytics (exceptions, holds, cycle time) | Finance Ops Analyst; Data Analyst | 250 | Track payment cycle times, exception reasons, hold durations, and reversal rates; identify automation opportunities and policy improvements.
Program Support | 3.6 | Data Reporting and Analytics | 3.6.06 | Annual evaluation support packs (ops metrics + narratives) | Program Manager; Compliance Lead; Data Analyst | 270 | Produce annual operational evaluation packs: KPIs, trends, major incidents, improvements delivered, and evidence summaries; coordinate with audit/reporting timelines.
Program Support | 3.7 | Maintenance and Updates | 3.7.01 | Support tooling maintenance (workflows, automations, integrations) | Support Operations Lead; DevOps Engineer | 390 | Maintain ticketing/CRM workflows, routing rules, macros, integrations, and automation scripts; accommodate program-year changes and new user personas.
Program Support | 3.7 | Maintenance and Updates | 3.7.02 | SOP updates for new program years (eligibility, artifacts, decision standards) | Program Manager; Compliance Lead; Technical Writer | 340 | Update SOPs and decision standards annually as program rules evolve; publish change summaries and train staff on deltas; maintain versioned SOP library.
Program Support | 3.7 | Maintenance and Updates | 3.7.03 | Escalation playbook maintenance (identity, ASP, payment, security) | Support Operations Lead; Security Engineer; SRE | 300 | Keep escalation playbooks current as vendors and systems evolve; run semiannual drills and incorporate lessons learned from incidents.
Program Support | 3.7 | Maintenance and Updates | 3.7.04 | Automation enhancements (self-serve, bot workflows, proactive alerts) | Support Operations Lead; Backend Engineer; Data Analyst | 450 | Implement and refine self-serve automations: proactive status alerts, guided troubleshooting, and bot-assisted ticket triage; measure deflection and iterate.
Program Support | 3.7 | Maintenance and Updates | 3.7.05 | Knowledge base lifecycle management (retire/refresh, content debt) | Technical Writer; Support Operations Lead | 250 | Quarterly content review cycles, retire outdated pages, refresh screenshots, and manage content debt backlog; ensure accessibility and translation readiness.
Program Support | 3.7 | Maintenance and Updates | 3.7.06 | Continuous improvement releases to ops processes | Program Manager; Support Operations Lead; Project Manager | 330 | Run structured improvement cycles for queues, SLAs, and handoffs; implement process changes, measure results, and standardize improvements across teams.
Category Total
[5 empty] | Hours | 83890
[5 empty] | Rate | 150
[5 empty] | Total Cost | 12583500

## Pass-Through Costs
RFP 124065 O5 – ONE RED Ag Data Bank and Grants Program - Incite AgPro LLC (“incite.ag”) - Itemized Pass-Through Costs
Cost Group | Provider | Category | Service | Pricing Model | Unit Rate | Unit | Qty Y1 | Qty Y2 | Qty Y3 | Monthly Baseline Y1 ($) | Monthly Baseline Y2 ($) | Monthly Baseline Y3 ($) | One-time Y1 | One-time Y2 | One-time Y3 | Year 1 Total ($) | Year 2 Total ($) | Year 3 Total ($) | 3-Year Total ($) | Notes / Cost Drivers
Security | InfoSec | Security | Security posture, annual audit/pen test, compliance support | annual | 10000 | $/mo | 1 | 1 | 1 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 120000 | 120000 | 120000 | 360000 | Represented as monthly equivalent in source file; treat as annual program cost (e.g. $120k/year) covering audits, pen tests, policy/evidence support.
Identity | ID.me | Security | Identity verification (OIDC gateway) | per_verification | 3.5 | $/verified user | 2000 | 5000 | 8000 |  |  |  | 20000 | 0 | 0 | 27000 | 17500 | 28000 | 72500 | Includes vendor onboarding ($20k) in Y1 and per-user verification fee. Driver: # of unique producers requiring verification (re-verifications may add).
Payments | PayPal | Payment | Hyperwallet payouts (disbursements) | per_payout | 2 | $/payout | 1500 | 4000 | 6000 |  |  |  | 20000 | 0 | 0 | 23000 | 8000 | 12000 | 43000 | Includes onboarding ($20k) in Y1 and per-payout fee. Driver: number of payments; batching and payment schedule affect count.
Identity | ID.me | Security | Identity verification support / minimums (estimated retainer) | fixed | 1000 | $/mo | 1 | 1 | 1 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 36000 | Some providers require monthly minimums/retainers. Replace with actual contract terms or set to 0 if none.
Cloud Core | Azure | Application | App hosting (web/API services) | variable | 300 | $/mo | 2 | 5 | 5 | 600 | 1500 | 1500 | 0 | 0 | 0 | 7200 | 18000 | 18000 | 43200 | App Service/Container Apps hosting per env. Driver: number of services, CPU/memory, autoscale, uptime requirements.
Support Tooling | Vendor TBD | Application | Ticketing/Helpdesk (Zendesk/Freshdesk/etc.) TBD | per_agent | 75 | $/agent/mo | 10 | 12 | 14 | 750 | 900 | 1050 | 0 | 0 | 0 | 9000 | 10800 | 12600 | 32400 | Driver: number of support agents/reviewers needing seats; includes automations and knowledge base modules.
ML/AI | Azure/GCP | Application | ML inference (GPU container apps) | variable | 800 | $/mo | 1 | 1 | 1 | 800 | 800 | 800 | 0 | 0 | 0 | 9600 | 9600 | 9600 | 28800 | Driver: GPU hours, concurrency, model size. If only used during batch scoring, switch to scheduled/batch compute to cut costs.
Analytics | Azure | Application | Data Warehouse / Synapse/Databricks (TBD) | variable | 800 | $/mo | 1 | 1 | 1 | 800 | 800 | 800 | 0 | 0 | 0 | 9600 | 9600 | 9600 | 28800 | Warehouse/lakehouse is used for analytics at scale. Driver: compute hours, concurrency, storage, and BI refresh schedules.
Payments | PayPal | Payment | Hyperwallet platform minimums/retainer | fixed | 100 | $/mo | 1 | 1 | 1 | 100 | 100 | 100 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 3600 | Potential monthly minimum/retainer; replace with contract terms. Does not include pass-through payment processing (ACH/card) fees if applicable.
Cloud Core | Azure | Data Storage | Azure SQL Database (configuration, reporting ops tables) | fixed | 200 | $/mo/db | 1 | 3 | 3 | 200 | 600 | 600 | 0 | 0 | 0 | 2400 | 7200 | 7200 | 16800 | SQL instance per environment; driver is vCores/DTUs, storage, HA/replicas.
Observability | Azure | Security | SIEM (Microsoft Defender / Azure Sentinel) | variable | 500 | $/mo | 1 | 1 | 1 | 500 | 500 | 500 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 18000 | Often required for audit/incident response; cost driver is log ingestion (GB/day) + retention.
Support Tooling | Vendor TBD or Internal | Application | Call center / VOIP (Aircall/etc.) TBD | per_user | 40 | $/agent/mo | 10 | 12 | 14 | 400 | 480 | 560 | 0 | 0 | 0 | 4800 | 5760 | 6720 | 17280 | If phone support is required. Driver: agent seats + minutes + recording retention.
Security | Azure | Security | Entra ID P1/P2 licenses | per_user | 9 | $/user/mo | 25 | 40 | 60 | 225 | 360 | 540 | 0 | 0 | 0 | 2700 | 4320 | 6480 | 13500 | Scale with NDWEE admin/reviewer/support accounts and internal operators. Adjust if using P2, B2C MAU, or external guest licensing.
Dev Tooling | Vendor TBD | Security | Dependency vulnerability monitoring (Snyk/Dependabot premium) | per_user | 30 | $/user/mo | 10 | 12 | 14 | 300 | 360 | 420 | 0 | 0 | 0 | 3600 | 4320 | 5040 | 12960 | Optional if not covered by GitHub Advanced Security; helps satisfy supply chain security expectations.
Cloud Core | Azure | Data Storage | Blob Storage / ADLS (data + documents) | variable | 100 | $/mo | 1 | 1 | 1 | 100 | 100 | 100 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 3600 | Baseline placeholder for storage account(s) per environment. Real driver is TB stored + transactions; add variable storage line-items once volumes are known.
Observability | Vendor TBD | Application | On-call + incident management (PagerDuty/Opsgenie) | per_user | 25 | $/user/mo | 10 | 12 | 14 | 250 | 300 | 350 | 0 | 0 | 0 | 3000 | 3600 | 4200 | 10800 | Driver: number of responders (SRE/engineering/ops). Often required for SLAs and incident response evidence.
Cloud Core | Azure | Data Storage | Cosmos DB NoSQL (grant apps, events, metadata) | variable | 20 | $/1000 RU/mo | 5 | 10 | 10 | 100 | 200 | 200 | 0 | 0 | 0 | 1200 | 2400 | 2400 | 6000 | Placeholder for Cosmos DB account per environment; real driver is RU/s + data size + regions (multi-region replication).
Dev Tooling | GitHub | Application | GitHub Enterprise/Advanced Security (repos + scanning) | per_user | 21 | $/user/mo | 10 | 12 | 14 | 210 | 252 | 294 | 0 | 0 | 0 | 2520 | 3024 | 3528 | 9072 | If using GH Advanced Security: secret scanning, code scanning, dependency review. Seat count scales with engineering + security roles.
Dev Tooling | System Provider | Security | Msft Intune managed development devices (laptops/desktops) | per_user | 1600 | $/user | 4 | 2 | 0 |  |  |  | 6400 | 3200 | 0 | 6400 | 3200 | 0 | 9600 | SOC2 / InfoSec control policies require managed developers devices with network access restrictions & software restrictions
Documents | Azure | Application | Document OCR/extraction (Azure API Foundry) | variable | 250 | $/mo | 1 | 1 | 1 | 250 | 250 | 250 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 9000 | Driver: pages processed; likely spiky around application windows. Consider batching and caching results.
Security | Vendor TBD | Security | Web application security scanning (SAST/DAST) | fixed | 250 | $/mo | 1 | 1 | 1 | 250 | 250 | 250 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 9000 | Automated scanning for OWASP Top 10; supports security posture and audit evidence.
[18 empty] | Total Pass-Through Costs | 774312