## Title Page
Nebraska Public Employees Retirement Systems |  | (NPERS)
Omaha School Employees Retirement System (OSERS) Transfer Project
Solution and Implementation Services Requirements Response Workbook

## Instructions
Nebraska Public Employees Retirement Systems (NPERS)
Omaha School Employees Retirement System (OSERS) Transfer Project
Instructions
This workbook provides the baseline of solution and implementation service requirements for future vendor(s) to configure the Omaha Public School (OPS) retirement plan in the Nebraska Public Retirement Information System (NPRIS). Bidder shall complete and submit the Solution and Implementation Services Requirements Workbook. The workbook contains the following information and response tabs: Tab 1. Requirements Categories Diagram (RCD) organizes similar requirements into various categories that reflect the OPS business processes that NPRIS will need to support going forward. The RCD is provided below for reference. The requirements provided on the Tab 2: Solution Requirements are organized by the categories identified in the RCD. No response required by the Bidder Tab 2. Solution Requirements details the business capabilities required to be implemented into NPRIS to help Bidders assess level of effort, timeframe, and other information needed to scope the work and put together a proposal. For each requirement, Bidders shall describe, generally, the process of how the bidder's solution will accomplish this requirement. Tab 3. Implementation Services Requirements outlines the high-level roles and responsibilities of both NPERS and the Bidder overall. For requirements denoted as the responsibility of the Bidder, Bidders shall describe, generally, the process of how the bidder's solution will accomplish this requirement. Response cells that are blacked out are for activities that are the responsibility of NPERS and do not require a bidder response.

## 1. RCD
Requirements Categories Diagram (RCD) - Overview of Categorization of Solution Requirements

## 2. Solution Requirements
Tab 2. Solution Requirements
Req ID | Business Capability Model (BCM) Level 0 | Business Capability Model (BCM) Level 1 | Sub-Category | Solution Requirement (SR) | Describe, generally, the process of how the bidder's solution will accomplish this requirement.
SR-1 | General Requirement | N/A | N/A | All system elements necessary to transfer the Omaha Public School (OPS) retirement plan into the Nebraska Public Retirement Information System (NPRIS) must be configured / developed by the successful respondent.
SR-2 | General Requirement | N/A | N/A | NPRIS must be configured to support all OPS benefit plans and tiers in NPRIS including but not limited to new development or modifications required to screens, forms, business rules, workflow, fields, letters, reports, document templates, interfaces, etc.
SR-3 | General Requirement | N/A | N/A | NPRIS must be configured so that new OPS members can be enrolled in their eligible retirement plan(s) via NPRIS.
SR-4 | Provide and Administer Benefits | Manage Eligibility & Enrollment | Identify Eligible Members | The OSERS plan and tiers and the reference tables that depend on them must be configured in NPRIS so that OSERS members' benefits are able to be managed in NPRIS and members can conduct related business transactions in NPRIS, including enrollment.
SR-5 | Provide and Administer Benefits | Manage Eligibility & Enrollment | Identify Eligible Members | NPRIS must support unique OSERS business rules including but not limited to the business rule which allows a retiree to return to work and accrue additional service. For example, after five years, the member can qualify for a new retirement benefit on just the additional service. Each such benefit is calculated independently. NPRIS must be configured to calculate independent benefits for just the additional service without considering the entire member account history.
SR-6 | Provide and Administer Benefits | Manage Eligibility & Enrollment | Suspend/ Restore/ Terminate Member Benefits | NPRIS must be configured to provide a retirement closeout method that takes a date range (i.e., of start and end dates) so that retirement closeouts can be selective for the period worked corresponding to a retirement event (which may not be accommodated in NPRIS today).
SR-7 | Provide and Administer Benefits | Manage Eligibility & Enrollment | Process Enrollment | NPRIS must be configured to include the jobs available for the OSERS Plan so that OSERS members can be enrolled through NPRIS.
SR-8 | Provide and Administer Benefits | Manage Member Accounts | Track Member Demographics and Employment History | NPRIS must be configured to allow all OSERS member accounts, including demographic information and account history, to be easily converted into NPRIS from the OPS PeopleSoft System. There may be multiple records for an individual in OSERS today (based on the way the OPS PeopleSoft System was historically configured) that would need to be consolidated into one individual account in NPRIS in the target state. For example, multiple records currently used for a single person in OSERS today because of re-retirement, beneficiary benefits, and alternate payee benefits would need to be consolidated so that demographic information for a single person is maintained in a single record in NPRIS.
SR-9 | Provide and Administer Benefits | Manage Member Accounts | Track Member Demographics and Employment History | NPRIS must be configured to allow new OSERS member accounts to be created in the system, and their demographics and employment history tracked appropriately.
SR-10 | Provide and Administer Benefits | Manage Member Accounts | Account Maintenance | NPRIS must support OSERS Member Account Maintenance.
SR-11 | Provide and Administer Benefits | Manage Member Accounts | Account Maintenance | NPRIS must be able to accommodate multiple retirement and re-employment events with defined employment periods that can impact benefits based on the related closure and cancellation transactions.
SR-12 | Provide and Administer Benefits | Manage Member Accounts | Account Maintenance | NPRIS must be configured to process Qualified Domestic Relations Orders (QDRO) from OPS plan participants according to OSERS business rules.
SR-13 | Provide and Administer Benefits | Manage Member Accounts | Manage Service Credit Business Rules | A full-time member of the retirement system who has completed 5 or more years of Omaha Public School service may purchase up to five years of service credit at any time prior to retirement. NPRIS must be configured to accommodate distinct business rules for processing multiple types of OSERS Optional Service Credits in NPRIS inclusive of eligibility rules, cost calculation rules (including but not limited to amortization interest, interest rates, monthly interest posting, etc.), source of funds for payment (e.g., payroll) and other workflow / configuration needed to support the process as necessary.
SR-14 | Provide and Administer Benefits | Manage Member Accounts | Manage Service Credit Business Rules | The system will need to be configured to allow conversion of the data related to all existing Optional Service Credit agreements from OSERS and any active (e.g., in-flight) agreements and associated workflow to be configured. After the transfer, NPRIS must be able to continue processing in-flight Optional Service Credit purchases with no or minimum impact to OSERS members.
SR-15 | Provide and Administer Benefits | Manage Member Accounts | Manage Service Credit Business Rules | NPRIS must be configured to ensure expired / closed purchase of service options that may have been obtained by OPS members is accurate reflected in the system.
SR-16 | Provide and Administer Benefits | Manage Member Accounts | Manage Service Credit Business Rules | NPRIS shall track all payments related to the service credit purchase agreement via installment and payroll deduction payment plans until the agreement is paid off in full, with all service credit and payment information available in the history of the member account for reference and/or calculation of the benefit (including the service credit).
SR-17 | Provide and Administer Benefits | Process Applications & Claims | Process Retirement Applications | NPRIS shall support OSERS Retirement Application Processing in NPRIS.
SR-18 | Provide and Administer Benefits | Process Applications & Claims | Process Retirement Applications | NPRIS must be configured to allow the transfer of the full actuarial cost to pay the anticipated state service annuity benefit as part of the retirement closeout business event (which may not be accommodated in NPRIS today).
SR-19 | Provide and Administer Benefits | Process Applications & Claims | Process Retirement Applications | NPRIS shall be configured to support business rules for processing NPERS and OSERS retirement applications and claims as defined by policy or statute even in cases where NPERS business rules are different than OSERS business rules.
SR-20 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Apply Benefits Adjustment | NPRIS must be configured to process OSERS Benefit Adjustments in NPRIS according to OSERS business rules. These business rules include provisions for multiple death benefit scenarios (including supporting Death Redistribution functionality), pension rights and divorce, military service provisions, COLA, Medical COLA, and Medical Cola Overrides that may differ between NPERS and OSERS.
SR-21 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Apply Benefits Adjustment | NPRIS must be configured to support the Medical COLA process (which is not be currently configured in NPRIS today), including but not limited to establishing fields to capture related data, associated calculations, and setting up this option in the plan for retirees. This may also have configuration impacts to the existing death process workflow and calculations that need to be assessed and accommodated.
SR-22 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Calculate Benefits Amount | NPRIS must ensure all calculations align with business rules specific to each plan and variation between OSERS and NPERS. Areas of assessment for potential differentiation should include but not be limited to: average compensation calculation rules, retirement options, and benefits calculation using the entire account history vs. segments of account history corresponding to a retirement instance (benefit account) to be calculated.
SR-23 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Calculate Benefits Amount | NPRIS must be able to calculate/recalculate benefits based on date ranges selected and produce benefit calculations based on the range of time applicable to each retirement event because OSERS allows independent calculation of benefits today. For example, OSERS business rules allow a retiree to return to work and accrue additional service. After five years, the member can qualify for a new retirement benefit on just the additional service. Each such benefit is calculated independently.
SR-24 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Member Interest Posting | NPRIS must be configured to support OSERS interest rates.
SR-25 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Member Interest Posting | NPRIS must be configured to support OSERS plan calculations (e.g., posted monthly based on the balance at one point in time during the year).
SR-26 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Estimate Member Benefit Calculation | NPRIS must be configured to provide, for OSERS data, the OSERS Benefits Estimates/Calculator in NPRIS including but not limited to incorporating the available benefit types and retirement options.
SR-27 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Estimate Member Benefit Calculation | The end-state NPRIS system must calculate the correct state service annuity using the service credit balance.
SR-28 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Employer Accounts | NPRIS must allow OPS to be configured as an employer in NPRIS.
SR-29 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Employer Accounts | NPRIS must support employer invoicing for OPS plan contributions.
SR-30 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Wages and Contributions | NPRIS must be configured to support payroll deductions (e.g., pre-tax payroll deductions; post-retirement benefit inclusive of the purchase of service credit) as allowed by the OSERS plan.
SR-31 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Wages and Contributions | NPRIS must be configured to support the OSERS Wage and Contribution business rules, workflow, calculations for penalty and interest, and associated reporting. NPRIS must be able to accept and process monthly payroll data from OSERS similar to existing school plan in NPRIS. NPRIS must be able to accept and process payroll adjustments from OSERs. NPRIS must be able to accept and process Non-cons from OSERs.
SR-32 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Wages and Contributions | NPRIS must be configured to support partial posting (e.g., the NPRIS batch process for posting employer payroll and contribution files must be modified to support partial posting). NPRIS will currently only post such files if 100% of the records are valid and contain no errors. If an error in a record is encountered, all posting transactions from the file are rolled back. This approach would degrade batch processing performance and create unacceptable processing delays for an employer the size of OPS. NPRIS must be configured to post the valid payroll records if the file meets an established threshold, such as 85 to 90% valid records. The valid records must post and records containing errors must be flagged for correction.
SR-33 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Inbound & Outbound Payments | NPRIS must be configured to accommodate any new fiduciary accounts necessary for processing (e.g., new bank accounts).
SR-34 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Inbound & Outbound Payments | NPRIS must be configured to support OSERS transaction types to support the tracking of historical, in-flight, and future financial transactions.
SR-35 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | NPRIS must be configured so that existing self-service features in PeopleSoft must be also provided in NPRIS, including the below:
SR-35.1 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | Online benefit estimator
SR 35.2 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | Ability to view payment advice details including these 5 components: 1 = Benefit of prior to 1951 service 2 = Taxable Omaha Benefit amount 3 = Non-taxable Omaha Benefit amount, which includes contributions prior to 1985 or buy in with after-tax dollars, so this is not taxed 4 = State Service Annuity 5 = Medical Cost of Living
SR-36 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | NPRIS must be configured so that self-service features in NPRIS that are available for other plans are also provided to the OPS plan members, including the below: a. Ability to reprint 1099R, b. Ability to change tax withholding preference c. Online benefit estimator d. Purchase of service credit estimator e. Ability to view account details, including balances f. Ability to view benefit payment information g. Ability to view beneficiaries h. Ability to view and update demographic information
SR-37 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | NPRIS must be configured to allow OSERS to submit and validate payroll data like existing school plan in NPRIS. OSERS must be able to submit and validate payroll adjustments. OSERS must be able to submit Non-cons.
SR-38 | Provide Agency Services | Provide Education Services | Provide Education Services | NPRIS must be configured to support any education services currently provided to OSERS members in the OPS PeopleSoft System, which may include but are not limited to: online help functions, frequently asked questions, etc.
SR-39 | Provide Agency Services | Provide Education Services | Provide Education Services | NPRIS must be configured to be able to register OSERS members for retirement seminars.
SR-40 | Provide Agency Services | Provide Member Services | Provide Member Services | NPRIS must be configured to support any member services currently provided to OSERS members in the OPS PeopleSoft System, which may include but are not limited to: automated communications, automated notifications, contact us features, self-service and reporting features, etc.
SR-41 | Provide Agency Services | Provide Member Services | Provide Member Services | NPRIS must be configured to enroll and maintain beneficiaries for OPS plan participants according to OSERS business rules.
SR-42 | Provide Agency Services | Provide Data Services | Provide Document Management Services | NPRIS must be configured to support document management of content converted and migrated to NPRIS (i.e., Hyland OnBase ECM) as digital media converted from OSERS non-digital content (e.g., paper, microfilm).
SR-43 | Provide Agency Services | Provide Data Services | Provide Document Management Services | NPRIS must be configured to accommodate any OSERS-specific document types and associated templates for forms, letters, etc.
SR-44 | Provide Agency Services | Provide Data Services | Provide Reporting Services | NPRIS must be configured to ensure compliance with State and Federal Reporting requirements, including Federal Tax Reporting requirements.
SR-45 | Provide Agency Services | Provide Data Services | Provide Reporting Services | NPRIS must be configured to support all reporting options available in the OPS PeopleSoft System today, including the configuration of reports in NPRIS.
SR-46 | Provide Agency Services | Manage Stakeholder Relationships | Manage Stakeholder Relationships | NPRIS must be configured to support any stakeholder relationship management functionality available in the OPS PeopleSoft System today, including but not limited to history of member transactions and interactions with staff or other features that help ensure customer satisfaction.
SR-47 | Ensure Security & Mitigate Risk | Conduct Internal Audits | Verify Compliance of System Records with Established Policies | NPRIS must be configured to have a mechanism for users to distinguish converted data and historical transactions migrated from OSERS vs. new data created once the transfer has taken place.
SR-48 | Ensure Security & Mitigate Risk | Conduct Internal Audits | Data Security | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) security provisions for protection of data.
SR-49 | Ensure Security & Mitigate Risk | Conduct Internal Audits | Security Roles & Permissions | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) security provisions, including user roles and security permissions, as available in the OPS PeopleSoft System.
SR-50 | Ensure Security & Mitigate Risk | Perform Fraud Detection | Perform Fraud Detection | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) security provisions, including user roles and security permissions, as available in the OPS PeopleSoft System.
SR-51 | Ensure Security & Mitigate Risk | Conduct External Audits | Conduct External Audits | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) reports, workflow, etc. to support any external audits that may need to be conducted (if applicable).
SR-52 | Ensure Security & Mitigate Risk | Ensure Business Continuity / Disaster Recovery | Ensure Business Continuity / Disaster Recovery | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) business continuity / disaster recovery functionality (if applicable).
SR-53 | Steward Funds | Maintain Finances and Accounting | Manage General Ledger | NPRIS must be configured to incorporate the OSERS General Ledger chart of accounts so that general ledger transactions are properly posted for all financial activities.
SR-54 | Steward Funds | Maintain Finances and Accounting | Manage General Ledger | NPRIS must be configured to accommodate the fiscal year range for the OSERS plan (which may differ from NPERS's fiscal year).
SR-55 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to calculate the OSERS Annuity Payroll in NPRIS.
SR-56 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to allow for the "prior 1951 benefit" to be part of the benefit roll and downstream processing.
SR-57 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to support tax levy garnishments.
SR-58 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to support benefit recipients splitting their benefit payments into multiple accounts (e.g., splitting a single benefit check to multiple direct deposit accounts).
SR-59 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to execute existing OSERS direct deposits so that members do not have to re-enroll for direct deposits after the transfer (e.g., set up routing numbers, etc.).
SR-60 | Steward Funds | Maintain Finances and Accounting | Manage Third Party Account Participants | NPRIS must be configured to issue payments to the third-party payees outside of NPRIS for the amounts recovered after benefit runs against the benefit receivable tax levy line items.
SR-61 | Steward Funds | Maintain Finances and Accounting | Request Refunds and Transfers | NPRIS must be configured to accommodate any OSERS-specific refund types for members and death situations not already configured in NPRIS (inclusive of Death Refunds, impact to a beneficiary if a member dies in retirement with an outstanding A/R). This may also need to include accommodating any configuration necessary for in-flight refund requests that need to be configured in NPRIS (depending on determined approach of how to address in-flight refund requests).
SR-62 | Steward Funds | Maintain Finances and Accounting | Request Refunds and Transfers | NPRIS must configured to allow users to view migrated OSERS data associated with refund and retirement transaction events so that it is available for reference purposes.
SR-63 | Steward Funds | Maintain Finances and Accounting | Request Refunds and Transfers | NPRIS must be configured to allow a new or existing fiduciary account to enable output payments for OSERS for cash disbursements related to refunds.

## 3. Imp. Svcs. Requirements
Tab 3. Implementation Services Requirements
Req ID | Implementation Phase | Implementation Service Requirement (ISR) | Responsibility |  | Describe, generally, the process of how the bidder's solution will accomplish this requirement.
|  |  | Bidder | NPERS
ISR-1.1 | Implementation Planning & Management | Provide a Project Manager (PM) to represent the Bidder in the management of the Project, interfacing with NPERS Project Manager (PM) in any decisions relating to the Project. | X
ISR-1.2 | Implementation Planning & Management | Assume and lead all day-to-day management of all Bidder personnel, including subcontractor personnel, and development of Deliverables related to the required services. | X
ISR-1.3 | Implementation Planning & Management | Provide a Project Manager to represent NPERS organization in this Project, interacting with the Bidder’s PM, and representing NPERS in any decisions relating to the Project. |  | X
ISR-1.4 | Implementation Planning & Management | Escalate items to the project governance (e.g., Steering Committee) for awareness and decision-making. |  | X
ISR-1.5 | Implementation Planning & Management | Participate in governance committee meetings upon request, and present project status. |  | X
ISR-1.6 | Implementation Planning & Management | Maintain a Disaster Recover or Business Continuity Plan that describes the approach to perform disaster recovery activities. |  | X
ISR-1.7 | Implementation Planning & Management | Conduct project oversight activities. | X
ISR-1.8 | Implementation Planning & Management | Interface with and support requests from Independent Project Oversight Consultant contracted by NPERS. | X
ISR-1.9 | Implementation Planning & Management | Provide a robust Project management methodology founded on industry best practices and covering all key project management processes. | X
ISR-1.10 | Implementation Planning & Management | Conduct project management activities throughout the life of the Project, maintaining planning documents current and executing the associated plans. | X
ISR-1.11 | Implementation Planning & Management | Provide, update, and maintain a formal Project Management Plan (PMP) that includes the following key components: - Project initiation activities, including developing Project Kickoff materials. - Risk and Issue Management Plans & Logs – Risk and Issue Management Plan, Escalation Plan, and Risks, Assumptions, Issues, and Dependencies (RAID) log. This should include risk management, identification, quantification of impact, monitoring, and mitigation plans. - Quality management. - Bidder and sub-contractor resource management. - Project success evaluation criteria and Project close-out activities. - Document management approach and document repository. - Relationships to other IT or business efforts. - Integrated Change Management Plan that outlines the change management process, including change request template, impact analysis template, request approval process, and processes for management and tracking of change requests. - Deliverable/product review and approval and other acceptance criteria. - Status and other reporting activities, including status reporting templates (including deliverable status reports, issues, risks, plan vs. actual status, etc.). | X
ISR-1.12 | Implementation Planning & Management | Develop project kickoff materials - Conduct a project kickoff meeting with key stakeholders within thirty (30) days of contract execution. The kickoff meeting will provide an overview of the project objectives, plans, project scope and schedule, introduce the Bidder’s project team and roles and responsibilities, and outline project start-up procedures. | X
ISR-1.13 | Implementation Planning & Management | Identify, document, provide, and implement risk mitigation measures and contingency plans as high-priority risks are identified and monitored. | X
ISR-1.14 | Implementation Planning & Management | Provide Ongoing Project Management Duties - Provide weekly project plan and schedule updates, weekly status reporting, weekly status meetings, risk and issue monitoring, and integrated change management activities. In addition to weekly status meetings, the Bidder’s Project Manager should participate in project Steering Committee meetings and other NPERS meetings as required. | X
ISR-1.15 | Implementation Planning & Management | Provide Project Status Reports and conduct regularly scheduled status meetings reviewing Project progress, risk mitigation, issue resolution, deliverable status, and next steps as mutually agreed upon by NPERS and the Bidder. | X
ISR-1.16 | Implementation Planning & Management | Use the documentation repository as agreed to and documented in the Project Management Plan deliverable. | X
ISR-1.17 | Implementation Planning & Management | Provide, update, and maintain a Baseline Project Schedule and Work Plan to reflect the project timelines, milestones, and deliverables. Provide periodic updates (as mutually agreed upon by NPERS and the Bidder) to the Project Schedule which is maintained by the Bidder. The Schedule will include the following key components: - A consolidated view of the activities, activity descriptions, and activity durations assigned to stakeholders and Bidder. - Gantt chart(s) and a project calendar in Microsoft Project that is developed and maintained in accordance with industry best practices. - Resources (NPERS, other stakeholders, and Bidder) assigned to each activity and their required level of effort. - A list of all required project deliverables tied to the appropriate project milestones. - Identification of all key project milestones. - Deliverable approval periods compliant with NPERS’ Deliverable Expectations Document process as described in the following section Deliverable Expectations Document. - A critical path analysis and reporting process. The work plan will reflect any changes from the baseline Schedule originally agreed to during the project initiation and be updated/published on a weekly basis. | X
ISR-1.18 | Implementation Planning & Management | Deployment Planning - Conduct workshops with NPERS and other stakeholders to finalize approach for deploying the transferred functionality into production. | X
ISR-1.19 | Implementation Planning & Management | Develop an Initial Deployment Plan (e.g., transition planning to finalize rollout details). Finalized approach for deploying the transferred functionality into production including any benefits and risks of strategy, including: - Overview of the current environment and considerations for deployment. - Identification of high-risk transition areas and impact, mitigation strategies, and recommended mitigation actions. - Any ongoing risks, based on finalization of phasing approach, should be tracked in a risk log. - Any decisions that impact the schedule should be documented in the project schedule. - Any cutover consideration(s) should be documented in the final Cutover Plan. | X
ISR-1.20 | Implementation Planning & Management | Create a Solution Environment and Configuration Management Plan (e.g., sandbox, development, testing, training, etc.) required to support all project phases including obtaining licenses (if applicable) and other required infrastructure. The Plan should describe the following (at a minimum): - Approach for managing programming changes and configuration settings made in NPRIS to transfer the OPS retirement plan, including testing, final approval of deployment, and deployment. | X
ISR-1.21 | Implementation Planning & Management | Implement the environment configurations required to support the project implementation. |  | X
ISR-1.22 | Implementation Planning & Management | Document proposed deliverable content, format, and acceptance criteria in Deliverable Expectation Documents (DEDs) as mutually agreed upon by NPERS and the Bidder. | X
ISR-1.23 | Implementation Planning & Management | Approve or request changes to Deliverable Expectation Documents (DEDs). |  | X
ISR-1.24 | Implementation Planning & Management | Provide project background information such as relevant charters, documentation, organization structure. |  | X
ISR-1.25 | Implementation Planning & Management | Submit completed deliverables aligned with Deliverable Expectation Documents and meet target deliverable submission dates. | X
ISR-1.26 | Implementation Planning & Management | Coordinate deliverable reviews and approvals. |  | X
ISR-1.27 | Implementation Planning & Management | Provide deliverable review comments and revisions needed for deliverable approval. |  | X
ISR-1.28 | Implementation Planning & Management | Prepare Change Requests as required. | X
ISR-1.29 | Implementation Planning & Management | Document impact analysis associated with proposed changes and follow the agreed upon change management process as documented in the Integrated Change Management Plan. | X
ISR-1.30 | Implementation Planning & Management | Approve and prioritize changes. |  | X
ISR-1.31 | Implementation Planning & Management | Communicate Project scope change process and procedures to NPERS stakeholders. |  | X
ISR-2.1 | Requirements Review & Confirmation | Implement and establish a formal requirements management process that includes: - Implementation requirements tracking, maintenance, and traceability (e.g., to test scenarios/cases). - Develop a Requirements Traceability Matrix - Bidder will review the functional and technical requirements defined in Appendix X. Implementation Requirements to validate the Bidder’s understanding of the requirements to meet stakeholders’ expectations and identify areas for discussion. An RTM may include any design considerations, gaps, issues, or risks that need to be addressed throughout the project and should be maintained over time to track the status of each requirement. | X
ISR-2.2 | Requirements Review & Confirmation | Develop a plan and schedule to conduct NPERS interviews, group workshops, and surveys to refine, and prioritize the detailed solution requirements. | X
ISR-2.3 | Requirements Review & Confirmation | Act as primary point of contact with stakeholders and offices to refine solution requirements, including scheduling NPERS staff for interviews and workshops. |  | X
ISR-2.4 | Requirements Review & Confirmation | Conduct and document NPERS interviews, group workshops, and surveys to refine, and prioritize the detailed functional and technical requirements. | X
ISR-2.5 | Requirements Review & Confirmation | Coordinate, schedule and communicate with all functional and technical SMEs for planning sessions. |  | X
ISR-2.6 | Requirements Review & Confirmation | Conduct business process analysis and reengineering focused on the transition or transformation of source system business processes to the target system. | X
ISR-2.7 | Requirements Review & Confirmation | Understand target datasets and NPRIS architecture. | X
ISR-2.8 | Requirements Review & Confirmation | Create a Functional Fit Gap Analysis. Conduct and document assessments of detailed functional requirements and generate the fit-gap analysis between the source (PeopleSoft) and target system (NPRIS), including affected systems recommendations and alternative options. | X
ISR-2.9 | Requirements Review & Confirmation | Create a Technical Fit Gap Analysis. Conduct and document assessments of detailed technical infrastructure requirements and generate the fit-gap analysis, including network infrastructure, desktops, etc. | X
ISR-2.10 | Requirements Review & Confirmation | Produce a Requirements Validation Document that documents any changes, revisions, clarifications to functional and technical requirements in the requirements repository (i.e., Requirements Traceability Matrix) to be maintained by the Bidder. This deliverable, once approved, serves as the validated detailed functional and technical requirements and includes security features. The requirements traceability matrix must be updated to reflect the approved Requirements Validation Document. | X
ISR-3.1 | Design | Facilitate interviews, group workshops, etc. to obtain and gain consensus on design. | X
ISR-3.2 | Design | Conduct and document functional and technical planning sessions to establish system configuration. | X
ISR-3.3 | Design | Provide a System Design Document, conceptual design documentation for required NPRIS modifications, data/content changes, and all activities required to achieve the transfer of the OPS plan into NPRIS. This deliverable includes: - “To-be” business process flows to address any requirements gaps identified and implement the validated detailed functional and technical requirements via configuration settings and custom development. - Updated Entity Relationship Diagrams. - Updated Data Dictionary. - Updated Security controls. | X
ISR-3.4 | Design | Develop the Solution Implementation Plan - Bidder will describe the implementation approach throughout application design, interface design, and conversion design. The Solution Implementation Plan should include the following (at a minimum): - How the Bidder will provide and/or leverage existing system management tools for all development environments and manage all development efforts using industry-standard software development tools and methodologies. - Ensure that the transferred components conform to defined standards for System design and Systems architecture. - Approach for managing programming environment changes including management of test and deployment of new releases while maintaining capacity to apply hotfixes to production. Note: NPERS should have the final authority to process and apply the hotfixes to production. | X
ISR-3.5 | Design | Bidder will provide the following sub-component plans as part of the Solution Implementation Plan that describe the following (at a minimum): Security Plan: Approach for continuing assurance of system security, including how the Bidder complies with applicable security protocols, regulations, etc. Security incident response plan details that describe the following (at a minimum): - Security roles and responsibilities, mission statement, key terms governing incident response, identification of an incident response lead, and incident detection channels. - Strategy to identify and categorize incidents. - Process to communicate, contain, eradicate, and recover from incidents. Infrastructure Services Plan: - Definition of each environment that will be required and used in the OPS Transfer Project activities (e.g., production, tagging, and test). - Approach for maintaining application and infrastructure component consistency across all environments. - Approach for certifying and/or providing quality assurance of environments. | X
ISR-4.1 | Development & Configuration | Configure OPS retirement plan in NPRIS based on the solution requirements of the RFP (Appendix A), approved Solution Implementation Plan and detailed design requirements identified in the previous phase. Perform all necessary technical design, configuration, testing, or scripting, of systems as required to provide and implement the functional and technical requirements. | X
ISR-4.2 | Development & Configuration | Define and document configuration management policies and procedures consistent with industry best practices. | X
ISR-4.3 | Development & Configuration | Adhere to NPERS audit and configuration management standards. | X
ISR-4.4 | Development & Configuration | Manage documentation of changes to the underlying environment via use of library management version control and turnover management. | X
ISR-4.5 | Development & Configuration | Review configuration management results. |  | X
ISR-4.6 | Development & Configuration | Perform configuration management activities throughout the Project. | X
ISR-4.7 | Development & Configuration | Provide configuration management tools. |  | X
ISR-4.8 | Development & Configuration | Conduct code and configuration reviews to ensure compliance with NPERS standards to reduce defects. | X
ISR-4.9 | Development & Configuration | Review and approve results of Bidder code and configuration reviews at NPERS’s discretion. |  | X
ISR-4.10 | Development & Configuration | Schedule releases (e.g. configuration changes). | X | X
ISR-4.11 | Development & Configuration | Provide a Role to Position Mapping Document to map the end-user roles to the positions within the organization. | X
ISR-4.12 | Development & Configuration | Create a Cutover Plan - Bidder will perform go live cutover planning activities to assess transition readiness, go / no-go criteria, and fallback positions to be taken if no-go conditions are encountered for deployment. The Cutover Plan will include (at a minimum): - A preliminary cutover schedule that clearly defines key milestones, deliverables, tasks, and responsibilities. The Cutover Plan will be updated prior to go live. - Cutover milestones where readiness to proceed is assessed, go/no-go criteria, and fallback positions to be taken if no-go conditions are encountered. - Pre-cutover checklist and post-cutover evaluation criteria. - Transition readiness assessment, including the preliminary schedule, rollback strategy, assessment scorecards, and defined critical readiness criteria that will drive go / no-go decisions related to overall readiness / preparedness for going live with transferred components in NPRIS. | X
ISR-5.1 | Data Conversion | Provide a Data Conversion Strategy, including identification of the methodology and tools for the migration of the source OSERS legacy data (PeopleSoft and external tables) to the target NPRIS system. | X
ISR-5.2 | Data Conversion | Provide a Data Conversion Plan, including identification of roles and responsibilities for Bidder and NPERS staff, and policies and procedures to ensure controls are in place in accordance with NPERS rules and regulations. This deliverable includes documentation of detail mappings from source to target data fields. The Plan will include (at a minimum): - Description of conversion methodology (e.g., processes to extract data, processes to validate data, documentation of data). - Number of mock runs that will be conducted (a mock run is an exercise of data conversion using the agreed upon mapping and transformation rules). - Description of manual conversion processes that cannot be automated. - Milestones, targets. - How much history is converted out of PeopleSoft / external tables and into NPRIS and the NPERS’ SQL tables. - List of data to not convert. - Manual data entry and error correction after conversion. - Plan for testing and validating converted data. | X
ISR-5.3 | Data Conversion | Execute the approved Data Conversion Plan. | X
ISR-5.4 | Data Conversion | Specify, provide and install necessary tools for data mapping and conversion activities. This includes: - Extract, Transform, and Load (ETL) tools. - Tool for obfuscation of data. - Tool for automated comparison of financial accounting calculation results between OPS PeopleSoft and NPRIS. | X
ISR-5.5 | Data Conversion | Assist with installation and configuration of ETL tools (e.g. legacy environments). |  | X
ISR-5.6 | Data Conversion | Execute Data Mapping– Map OPS PeopleSoft and External Table data to the appropriate NPRIS MS SQL tables, as well as execute conversion. | X
ISR-5.7 | Data Conversion | Create data conversion extracts from legacy/existing data files in a format specified by the Data Conversion Plan. | X
ISR-5.8 | Data Conversion | Provide coding of automated data conversion extracts from legacy/existing data files, using techniques that are consistent with the development standards. | X
ISR-5.9 | Data Conversion | Extract legacy data for purposes of transformation and loading into the target application files structures. | X | X
ISR-5.10 | Data Conversion | Transform and load cleansed legacy data. | X
ISR-5.11 | Data Conversion | Review the data and the data cleansing metrics as delineated in Data Conversion Plan. |  | X
ISR-5.12 | Data Conversion | Perform manual data cleansing (cleansing of data that cannot be cleansed automatically). | X | X
ISR-5.13 | Data Conversion | Coordinate and execute manual data loads if required. | X
ISR-5.14 | Data Conversion | Provide converted legacy data for transactional testing during integration, end to end, parallel, user acceptance, etc. | X
ISR-5.15 | Data Conversion | Perform Data Conversion from the source system(s) to the target NPRIS system, by electronic or manual methods and track data conversion status and notifications. | X
ISR-6.1 | Letters, Forms & Reports | Specify how all reports, letters, and forms will be modified to accommodate the OPS plan in NPRIS, including (but not limited to): - Data merged letters, correspondences, and forms. - Standardized and parameterized reports. | X
ISR-6.2 | Letters, Forms & Reports | Create the Letters, Forms, and Report Specification Document, to include the following design specifications (at a minimum): - Identify report fields and parameters (as applicable). - Mapping database fields to report fields. - Document required ad-hoc query and reporting functionality. | X
ISR-6.3 | Letters, Forms & Reports | Develop and/or modify all reports – execute report development and unit testing. | X
ISR-6.4 | Letters, Forms & Reports | Develop and document custom reports (as required to provide and implement functional and technical requirements). | X
ISR-7.1 | Testing | Develop a Test Management Strategy deliverable that lists all test events, entrance and exit criteria for each test event, roles and responsibilities, defect management processes, high-level data requirements for each test event, tools used for each test event, including User Acceptance Testing. | X
ISR-7.2 | Testing | Provide a Test Plan that covers each test event and provides the detailed approach that shall be taken to fully test all components of the system including test control and approval processes, test participants, how testing will interface with the configuration management process, and test documentation expectations for the following test types: unit, system, security / intrusion, regression, stress/performance, and user acceptance. The Test Plan must include the following at a minimum: - Security / Intrusion testing. - Regression testing. - Test Data Creation approach, including data refresh processes. - Stress / performance testing, including pass criteria that can handle the batch transaction load data. - Automated Test Usage (optional, but preferred by NPERS). - User Acceptance testing scripts and support. - Defect remediation release strategy and regression testing. | X
ISR-7.3 | Testing | Maintain the Test Management Strategy and all Test Plans. | X
ISR-7.4 | Testing | Manage and execute the agreed upon Test Management Strategy and approved Test Plan, including regression testing, and creating and maintaining the required test data during the testing period. | X
ISR-7.5 | Testing | Provide automated testing tools and procedures for testing including UAT, system, regression, performance, stress, etc. | X
ISR-7.6 | Testing | Document/create standards and procedures for the use of the tools that support all testing activities. | X
ISR-7.7 | Testing | Install, configure, and implement the testing application software, hardware, data, desktops, etc. | X
ISR-7.8 | Testing | Create Test Scripts, Test Cases, and Test Data, aligned to functional and technical requirements; and perform all appropriate testing events as agreed to in the approved Test Plan. | X
ISR-7.9 | Testing | Assist with testing (i.e. integration, regression, system, performance) and provide input to scripts and perform user acceptance testing. |  | X
ISR-7.10 | Testing | Configure Hardware Environments (testing) to test and/or demonstrate the functionality has been satisfied. |  | X
ISR-7.11 | Testing | Configure Hardware Environments (testing) Documentation, including specification of hardware, network, storage, utilities, licensees, and other required infrastructure. |  | X
ISR-7.12 | Testing | Provide documentation of System, Regression, Performance/Stress, and Security/Intrusion Test Results that describe the following (at a minimum): - Date scenario was executed. - Person who executed the scenario. - Test result status (pass/fail). - Defects discovered. - Retest dates and results. - Justification for exiting Test stage, including performance testing success. | X
ISR-7.13 | Testing | Validate the system for compliance with the Security Plan. | X
ISR-7.14 | Testing | Correct defects found as a result of testing efforts. | X
ISR-7.15 | Testing | Review testing results for compliance with policies, procedures, plans, and test criteria and metrics (e.g. defect rates, progress against schedule). |  | X
ISR-7.16 | Testing | Coordinate the scheduling of user acceptance testing (e.g. gain user involvement, establish, and define acceptance criteria, set high-level test objectives, establish high-level test scenarios). |  | X
ISR-7.17 | Testing | Facilitate and support user acceptance test as prescribed by NPERS, including: establishing adequate test environment based on user acceptance criteria; preparing data to support test scenarios within modified system as well as managing the relationship with all interfaced systems necessary to conduct test; troubleshooting; supporting users to progress through scenarios; simulating interfaces or working with integrated systems to conduct end-to-end tests; supporting batch processing; exercising functionality; converting production data, and reporting results. | X
ISR-7.18 | Testing | Conduct user acceptance testing. |  | X
ISR-7.19 | Testing | Use a Defect Tracking System (provided by the Bidder) for purposes of allowing NPERS to initiate, track, and report all testing defects (e.g. integration, end to end, parallel, and user acceptance testing). |  | X
ISR-7.20 | Testing | Correct defects found as a result of testing efforts. | X
ISR-7.21 | Testing | Provide documentation of satisfying agreed upon exit success criteria for User Acceptance Testing in the User Acceptance Test Results Report. | X
ISR-8.1 | Deployment | Provide detailed Final Technical Documentation including the technical and architectural documents, diagrams, and specifications. | X
ISR-8.2 | Deployment | Provide updated Artifacts from the Implementation for Production, including functional, technical specifications, operational documentation (e.g. batch schedule, runtime procedures). | X
ISR-8.3 | Deployment | Provide Final As-Built Configuration Documentation of each of the delivered environments, including the results of smoke tests of those environments. Bidder will provide documentation specific to the Agency’s implementation. | X
ISR-8.4 | Deployment | Provide updated and Final Cutover Plan and Cutover Schedule. | X
ISR-8.5 | Deployment | Provide the Configured Hardware Environments (production and disaster recovery). |  | X
ISR-8.6 | Deployment | Provide Configured Hardware Environments (production and disaster recovery) Documentation, including specification of hardware, network, storage, utilities, licensees, and other required infrastructure. |  | X
ISR-8.7 | Deployment | Provide Readiness Report to confirm the overall readiness of NPRIS to support the transferred components / modified functionality in production. This will inform the Go/No-Go decision. | X
ISR-8.8 | Deployment | Conduct Go/No-go Meeting. | X
ISR-8.9 | Deployment | Perform deployment and support activities as directed by NPERS Project Manager. | X
ISR-8.10 | Deployment | Provide recommended operations and administration procedures related to the deployment. | X
ISR-8.11 | Deployment | Approve production deployment go/no-go decisions. |  | X
ISR-8.12 | Deployment | Deploy application into production. | X
ISR-8.13 | Deployment | Track deployment status and notification. | X
ISR-8.14 | Deployment | Provide Cutover Completion Report deliverable that validates the full transition of modified functionality into production. | X
ISR-8.15 | Deployment | Provide the configuration and customization documentation and readable source code and object (executable) code for the system in the configuration management system. | X
ISR-9.1 | Transition & Post-Implementation Stabilization Support | Perform an Implementation Phase Closeout including system tuning activities, assessment of knowledge transfer tasks, transfer Project artifacts to Project repository, lessons learned document, update design documents, and transition support to NPERS as appropriate. Document completed Phase Closeout activities in a Project Closeout Report. | X
ISR-9.2 | Transition & Post-Implementation Stabilization Support | Provide Monthly Stabilization Support Reports – Bidder will create initial templates of monthly stabilization support reports for NPERS to verify that the reports are sufficient and accurate before the project closes; Reports will include the following: - Maintenance / Stabilization services completed per period. - Maintenance / Stabilization services in progress per period. - Maintenance / Stabilization services planned next period. - Risks and issues. | X
ISR-9.3 | Transition & Post-Implementation Stabilization Support | Escalate and assist with the resolution of issues with Bidder post-production support team. |  | X
ISR-9.4 | Transition & Post-Implementation Stabilization Support | Provide 12 months of system stabilization support. | X
ISR-9.5 | Transition & Post-Implementation Stabilization Support | Provide Level 1 Help Desk—simple (with coordination of user support activities including “how to” support) and user account and password administration. |  | X
ISR-9.6 | Transition & Post-Implementation Stabilization Support | Provide Level 2 and 3 Help Desk for the system-related incidents and problems. | X
ISR-9.7 | Transition & Post-Implementation Stabilization Support | Provide support organization to advise and assist business end-users and staff in the use of systems and NPERS-specific policies. |  | X
ISR-9.8 | Transition & Post-Implementation Stabilization Support | Respond to escalated trouble ticket items in accordance with established procedures. | X
ISR-9.9 | Transition & Post-Implementation Stabilization Support | Establish priority of trouble ticket items / service requests. |  | X
ISR-9.10 | Transition & Post-Implementation Stabilization Support | Maintain “end state” system architecture documentation. | X
ISR-9.11 | Transition & Post-Implementation Stabilization Support | Provide maintenance and repair policies and procedures. | X
ISR-9.12 | Transition & Post-Implementation Stabilization Support | Provide technical and functional support to NPERS IT staff and other groups as directed by NPERS. | X
ISR-9.13 | Transition & Post-Implementation Stabilization Support | Provide processes and procedures for tracking and reporting the status of all post-implementation support and stabilization services. | X
ISR-9.14 | Transition & Post-Implementation Stabilization Support | Perform system fixes for problems that the Bidder was responsible for providing. | X
ISR-9.15 | Transition & Post-Implementation Stabilization Support | Perform data fixes for errors that the Bidder was responsible for, including but not limited to improperly converted files or data. | X
ISR-9.16 | Transition & Post-Implementation Stabilization Support | Regression test the system to ensure that no errors are introduced. | X
ISR-9.17 | Transition & Post-Implementation Stabilization Support | Approve all post-implementation support and stabilization service fixes with formal sign-off. |  | X
ISR-9.18 | Transition & Post-Implementation Stabilization Support | Update all documentation and related files/Deliverables associated with post-implementation support services. | X
ISR-9.19 | Transition & Post-Implementation Stabilization Support | Test remediated code or configurations (and regression test the entire solution) to verify that no errors are introduced. | X
ISR-9.20 | Transition & Post-Implementation Stabilization Support | Update all appropriate documentation to reflect defect corrections. | X
ISR-9.21 | Transition & Post-Implementation Stabilization Support | Provide Final Acceptance Document deliverable that includes a checklist of all Project closeout activities and validates that support has been provided for the duration of the Minimum Support Period (i.e., 12 months). | X