## Title Page
Nebraska Public Employees Retirement Systems |  | (NPERS)
Omaha School Employees Retirement System (OSERS) Transfer Project
Solution and Implementation Services Requirements Response Workbook

## Instructions
Nebraska Public Employees Retirement Systems (NPERS)
Omaha School Employees Retirement System (OSERS) Transfer Project
Instructions
This workbook provides the baseline of solution and implementation service requirements for future vendor(s) to configure the Omaha Public School (OPS) retirement plan in the Nebraska Public Retirement Information System (NPRIS). Bidder shall complete and submit the Solution and Implementation Services Requirements Workbook. The workbook contains the following information and response tabs: Tab 1. Requirements Categories Diagram (RCD) organizes similar requirements into various categories that reflect the OPS business processes that NPRIS will need to support going forward. The RCD is provided below for reference. The requirements provided on the Tab 2: Solution Requirements are organized by the categories identified in the RCD. No response required by the Bidder Tab 2. Solution Requirements details the business capabilities required to be implemented into NPRIS to help Bidders assess level of effort, timeframe, and other information needed to scope the work and put together a proposal. For each requirement, Bidders shall describe, generally, the process of how the bidder's solution will accomplish this requirement. Tab 3. Implementation Services Requirements outlines the high-level roles and responsibilities of both NPERS and the Bidder overall. For requirements denoted as the responsibility of the Bidder, Bidders shall describe, generally, the process of how the bidder's solution will accomplish this requirement. Response cells that are blacked out are for activities that are the responsibility of NPERS and do not require a bidder response.

## 1. RCD
Requirements Categories Diagram (RCD) - Overview of Categorization of Solution Requirements

## 2. Solution Requirements
Tab 2. Solution Requirements
Req ID | Business Capability Model (BCM) Level 0 | Business Capability Model (BCM) Level 1 | Sub-Category | Solution Requirement (SR) | Describe, generally, the process of how the bidder's solution will accomplish this requirement.
SR-1 | General Requirement | N/A | N/A | All system elements necessary to transfer the Omaha Public School (OPS) retirement plan into the Nebraska Public Retirement Information System (NPRIS) must be configured / developed by the successful respondent. | The system will be configured and the software will be modified to integrate the Omaha Public School (OPS) retirement plan(s) into the Nebraska Public Retirement Information System (NPRIS). There will also be business Rules captured for any and all rules for OPS system and the data will be transformed and migrated to NPRIS. The sytem will be developed, unit tested and delivered to User Acceptance. Once the User Acceptance test is approved, the system will be deployed to production.
SR-2 | General Requirement | N/A | N/A | NPRIS must be configured to support all OPS benefit plans and tiers in NPRIS including but not limited to new development or modifications required to screens, forms, business rules, workflow, fields, letters, reports, document templates, interfaces, etc. | As describe in the rows below, the NPRIS system will be configured to integrate OSERS into NPRIS and all modifications needed for reference tables, screens, business rules, workflows, letters and forms, interfaces and Self Service will be accomplished over the lifecycle of the project.
SR-3 | General Requirement | N/A | N/A | NPRIS must be configured so that new OPS members can be enrolled in their eligible retirement plan(s) via NPRIS. | Report the School employee details through Wages and Contribution. We can configure all the School Employers and w can associate the employer with the plan/ covered job class which will be configured. Once this is done, employers can start reporting on the school employees
SR-4 | Provide and Administer Benefits | Manage Eligibility & Enrollment | Identify Eligible Members | The OSERS plan and tiers and the reference tables that depend on them must be configured in NPRIS so that OSERS members' benefits are able to be managed in NPRIS and members can conduct related business transactions in NPRIS, including enrollment. | This requirement can be accomplished by configuring new Job Class Codes, Wage Limits, Benefit Structures, Payrates, hours and limits and tier information. This will enable us to enroll .
SR-5 | Provide and Administer Benefits | Manage Eligibility & Enrollment | Identify Eligible Members | NPRIS must support unique OSERS business rules including but not limited to the business rule which allows a retiree to return to work and accrue additional service. For example, after five years, the member can qualify for a new retirement benefit on just the additional service. Each such benefit is calculated independently. NPRIS must be configured to calculate independent benefits for just the additional service without considering the entire member account history. | The system will be configured and the new business rules for multiple retirements based on eligibility and vesting will be coded into the system. This will allow for data migration to bring in multiple retirements to NPRIS for a single member and the system to cater to multiple retirements for a member. The system will have to be changed to have members to be retired as well as be re-employed and accruing serivce credit and contributions and any new retirement requests will have to look for service credit within a data range (start from previous retirement date)
SR-6 | Provide and Administer Benefits | Manage Eligibility & Enrollment | Suspend/ Restore/ Terminate Member Benefits | NPRIS must be configured to provide a retirement closeout method that takes a date range (i.e., of start and end dates) so that retirement closeouts can be selective for the period worked corresponding to a retirement event (which may not be accommodated in NPRIS today). | Currently in base JClarety, benefits are calculated based on the net service, pension factor, FAS and age as of termination date(retirement date is always 1 day after termination date). If date range needs to be applied, then benefits will be calculated based on the service, pension factor, FAS and age as of that specified date range.
SR-7 | Provide and Administer Benefits | Manage Eligibility & Enrollment | Process Enrollment | NPRIS must be configured to include the jobs available for the OSERS Plan so that OSERS members can be enrolled through NPRIS. | Static data will be configured to include new position codes/job class codes for the new OSERS members, so that when the member enrolls into NPRIS under school plan, they should be able to choose the appropriate jobs.
SR-8 | Provide and Administer Benefits | Manage Member Accounts | Track Member Demographics and Employment History | NPRIS must be configured to allow all OSERS member accounts, including demographic information and account history, to be easily converted into NPRIS from the OPS PeopleSoft System. There may be multiple records for an individual in OSERS today (based on the way the OPS PeopleSoft System was historically configured) that would need to be consolidated into one individual account in NPRIS in the target state. For example, multiple records currently used for a single person in OSERS today because of re-retirement, beneficiary benefits, and alternate payee benefits would need to be consolidated so that demographic information for a single person is maintained in a single record in NPRIS. | Current data from OPS PeopleSoft System should be moved to NPRIS via Data conversion process and it should include the following: 1. Many - 1 relation ( demographic Info) for a Member from OSERS to NPRIS should be identified. 2. Relevant data should be stored in the appropriate NPRIS tables or if needed, new tables should be configured to store any additional information for the member. Appropriate data conversion rules will have to be written to convert the date from OSERS to NPRIS
SR-9 | Provide and Administer Benefits | Manage Member Accounts | Track Member Demographics and Employment History | NPRIS must be configured to allow new OSERS member accounts to be created in the system, and their demographics and employment history tracked appropriately. | Initial enrollment of OSERS members happen via wages and contribution reporting, data conversion and through the enrollment process of NPRIS application. After enrollment into the NPRIS system, employment details, demographic informations will be tracked automatically via the posting jobs.
SR-10 | Provide and Administer Benefits | Manage Member Accounts | Account Maintenance | NPRIS must support OSERS Member Account Maintenance. | Once the OSERS member gets enrolled into the system successfully, his/her own member account will be created and contributions will come into the account via postings from employer on biweekly/monthly/semi-monthly based on employer's reporting frequency. This process should take care of account details to be tracked/viewed for future purposes. OSERS member account details can be viewed under various reports(member transaction history report, etc.) Member account maintenance can be done via the Maintain/ Transaction screen.
SR-11 | Provide and Administer Benefits | Manage Member Accounts | Account Maintenance | NPRIS must be able to accommodate multiple retirement and re-employment events with defined employment periods that can impact benefits based on the related closure and cancellation transactions. | The system will be configured and the new business rules for multiple retirements based on eligibility and vesting will be coded into the system. This will allow for data migration to bring in multiple retirements to NPRIS for a single member and the system to cater to multiple retirements for a member. The system will have to be changed to have members to be retired as well as be re-employed and accruing serivce credit and contributions and any new retirement requests will have to look for service credit within a data range (start from previous retirement date)
SR-12 | Provide and Administer Benefits | Manage Member Accounts | Account Maintenance | NPRIS must be configured to process Qualified Domestic Relations Orders (QDRO) from OPS plan participants according to OSERS business rules. | Normally, QDRO comes into picture during refunds and retirement processes. During either of the process, court order information(case number, divorce/marriage date, benefit/refund percentage, method of benefit - flat amount/percentage, service credit, etc.) will be entered into the system and refund/regular benefits will be calculated and disbursed accordingly.
SR-13 | Provide and Administer Benefits | Manage Member Accounts | Manage Service Credit Business Rules | A full-time member of the retirement system who has completed 5 or more years of Omaha Public School service may purchase up to five years of service credit at any time prior to retirement. NPRIS must be configured to accommodate distinct business rules for processing multiple types of OSERS Optional Service Credits in NPRIS inclusive of eligibility rules, cost calculation rules (including but not limited to amortization interest, interest rates, monthly interest posting, etc.), source of funds for payment (e.g., payroll) and other workflow / configuration needed to support the process as necessary. | OSC can be purchased if OPS employees meets the vested criteria of 5 or more years of earned service before retirement. NPRIS OSC purchases will be distinguised from OSERS OSC types via static data entry - eligibility rules, OSC cost factors. Initially, purchase request will be created with the cost details of the purchase. After the request, an agreement will be created for the same via NPRIS agreement sytem. Once agreements are created, payments can be made in Installments, Lumpsum payments - via payroll deductions, OSC post/pre-tax checks, and also payment by employer on behalf of employee.
SR-14 | Provide and Administer Benefits | Manage Member Accounts | Manage Service Credit Business Rules | The system will need to be configured to allow conversion of the data related to all existing Optional Service Credit agreements from OSERS and any active (e.g., in-flight) agreements and associated workflow to be configured. After the transfer, NPRIS must be able to continue processing in-flight Optional Service Credit purchases with no or minimum impact to OSERS members. | Pending/In-progress agreements from the OSERS system to the NPRIS system will be handled through data migration process. Once the data migration completes, those agreements will be viewed on the NPRIS system - tab agreements/payments. Payments can be made in Installments, Lumpsum payments - via payroll deductions, OSC post/pre-tax checks, and also payment by employer on behalf of employees.
SR-15 | Provide and Administer Benefits | Manage Member Accounts | Manage Service Credit Business Rules | NPRIS must be configured to ensure expired / closed purchase of service options that may have been obtained by OPS members is accurate reflected in the system. | Once the data migration completes, those expired/closed agreements will be viewed on the NPRIS system - tab agreements/payments. Concept of "Extended Interest" must be incorported while creating agreements if there is a business requirement to renew Expired Agreements .
SR-16 | Provide and Administer Benefits | Manage Member Accounts | Manage Service Credit Business Rules | NPRIS shall track all payments related to the service credit purchase agreement via installment and payroll deduction payment plans until the agreement is paid off in full, with all service credit and payment information available in the history of the member account for reference and/or calculation of the benefit (including the service credit). | Installment Purchases of Agreement should be enabled if not already in NPRIS. The system will need to get Wage code for Installment purchases so that the money coming against this wage code can be routed for Tax-Deferred-Payment Purchase. New Indicator ( if not present already) should be allowed in Agreement Screen. Need to check if Service Proration is required or already present, based on this Member Account Maintenance Service Credit calculation logic needs to be changed.
SR-17 | Provide and Administer Benefits | Process Applications & Claims | Process Retirement Applications | NPRIS shall support OSERS Retirement Application Processing in NPRIS. | Once new OSERS plan is added via employer maintenance and Static data entries are done, retirement business rules(based on age, total service credit, retirement date, highest pension factor, etc) will be determined/incorporated for the newly added OSERS plan - benefit structure in the NPRIS current system.
SR-18 | Provide and Administer Benefits | Process Applications & Claims | Process Retirement Applications | NPRIS must be configured to allow the transfer of the full actuarial cost to pay the anticipated state service annuity benefit as part of the retirement closeout business event (which may not be accommodated in NPRIS today). | Our team's developers would need to investigate this issue in further detail to determine configuration challenges
SR-19 | Provide and Administer Benefits | Process Applications & Claims | Process Retirement Applications | NPRIS shall be configured to support business rules for processing NPERS and OSERS retirement applications and claims as defined by policy or statute even in cases where NPERS business rules are different than OSERS business rules. | Currently NPRIS retirement closeout process has NPRIS business rules implemented for retirement applications. When OSERS is implemented within NPRIS, the system will be configured for its own retirement business rules(eligibility criteria - based on age, service credit, FAS, pension factor and other parameters if any specific for OSERS) and claims.
SR-20 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Apply Benefits Adjustment | NPRIS must be configured to process OSERS Benefit Adjustments in NPRIS according to OSERS business rules. These business rules include provisions for multiple death benefit scenarios (including supporting Death Redistribution functionality), pension rights and divorce, military service provisions, COLA, Medical COLA, and Medical Cola Overrides that may differ between NPERS and OSERS. | The system will have to be configured and coded for this reqirement. Once the rules are established for the multiple retirement, rules can be gathered for multiple death benefit scenarios and the same will be developed in to the NPRIS system,
SR-21 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Apply Benefits Adjustment | NPRIS must be configured to support the Medical COLA process (which is not be currently configured in NPRIS today), including but not limited to establishing fields to capture related data, associated calculations, and setting up this option in the plan for retirees. This may also have configuration impacts to the existing death process workflow and calculations that need to be assessed and accommodated. | This can be configured by including in the benefit adjustment under gross category, such that Medical COLA gets included in the benefit calculations and death workflow process This Medical COLA can either be entered into the system via online screens or through batch job which perfoms Medical COLA calculations(by identifying eligible retirees and business rules.).
SR-22 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Calculate Benefits Amount | NPRIS must ensure all calculations align with business rules specific to each plan and variation between OSERS and NPERS. Areas of assessment for potential differentiation should include but not be limited to: average compensation calculation rules, retirement options, and benefits calculation using the entire account history vs. segments of account history corresponding to a retirement instance (benefit account) to be calculated. | Currently NPRIS system has NPERS business rules implemented for retirement applications. When OSERS comes into the process processes such as benefits calculations, retirement options will have its own business rules(eligibility criteria - based on age, service credit, FAS, pension factor and other parameters if any specific for OSERS) and claims.
SR-23 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Calculate Benefits Amount | NPRIS must be able to calculate/recalculate benefits based on date ranges selected and produce benefit calculations based on the range of time applicable to each retirement event because OSERS allows independent calculation of benefits today. For example, OSERS business rules allow a retiree to return to work and accrue additional service. After five years, the member can qualify for a new retirement benefit on just the additional service. Each such benefit is calculated independently. | The system will be configured and the new business rules for multiple retirements based on eligibility and vesting will be coded into the system. This will allow the system to calculate/ recalculate benefits based on date ranges
SR-24 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Member Interest Posting | NPRIS must be configured to support OSERS interest rates. | Static data will include the interest rate specifc to OSERS plan. Based on the interest rates, interest posting will be carried out either by interest posting batch job (which will run after the contributions are posted for the last month of the previous fiscal year to perform the actual calculation and posting of interest to member accounts as of the end of the previous fiscal year) or through Interest Adjustment screen based on the account balance.
SR-25 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Member Interest Posting | NPRIS must be configured to support OSERS plan calculations (e.g., posted monthly based on the balance at one point in time during the year). | OSERS plan calculations will be based on the interest rate slabs available for OSERS plan in the static table as like existing plans in NPRIS system. Need clarification regarding Monthly/yearly account balance
SR-26 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Estimate Member Benefit Calculation | NPRIS must be configured to provide, for OSERS data, the OSERS Benefits Estimates/Calculator in NPRIS including but not limited to incorporating the available benefit types and retirement options. | This activity allows the web user to calculate benefit estimates on-line user-entered parameters. The web user can calculate a benefit estimate for a specified retirement date or dates, comparing the retirement options appropriate to their plan and coverage. Data in the static table should be added with OSERS plan details and Generate Benefit Estimate Process of the Member Functionality should be modified according to OSERS rule if plan is "School Plan".
SR-27 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Estimate Member Benefit Calculation | The end-state NPRIS system must calculate the correct state service annuity using the service credit balance. | Calculations are based on the applicable Pension Factor for years of service and percentage of FAS for the specific plan in which the member is enrolled into the system.
SR-28 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Employer Accounts | NPRIS must allow OPS to be configured as an employer in NPRIS. | Maintain Organization activity can be used to capture the organization's demographic information. For a new employer, it will also capture the reporting information and other details about the employer. Anytime an employer changes plans or any other detail, the system screens can be used to enter the data.
SR-29 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Employer Accounts | NPRIS must support employer invoicing for OPS plan contributions. | Once the regular wages and contributions are posted into the member's account, an invoice summary by reporting period can be created and sent to the employer for the payment.
SR-30 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Wages and Contributions | NPRIS must be configured to support payroll deductions (e.g., pre-tax payroll deductions; post-retirement benefit inclusive of the purchase of service credit) as allowed by the OSERS plan. | Apart from regular wages and contributions that are reported, employer will have to send in payroll deduction details for the OSC purchases through a separate deduction code. Payment for this code will be handled separately to award purchased service.
SR-31 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Wages and Contributions | NPRIS must be configured to support the OSERS Wage and Contribution business rules, workflow, calculations for penalty and interest, and associated reporting. NPRIS must be able to accept and process monthly payroll data from OSERS similar to existing school plan in NPRIS. NPRIS must be able to accept and process payroll adjustments from OSERs. NPRIS must be able to accept and process Non-cons from OSERs. | Validations and Postings batch jobs will be modified to handle OSERs new business rules(wage limitation, hours reported, wage codes, basic member record validations - name, SSN, DOB, etc.) same as that of existing plans in NPRIS.
SR-32 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Wages and Contributions | NPRIS must be configured to support partial posting (e.g., the NPRIS batch process for posting employer payroll and contribution files must be modified to support partial posting). NPRIS will currently only post such files if 100% of the records are valid and contain no errors. If an error in a record is encountered, all posting transactions from the file are rolled back. This approach would degrade batch processing performance and create unacceptable processing delays for an employer the size of OPS. NPRIS must be configured to post the valid payroll records if the file meets an established threshold, such as 85 to 90% valid records. The valid records must post and records containing errors must be flagged for correction. | The NPRIS system can be modified to post as many wage and contribution records if they have passed all the validation rules. This posting of member records can be done based on a threshold of the number of records passing al the validations. Other non-posted records will be marked as either flagged/suspended based on the error messages they hold and will be processed in the subsequent postings batch runs(after user edit).
SR-33 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Inbound & Outbound Payments | NPRIS must be configured to accommodate any new fiduciary accounts necessary for processing (e.g., new bank accounts). | Maintain routing information process allows the user to capture the benefit retiree direct deposit information. NPRIS would use the Direct Deposit Authorization for retirees form to capture the new or changed direct deposit information and Waiver of Direct Deposit form in case if the benefit retiree wants to stop the direct deposit/ not to have a direct deposit. This process would also allow the user to add the new bank if the bank does not exists in the system while capturing the direct deposit information. And payroll would use the added Direct Deposit Information after the pre-note verification is done.
SR-34 | Provide and Administer Benefits | Manage Contributions and Process Benefits | Manage Inbound & Outbound Payments | NPRIS must be configured to support OSERS transaction types to support the tracking of historical, in-flight, and future financial transactions. | General Ledgers static data tables will be modified to accommodate the new OSERs school plan GL codes and this can be viewed in the GL browser screens(both historical as well as current transactions).
SR-35 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | NPRIS must be configured so that existing self-service features in PeopleSoft must be also provided in NPRIS, including the below:
SR-35.1 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | Online benefit estimator | Self Service system can be modified according to the OSERS business rules to calculate benefit estimates.
SR 35.2 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | Ability to view payment advice details including these 5 components: 1 = Benefit of prior to 1951 service 2 = Taxable Omaha Benefit amount 3 = Non-taxable Omaha Benefit amount, which includes contributions prior to 1985 or buy in with after-tax dollars, so this is not taxed 4 = State Service Annuity 5 = Medical Cost of Living | Retiree’s current pension warrant details, Direct Deposit Information and Tax data can be viewed in the retiree's home page. Using this screen, the user can view the exact net pension amount that the retiree’s are going to get for the current month and the various line items(taxable benefit amount, non-taxable benefit amount, service annuity details) and deductions involved on the warrants. These screens can be modified to show the other details mentioned in points 1 through 5.
SR-36 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | NPRIS must be configured so that self-service features in NPRIS that are available for other plans are also provided to the OPS plan members, including the below: a. Ability to reprint 1099R, b. Ability to change tax withholding preference c. Online benefit estimator d. Purchase of service credit estimator e. Ability to view account details, including balances f. Ability to view benefit payment information g. Ability to view beneficiaries h. Ability to view and update demographic information | As like NPRIS self service system, OPS plan members/retirees will also be able to view the 1099R, tax information, perform benefit calculations, perform OSC purchase estimation, view benefit details, modify/view demographic information, view beneficiary information. This will be achieved once the OSERS plan is enrolled into the NPRIS system.
SR-37 | Provide and Administer Benefits | Provide Self-Service Tools | Provide Self-Service Portals | NPRIS must be configured to allow OSERS to submit and validate payroll data like existing school plan in NPRIS. OSERS must be able to submit and validate payroll adjustments. OSERS must be able to submit Non-cons. | Employer screens within the Self Service application can be used to submit and validate Payroll data for the employer. The employer can choose to create and submit either Regular reports or Adjustment reports
SR-38 | Provide Agency Services | Provide Education Services | Provide Education Services | NPRIS must be configured to support any education services currently provided to OSERS members in the OPS PeopleSoft System, which may include but are not limited to: online help functions, frequently asked questions, etc. | Based on the OSERS business rules document provided, self service pages will be uploaded/modified with the appropriate help functions, FAQs, etc.
SR-39 | Provide Agency Services | Provide Education Services | Provide Education Services | NPRIS must be configured to be able to register OSERS members for retirement seminars. | This requirement can be simple or complex based on OSERS' functional needs. For instance, it his simply registering for announcements emails, or is a complex attendence system required. Developers would need to investigate this further
SR-40 | Provide Agency Services | Provide Member Services | Provide Member Services | NPRIS must be configured to support any member services currently provided to OSERS members in the OPS PeopleSoft System, which may include but are not limited to: automated communications, automated notifications, contact us features, self-service and reporting features, etc. | The NPRIS system can be modified to accommodate the current functionality the members of the OSERS system have. These functionalities will be discussed in the requirements gathering phase of the project and will appropriately be either added or an alternative will be provided.
SR-41 | Provide Agency Services | Provide Member Services | Provide Member Services | NPRIS must be configured to enroll and maintain beneficiaries for OPS plan participants according to OSERS business rules. | Beneficiary could be a new member or already enrolled in the NPRIS system. Once a beneficiary is chosen, then the relationship between the owner and the beneficiary should be provided and the beneficiary type should be specified - survivor or refund, and the benefit amounts for the beneficiaries will be calculated as per OSERS benefit rules(percentage to be awarded, etc).
SR-42 | Provide Agency Services | Provide Data Services | Provide Document Management Services | NPRIS must be configured to support document management of content converted and migrated to NPRIS (i.e., Hyland OnBase ECM) as digital media converted from OSERS non-digital content (e.g., paper, microfilm). | The current document management system can be configured in accordance with the OSERS business rules/ requirements
SR-43 | Provide Agency Services | Provide Data Services | Provide Document Management Services | NPRIS must be configured to accommodate any OSERS-specific document types and associated templates for forms, letters, etc. | The document inventory tables can be configured to hold the new document types and associated tempaltes can be created and incorprated into the NPRIS system
SR-44 | Provide Agency Services | Provide Data Services | Provide Reporting Services | NPRIS must be configured to ensure compliance with State and Federal Reporting requirements, including Federal Tax Reporting requirements. | 1099r reports functionality within NPRIS can be leveraged, including forms(1-a, etc) specific to States, gross benefit amount, taxable amount for the assessment year, total deductions taken out in the pension checks, insurance details and so on.
SR-45 | Provide Agency Services | Provide Data Services | Provide Reporting Services | NPRIS must be configured to support all reporting options available in the OPS PeopleSoft System today, including the configuration of reports in NPRIS. | Based on the available OPS PeopleSoft reports, additional reports might have to be developed in NPRIS system or eixsting reports can be configured to handle OSERS reports also.
SR-46 | Provide Agency Services | Manage Stakeholder Relationships | Manage Stakeholder Relationships | NPRIS must be configured to support any stakeholder relationship management functionality available in the OPS PeopleSoft System today, including but not limited to history of member transactions and interactions with staff or other features that help ensure customer satisfaction. | Stakeholder relationship management functionality will be handled in the Notes screen, Contact History screen, which will have the following information: Contact Log screen displays a detailed listing of all processes for an individual or organization, both workflow and non-workflow. This screen will be used for reference by the user to see the history of an individuals or organizations activity. Notes screen is to maintain notes related to a person/organization/member account. For Example, notes for benefit estimate calculations etc. can be registered here so that other users would be able to refer to them. These notes will not be printed on any reports or estimates. It is for internal use only.
SR-47 | Ensure Security & Mitigate Risk | Conduct Internal Audits | Verify Compliance of System Records with Established Policies | NPRIS must be configured to have a mechanism for users to distinguish converted data and historical transactions migrated from OSERS vs. new data created once the transfer has taken place. | Converted data and New data can be distinguised using unique transaction codes for converted data and using unique record creator names during conversion process
SR-48 | Ensure Security & Mitigate Risk | Conduct Internal Audits | Data Security | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) security provisions for protection of data. | Data that requires masking will be masked in reports and letters and development databases will also be mased - SSNs, routing numbers, bank account numbers, member/retirees address details, etc.
SR-49 | Ensure Security & Mitigate Risk | Conduct Internal Audits | Security Roles & Permissions | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) security provisions, including user roles and security permissions, as available in the OPS PeopleSoft System. | Existing roles and groups from the NPRIS system can be used or new roles and groups can be created for the OSERS system and the existing system security will be leveraged for the new OSERS project
SR-50 | Ensure Security & Mitigate Risk | Perform Fraud Detection | Perform Fraud Detection | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) security provisions, including user roles and security permissions, as available in the OPS PeopleSoft System. | Existing roles and groups from the NPRIS system can be used or new roles and groups can be created for the OSERS system and the existing system security will be leveraged for the new OSERS project
SR-51 | Ensure Security & Mitigate Risk | Conduct External Audits | Conduct External Audits | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) reports, workflow, etc. to support any external audits that may need to be conducted (if applicable). | Existing workflows and reports from the NPRIS system can be leveraged and if new workflows or reports are needed as determined by the requirements phase, then the same will be created.
SR-52 | Ensure Security & Mitigate Risk | Ensure Business Continuity / Disaster Recovery | Ensure Business Continuity / Disaster Recovery | NPRIS must be configured to accommodate existing (or comparable to OPS PeopleSoft System) business continuity / disaster recovery functionality (if applicable). | Existing Business Continuity/ Disaster Recovery proceses will be leveraged for this requirement. If there is a need to change a process within the existing Business Continutiy/ Disaster Recovery process, as determined in the Requirements gathering phase, then the change will be made appropriately.
SR-53 | Steward Funds | Maintain Finances and Accounting | Manage General Ledger | NPRIS must be configured to incorporate the OSERS General Ledger chart of accounts so that general ledger transactions are properly posted for all financial activities. | General Ledgers static data tables will be modified to accommodate the new OSERs school plan GL codes and this can be viewed in the GL browser screens(both historical as well as current transactions). These codes will also be used when financial activities(postings, purchases, retirements) are carried out on OSERs member account.
SR-54 | Steward Funds | Maintain Finances and Accounting | Manage General Ledger | NPRIS must be configured to accommodate the fiscal year range for the OSERS plan (which may differ from NPERS's fiscal year). | OSERS plan's fiscal year details will be configured in the static table as like NPERS's fiscal year data. GL browser screen will be modified to display the fiscal year date range based on the plan selected(OSERS or NPERS).
SR-55 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to calculate the OSERS Annuity Payroll in NPRIS. | Current payroll system (monthly batch job) in NPRIS - calculate each individual benefit recipient's/vendor’s warrant amounts who are receiving pension warrant. The recipient pension warrant amount is determined by adding pension amount, cola amount, and positive adjustment amounts then deducting federal tax, state tax, insurance and any other applicable deductions. Current system will be modified to include OSERS plan also, when a member becomes eligible to retire and starts receiving pension on OSERS plan(based on OSERS specific retirement eligibility rules)
SR-56 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to allow for the "prior 1951 benefit" to be part of the benefit roll and downstream processing. | Developers would need additional details to determine how to achieve this requirement. For instance, is there a specific indication to be marked for members having "prior 1951 benefit"?
SR-57 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to support tax levy garnishments. | Tax Levy Changes letter will be mailed to a benefit recipient when NPRIS system receives a tax levy from the Internal Revenue Service, levying the net benefit. This levy will be processed with the payroll in the given deduction amount unless NPRIS system is notified to release the levy.
SR-58 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to support benefit recipients splitting their benefit payments into multiple accounts (e.g., splitting a single benefit check to multiple direct deposit accounts). | The system will have to be configured and coded for this reqirement. Once the rules are established for this requirement, the same will be developed in to the NPRIS system,
SR-59 | Steward Funds | Maintain Finances and Accounting | Annuity Payroll | NPRIS must be configured to execute existing OSERS direct deposits so that members do not have to re-enroll for direct deposits after the transfer (e.g., set up routing numbers, etc.). | If OSERS members have already opted for direct deposit information(routing numbers, bank details) in OPS PeopleSoft, then the data migration process will take care of handling the data into NPRIS system mapping to the appropriate business entities.
SR-60 | Steward Funds | Maintain Finances and Accounting | Manage Third Party Account Participants | NPRIS must be configured to issue payments to the third-party payees outside of NPRIS for the amounts recovered after benefit runs against the benefit receivable tax levy line items. | The system can either leverage existing functionality to issue payments to third-party payees or new functionality can be developer after it is discussed in the requirements phase of the project and rules are established
SR-61 | Steward Funds | Maintain Finances and Accounting | Request Refunds and Transfers | NPRIS must be configured to accommodate any OSERS-specific refund types for members and death situations not already configured in NPRIS (inclusive of Death Refunds, impact to a beneficiary if a member dies in retirement with an outstanding A/R). This may also need to include accommodating any configuration necessary for in-flight refund requests that need to be configured in NPRIS (depending on determined approach of how to address in-flight refund requests). | Currently NPRIS system processes Member, Death(Beneficiary), Residual refunds. If OSERS has other refund types apart from the above mentioned, then the NPRIS system(Refund batch job) will be modified to capture these scenarios as per the norms.
SR-62 | Steward Funds | Maintain Finances and Accounting | Request Refunds and Transfers | NPRIS must configured to allow users to view migrated OSERS data associated with refund and retirement transaction events so that it is available for reference purposes. | Refund application screens are used to create/view the member refund applications. Once OSERS data are migrated to NPRIS system specific entities, existing(if any) application details can be viewed on the refund screens. Retirement transaction details will be displayed on the transaction screens. Once OSERS converted retirement data comes into NPRIS system via migration, transaction screen will populate the appropriate retirement data.
SR-63 | Steward Funds | Maintain Finances and Accounting | Request Refunds and Transfers | NPRIS must be configured to allow a new or existing fiduciary account to enable output payments for OSERS for cash disbursements related to refunds. | Maintain routing information process allows the user to capture the member's direct deposit information. NPRIS would use the Direct Deposit Authorization for members form to capture the new or changed direct deposit information and Waiver of Direct Deposit form in case if the member wants to stop the direct deposit/ not to have a direct deposit. Refund checks are disbursed to the OSERS members based on the opted direct deposit information.

## 3. Imp. Svcs. Requirements
Tab 3. Implementation Services Requirements
Req ID | Implementation Phase | Implementation Service Requirement (ISR) | Responsibility |  | Describe, generally, the process of how the bidder's solution will accomplish this requirement.
|  |  | Bidder | NPERS
ISR-1.1 | Implementation Planning & Management | Provide a Project Manager (PM) to represent the Bidder in the management of the Project, interfacing with NPERS Project Manager (PM) in any decisions relating to the Project. | X |  | Linea has created a Project Management Office (PMO) to fully cover all aspects of Project Management on the project, including executive oversight, quality assurance, technical compliance, and risk management. We have assigned a lead project manager (PM) to head all day-to-day activities and be the key point of contact between Linea's team and NPERS project management. Linea uses PMBOK project management standards.
ISR-1.2 | Implementation Planning & Management | Assume and lead all day-to-day management of all Bidder personnel, including subcontractor personnel, and development of Deliverables related to the required services. | X |  | Linea's lead PM will oversee all assigned Linea staff as well as the subcontracted staff used. Additionally, our subcontractor has provided a development manager to coordinate with Linea's lead PM. The lead PM will provide regular reporting, will address and coordinate personnel issues and will be fully available to NPERS project stakeholders and will communicate on a daily basis based on project progress and challenges.
ISR-1.3 | Implementation Planning & Management | Provide a Project Manager to represent NPERS organization in this Project, interacting with the Bidder’s PM, and representing NPERS in any decisions relating to the Project. |  | X
ISR-1.4 | Implementation Planning & Management | Escalate items to the project governance (e.g., Steering Committee) for awareness and decision-making. |  | X
ISR-1.5 | Implementation Planning & Management | Participate in governance committee meetings upon request, and present project status. |  | X
ISR-1.6 | Implementation Planning & Management | Maintain a Disaster Recover or Business Continuity Plan that describes the approach to perform disaster recovery activities. |  | X
ISR-1.7 | Implementation Planning & Management | Conduct project oversight activities. | X |  | Linea has assigned an Oversight Executive, Ray McIntosh, to provide oversigth and quality assurance of the entire initiative. He is part of Linea's assigned PMO, and will provide guidance and strategy to both the Linea team as well as to NPERS' stakeholders throughout the initiative. Ray was the original project manager overseeing the assessment for the feasibility of this project.
ISR-1.8 | Implementation Planning & Management | Interface with and support requests from Independent Project Oversight Consultant contracted by NPERS. | X |  | Linea is comfortable working with independent oversight vendors on projects of this caliber. We have been the independent oversight vendor on state-level and large scale pension and benefits modernization efforts, including IV&V, Board-level & OCIO auditing, executive oversight, and quality assurance. We have also worked with auditors and executive teams as project leads. We will work to collaborate with all parties involved, we understand that all parties are seeking win-win outcomes for the initiative, and will provide assistance and reporting to all teams and committees as required.
ISR-1.9 | Implementation Planning & Management | Provide a robust Project management methodology founded on industry best practices and covering all key project management processes. | X |  | Linea uses the Project Management Institute's (PMI) Project Management Body of Knowledge (PMBOK) as our standard for project management activities. All three of our assigned project managers in the our PMO for this initiative are Project Management Professionals (PMP). Additionally, we use Prosci and the ADKAR process standards for our change management methods. we use Six Sigma Lean practices as part of our business process improvement on most projects. We understand and use Agile, Agile-Hybrid, and Waterfall practices as a project requires (with this project primarily being Agile-Hybrid).
ISR-1.10 | Implementation Planning & Management | Conduct project management activities throughout the life of the Project, maintaining planning documents current and executing the associated plans. | X |  | Linea has assigned a team of project managers to oversee all activities and coordinate with the NPERS project manager. This includes regular reporting, upkeep of project tracking documents such as the project plan and the RTM, and monitoring of all risks and issues.
ISR-1.11 | Implementation Planning & Management | Provide, update, and maintain a formal Project Management Plan (PMP) that includes the following key components: - Project initiation activities, including developing Project Kickoff materials. - Risk and Issue Management Plans & Logs – Risk and Issue Management Plan, Escalation Plan, and Risks, Assumptions, Issues, and Dependencies (RAID) log. This should include risk management, identification, quantification of impact, monitoring, and mitigation plans. - Quality management. - Bidder and sub-contractor resource management. - Project success evaluation criteria and Project close-out activities. - Document management approach and document repository. - Relationships to other IT or business efforts. - Integrated Change Management Plan that outlines the change management process, including change request template, impact analysis template, request approval process, and processes for management and tracking of change requests. - Deliverable/product review and approval and other acceptance criteria. - Status and other reporting activities, including status reporting templates (including deliverable status reports, issues, risks, plan vs. actual status, etc.). | X |  | Linea will work with NPERS in the first month to confirm the project plan and build a project charter which includes a project management plan, project schedule, resourcing plan, governance, risk management plan, change management plan, deplayment plan, and confirmation of deliverable expectations. Linea follows PMBOK standards combined with customization based on our past experience with pensino fund implementations. Linea uses Prosci concepts and practices when designing change management initiatives, and specifically the ADKAR approach.
ISR-1.12 | Implementation Planning & Management | Develop project kickoff materials - Conduct a project kickoff meeting with key stakeholders within thirty (30) days of contract execution. The kickoff meeting will provide an overview of the project objectives, plans, project scope and schedule, introduce the Bidder’s project team and roles and responsibilities, and outline project start-up procedures. | X |  | Due to the rigid timeline of this project, Linea intends to schedule a project kick-off include both Linea and NeuOrbis teams plus all associated NPERS stakeholders within the first week of project launch. The kick-off will last two hours and will cover broad topics on what to expect from the project as well as information on activities to occur in the first month during project setup.
ISR-1.13 | Implementation Planning & Management | Identify, document, provide, and implement risk mitigation measures and contingency plans as high-priority risks are identified and monitored. | X |  | Risk mitigation is a standard part of Linea's project management practice, including the use of a risk register and a heat map to track the severity and likelihood of all project risks. Linea categorizes risks as "Project Level," "Steering Committee Level," and "Board/Public Level."
ISR-1.14 | Implementation Planning & Management | Provide Ongoing Project Management Duties - Provide weekly project plan and schedule updates, weekly status reporting, weekly status meetings, risk and issue monitoring, and integrated change management activities. In addition to weekly status meetings, the Bidder’s Project Manager should participate in project Steering Committee meetings and other NPERS meetings as required. | X |  | Linea will provide a weekly status report to keep all relevant parties apprised of progress, potential risks, and milestones reached. The format of this report will be customized and decided upon by Linea and NPERS in the first month of the project. A linea project management representative will attend every steering committee meeting, either through zoom, or on-site as applicable.
ISR-1.15 | Implementation Planning & Management | Provide Project Status Reports and conduct regularly scheduled status meetings reviewing Project progress, risk mitigation, issue resolution, deliverable status, and next steps as mutually agreed upon by NPERS and the Bidder. | X |  | Linea will customize the frequency and type of reports created to meet the needs of all relevant parties. For instance, board reports will be at a higher level and will focus on overall progress, while weekly reports will address actionable and immediate activities and issues.
ISR-1.16 | Implementation Planning & Management | Use the documentation repository as agreed to and documented in the Project Management Plan deliverable. | X |  | Linea has work with many types of document repositories. We regularly use Box.com and Sharepoint on project initiatives, but are able to adapt to any tool or repository decided upon by NPERS. We typically take early steps to ensure security measures and practices regarding repository use.
ISR-1.17 | Implementation Planning & Management | Provide, update, and maintain a Baseline Project Schedule and Work Plan to reflect the project timelines, milestones, and deliverables. Provide periodic updates (as mutually agreed upon by NPERS and the Bidder) to the Project Schedule which is maintained by the Bidder. The Schedule will include the following key components: - A consolidated view of the activities, activity descriptions, and activity durations assigned to stakeholders and Bidder. - Gantt chart(s) and a project calendar in Microsoft Project that is developed and maintained in accordance with industry best practices. - Resources (NPERS, other stakeholders, and Bidder) assigned to each activity and their required level of effort. - A list of all required project deliverables tied to the appropriate project milestones. - Identification of all key project milestones. - Deliverable approval periods compliant with NPERS’ Deliverable Expectations Document process as described in the following section Deliverable Expectations Document. - A critical path analysis and reporting process. The work plan will reflect any changes from the baseline Schedule originally agreed to during the project initiation and be updated/published on a weekly basis. | X |  | A project plan is created and confirmed in the first month during project setup. Linea prefers Micosoft Project due to a robust project tracking and Gantt chart feature set, we use this software with most of our pension adminstration system implementation oversight projects and will do so with NPERS. All deliverables will included a DED. Critical path issues will be accounted for in the plan and addressed during weekly reports. Adequate approval time will be given to NPERS to review deliverables.
ISR-1.18 | Implementation Planning & Management | Deployment Planning - Conduct workshops with NPERS and other stakeholders to finalize approach for deploying the transferred functionality into production. | X |  | Deployment strategy will begin during project initiation, but will be refined and updated as the project enters UAT and closes toward launch. Deployment preparation will be integrated into final training. Analysts, project managers, and the training lead will all be heavily involved with the deployment phase.
ISR-1.19 | Implementation Planning & Management | Develop an Initial Deployment Plan (e.g., transition planning to finalize rollout details). Finalized approach for deploying the transferred functionality into production including any benefits and risks of strategy, including: - Overview of the current environment and considerations for deployment. - Identification of high-risk transition areas and impact, mitigation strategies, and recommended mitigation actions. - Any ongoing risks, based on finalization of phasing approach, should be tracked in a risk log. - Any decisions that impact the schedule should be documented in the project schedule. - Any cutover consideration(s) should be documented in the final Cutover Plan. | X |  | The initial deployment plan will be created during the first month of project initiation, though may evolve and be updated based on the development and discovered needs of the project. Linea's project management lead will work directly with NPERS' project lead to map out all deployment activities.
ISR-1.20 | Implementation Planning & Management | Create a Solution Environment and Configuration Management Plan (e.g., sandbox, development, testing, training, etc.) required to support all project phases including obtaining licenses (if applicable) and other required infrastructure. The Plan should describe the following (at a minimum): - Approach for managing programming changes and configuration settings made in NPRIS to transfer the OPS retirement plan, including testing, final approval of deployment, and deployment. | X |  | Linea will work with NeuOrbis to create a Configuration Management Plan, including all necessary environments. Finalization of this plan will occur during the late stages of requirements gathering. Linea will coordinate with NPERS' IT staff to ensure understanding, expectations, roles, and and governance of configuration management.
ISR-1.21 | Implementation Planning & Management | Implement the environment configurations required to support the project implementation. |  | X
ISR-1.22 | Implementation Planning & Management | Document proposed deliverable content, format, and acceptance criteria in Deliverable Expectation Documents (DEDs) as mutually agreed upon by NPERS and the Bidder. | X |  | DED's are standard components of many Linea projects. Ideal DED's employe brevity, language that is clearly understood by many types of stakeholders, and which have focus on key points of value brought forth by the deliverable.
ISR-1.23 | Implementation Planning & Management | Approve or request changes to Deliverable Expectation Documents (DEDs). |  | X
ISR-1.24 | Implementation Planning & Management | Provide project background information such as relevant charters, documentation, organization structure. |  | X
ISR-1.25 | Implementation Planning & Management | Submit completed deliverables aligned with Deliverable Expectation Documents and meet target deliverable submission dates. | X |  | Linea will submit deliverables according to the project schedule and will assign review and approval time for NPERS to accept or request updates to the deliverable. Linea makes an assumption of up to two deliverable revisions based on NPERS' comments and questions during review.
ISR-1.26 | Implementation Planning & Management | Coordinate deliverable reviews and approvals. |  | X
ISR-1.27 | Implementation Planning & Management | Provide deliverable review comments and revisions needed for deliverable approval. |  | X
ISR-1.28 | Implementation Planning & Management | Prepare Change Requests as required. | X |  | Linea is flexible in its ability to adapting to the needs of our clients, whether that is an alteratation in resourcing, and adjustment to a schedule, a revision of scope, or simply a clarification of contract. Change requests are routed through the project manager and are addressed by the account exectuive.
ISR-1.29 | Implementation Planning & Management | Document impact analysis associated with proposed changes and follow the agreed upon change management process as documented in the Integrated Change Management Plan. | X |  | Linea agrees to document the impact of changes that occur, following along with the Integrated Change Management Plan (or Change Control Plan). Regarding this, we would like to note that Linea typically refers to the tracking of necessary project changes as "change control," and the preparation of an organization for the changes brought on by the project as "change management." Linea will perform both duties for this initiative.
ISR-1.30 | Implementation Planning & Management | Approve and prioritize changes. |  | X
ISR-1.31 | Implementation Planning & Management | Communicate Project scope change process and procedures to NPERS stakeholders. |  | X
ISR-2.1 | Requirements Review & Confirmation | Implement and establish a formal requirements management process that includes: - Implementation requirements tracking, maintenance, and traceability (e.g., to test scenarios/cases). - Develop a Requirements Traceability Matrix - Bidder will review the functional and technical requirements defined in Appendix X. Implementation Requirements to validate the Bidder’s understanding of the requirements to meet stakeholders’ expectations and identify areas for discussion. An RTM may include any design considerations, gaps, issues, or risks that need to be addressed throughout the project and should be maintained over time to track the status of each requirement. | X |  | Linea has a standardized requirements gathering and confirmation process which will be employed in the first months of the initiative. It is based on requirements gathered during other PAS initiative. After planning and stakeholder SME identification, Linea follows a six step process: Review of documents and rules, identify requirements in work sessions, analyze requirements for challenges and opportunities, document the requirements, NPERS SME review, and management review. All requirements are compiled into requirements documentation and an RTM, which is then used as part of development.
ISR-2.2 | Requirements Review & Confirmation | Develop a plan and schedule to conduct NPERS interviews, group workshops, and surveys to refine, and prioritize the detailed solution requirements. | X |  | Because NPERS SMEs are required for the requirements gathering workshops, but typically also have full work schedules maintaining organizational operations, Linea will work with NPERS stakeholders to build a schedule that does not interrupt critical operational processes and which is flexible based on the needs of SMEs. Requirements sessions take no longer than two hours, and we usually plan no more than two sessions per day. The Linea PM will work with NPERS' PM to solidify a schedule for these sessions.
ISR-2.3 | Requirements Review & Confirmation | Act as primary point of contact with stakeholders and offices to refine solution requirements, including scheduling NPERS staff for interviews and workshops. |  | X
ISR-2.4 | Requirements Review & Confirmation | Conduct and document NPERS interviews, group workshops, and surveys to refine, and prioritize the detailed functional and technical requirements. | X |  | Group workshops are step two of Linea's standard six step process of gathering requirements. Sessions last no more than 2 hours, are typically performed twice a day, three times a week. Beyond gathering the requirement, Linea looks for opportunities for improvement and potential implementation challeges during these sessions.
ISR-2.5 | Requirements Review & Confirmation | Coordinate, schedule and communicate with all functional and technical SMEs for planning sessions. |  | X
ISR-2.6 | Requirements Review & Confirmation | Conduct business process analysis and reengineering focused on the transition or transformation of source system business processes to the target system. | X |  | BPI and BPR are a standard part of Linea's requirements-gathering activities. There may be OSERS processes that are not necessary or require re-mapping or reconfiguring to smoothly integrate with NPRIS.
ISR-2.7 | Requirements Review & Confirmation | Understand target datasets and NPRIS architecture. | X |  | Linea's technical architect and NeuOrbis' technical lead will perform an analysis of the NPRIS datasets in the first months of the initiative (this is required to move data migration forward in parallel with development).
ISR-2.8 | Requirements Review & Confirmation | Create a Functional Fit Gap Analysis. Conduct and document assessments of detailed functional requirements and generate the fit-gap analysis between the source (PeopleSoft) and target system (NPRIS), including affected systems recommendations and alternative options. | X |  | The functional gap analysis is performed during steps three and four of Linea's standard requirements methodology. This analysis is reviewed for processes within each functional area.
ISR-2.9 | Requirements Review & Confirmation | Create a Technical Fit Gap Analysis. Conduct and document assessments of detailed technical infrastructure requirements and generate the fit-gap analysis, including network infrastructure, desktops, etc. | X |  | Similar to the functional gap analysis, the technical gap analysis occurs as a standard part of technical requirements gathering (steps 3 and 4). Though this analysis is performed through architecture review and requires fewer work sessions from NPERS IT SMEs.
ISR-2.10 | Requirements Review & Confirmation | Produce a Requirements Validation Document that documents any changes, revisions, clarifications to functional and technical requirements in the requirements repository (i.e., Requirements Traceability Matrix) to be maintained by the Bidder. This deliverable, once approved, serves as the validated detailed functional and technical requirements and includes security features. The requirements traceability matrix must be updated to reflect the approved Requirements Validation Document. | X |  | Linea has a standard RTM template and our lead functional analyst and project manager will provide design confirmation duties during the design phases through all sprints prior to UAT. This is document and is one of the most essential tools for a project of this nature.
ISR-3.1 | Design | Facilitate interviews, group workshops, etc. to obtain and gain consensus on design. | X |  | Linea's PM and functional lead will schedule and run interviews and design sessions and will gather input and feedback both before and after sessions in order to gain consensus on design. In order to achieve consensus, Linea focusses on the following principles: Efficiency - The process is viewed as being highly respectful of the investment required of each of the participants. This includes avoiding a longer than necessary string of meetings; both one-on-one and group discussions, that are deemed to be unproductive. Respectful - The process provides a forum for each of the participants to share their individual points of view. What we try to avoid is a situation where one point of view effectively overrules the opinions of others, thereby clouding the lines of common understanding and agreement. Realistic - The process recognizes that each of the participants have different priorities and concerns. We need to ensure that the strategic plan addresses these. A Process, Not an Event - Our experience with facilitation engagements tells us that the likelihood of success is maximized to the extent that all the participants understand that they are engaging in a process, rather than an event. Transparency - The process is considered by all participants to be unbiased and that no agenda is being promoted. Expert Support - The process is being supported by experts who can support the participants individually and collectively by sharing their experiences in similar circumstances.
ISR-3.2 | Design | Conduct and document functional and technical planning sessions to establish system configuration. | X |  | Design sessions proceed the requirements gathering phase of the project. NeuOrbis developers are brought into work sessions with Linea analysts and NPERS SMEs and stakeholders.
ISR-3.3 | Design | Provide a System Design Document, conceptual design documentation for required NPRIS modifications, data/content changes, and all activities required to achieve the transfer of the OPS plan into NPRIS. This deliverable includes: - “To-be” business process flows to address any requirements gaps identified and implement the validated detailed functional and technical requirements via configuration settings and custom development. - Updated Entity Relationship Diagrams. - Updated Data Dictionary. - Updated Security controls. | X |  | System design documents will be created and will include any BPI (Business Process Improvement) incorporated based on requirements. As Linea intends to execute a Hybrid-Agile style of development, the design documents will be created for functional areas to allow for development and system testing to occur early on (rather than completing all designs for all functional areas as would occur in a Waterfall project).
ISR-3.4 | Design | Develop the Solution Implementation Plan - Bidder will describe the implementation approach throughout application design, interface design, and conversion design. The Solution Implementation Plan should include the following (at a minimum): - How the Bidder will provide and/or leverage existing system management tools for all development environments and manage all development efforts using industry-standard software development tools and methodologies. - Ensure that the transferred components conform to defined standards for System design and Systems architecture. - Approach for managing programming environment changes including management of test and deployment of new releases while maintaining capacity to apply hotfixes to production. Note: NPERS should have the final authority to process and apply the hotfixes to production. | X |  | (1) In addition to leveraging the existing Clarety tools and scripts we plan to add industry recognized operations tools: Sonatype Nexus for its internal software repo features, Jenkins for its DevOps and automation capabilities, Chocolatey for its Nuget based software package management cabilities for Windows environments, and SonarQube for static code analysis. (2) In addition to code reviews we will leverage the SonarQube plugin from "checkstyle" to enforce coding standards.(3) We will leverage the capabilities of the source control toolset, and Jenkins automation capabilities to support build and deployment tasks in various environments to facilitate the current mainline and feature branch(s) release plans as outlined in the configuration and release management documentation. Jenkins automation supports both a manual approval step, as well as, Role Based Access Control (RBAC) over jobs that perform specific functions (e.g., A production deployment)
ISR-3.5 | Design | Bidder will provide the following sub-component plans as part of the Solution Implementation Plan that describe the following (at a minimum): Security Plan: Approach for continuing assurance of system security, including how the Bidder complies with applicable security protocols, regulations, etc. Security incident response plan details that describe the following (at a minimum): - Security roles and responsibilities, mission statement, key terms governing incident response, identification of an incident response lead, and incident detection channels. - Strategy to identify and categorize incidents. - Process to communicate, contain, eradicate, and recover from incidents. Infrastructure Services Plan: - Definition of each environment that will be required and used in the OPS Transfer Project activities (e.g., production, tagging, and test). - Approach for maintaining application and infrastructure component consistency across all environments. - Approach for certifying and/or providing quality assurance of environments. | X |  | (1) defer to security plan documentation; (2) defer to security plan documentation; (3) Clarety was originally deployed with a disaster recovery environment and plan, we will leverage both of these and extend them as needed to include system changes related to the onboarding of the OPS fund and any related new processes. (4) The additional environments needed to support the development and testing of OPS onboarding in accordance with the data migration plan and the feature release plan will include - Development environment(s), Staging, System Test environment(s), and UAT environments that are distinct from the current mainline Clarety environments.; (5) Component consistency will be managed through Jenkens jobs and processes defined in the "configuration and release management" documentation.(6) Certification of environments will be provided in two ways: first - as part of each deployment automation and/or manual verification checks will be performed; second the test team on completing tests as outlined in the test plan will certify the environment.
ISR-4.1 | Development & Configuration | Configure OPS retirement plan in NPRIS based on the solution requirements of the RFP (Appendix A), approved Solution Implementation Plan and detailed design requirements identified in the previous phase. Perform all necessary technical design, configuration, testing, or scripting, of systems as required to provide and implement the functional and technical requirements. | X |  | This work will be done leveraging the appropriate tools and processes to meet project goals, timing of milestones and key inputs will be coordinated with project stakeholders
ISR-4.2 | Development & Configuration | Define and document configuration management policies and procedures consistent with industry best practices. | X |  | Linea and NeuOrbis follow rigorous best practices regarding configuration management.
ISR-4.3 | Development & Configuration | Adhere to NPERS audit and configuration management standards. | X |  | Linea will work with NPERS in the first two moinths to ensure all work activities conform to all required standards
ISR-4.4 | Development & Configuration | Manage documentation of changes to the underlying environment via use of library management version control and turnover management. | X |  | Initial infrastructure architecture for the OPS onboarding will be created and stored in clients Content Hosting platform. These documents will be updated as infrastructure changes are made to reflect the current state of the system. We will also add release notes associated with each release to this system.
ISR-4.5 | Development & Configuration | Review configuration management results. |  | X | Linea will provide ample time for NPERS to review configuration.
ISR-4.6 | Development & Configuration | Perform configuration management activities throughout the Project. | X |  | We will provide processes and automation to continually manage CM activities through final delivery as outlined in the "configuration and release management" and the "coding standards" documentation
ISR-4.7 | Development & Configuration | Provide configuration management tools. |  | X | While this is demarked as an NPERS responsibility, Linea will work to confirm the full set of configuration management tools with NPERS collaboratively.
ISR-4.8 | Development & Configuration | Conduct code and configuration reviews to ensure compliance with NPERS standards to reduce defects. | X |  | refer to coding and configuration standards document
ISR-4.9 | Development & Configuration | Review and approve results of Bidder code and configuration reviews at NPERS’s discretion. |  | X | Linea will grant adequate time to NPERS for such review and approval. That being said, due to the time constraints of this project, it is vital that NPERS' allocates adequate resource availabilty for any staff reviewers and understands that delays in the review and approval process is a common and potentially serious risk on projects of this scope. Our PM will work with NPERS' project lead to ensure there is no breakdown in the NPERS approval pipeline.
ISR-4.10 | Development & Configuration | Schedule releases (e.g. configuration changes). | X | X | Scheduling releases is a standard component of Agile-Hybrid development and will be planned according to functional area. That being said, Linea wants to iterate that Agile-Hybrid differs from true Agile in that there will be no daily releases.
ISR-4.11 | Development & Configuration | Provide a Role to Position Mapping Document to map the end-user roles to the positions within the organization. | X |  | Clarety roles/positions are defined in the ibm-application-bnd.xml file which we will create an excel document listing the current NPRIS configuration and merge and/or create new OPS role/positions as required.
ISR-4.12 | Development & Configuration | Create a Cutover Plan - Bidder will perform go live cutover planning activities to assess transition readiness, go / no-go criteria, and fallback positions to be taken if no-go conditions are encountered for deployment. The Cutover Plan will include (at a minimum): - A preliminary cutover schedule that clearly defines key milestones, deliverables, tasks, and responsibilities. The Cutover Plan will be updated prior to go live. - Cutover milestones where readiness to proceed is assessed, go/no-go criteria, and fallback positions to be taken if no-go conditions are encountered. - Pre-cutover checklist and post-cutover evaluation criteria. - Transition readiness assessment, including the preliminary schedule, rollback strategy, assessment scorecards, and defined critical readiness criteria that will drive go / no-go decisions related to overall readiness / preparedness for going live with transferred components in NPRIS. | X |  | A cutover plan will be created during UAT including Go / No-Go criteria. Linea has assigned a training specialist for the last 5.5 months of the initiative to assist with transition planning, go-live readiness, and training on the new integrated system. Becuase NPERS faces a rigid deadline, Linea has scheduled the project with 1.5 months of leeway to prepare for and execute go-live prior to the July deadline. Linea will work with NPERS to build strategies for a No-Go, including adjustments to feature rollout that allow for the achievement of the deadline even providing unavoidable project delays.
ISR-5.1 | Data Conversion | Provide a Data Conversion Strategy, including identification of the methodology and tools for the migration of the source OSERS legacy data (PeopleSoft and external tables) to the target NPRIS system. | X |  | Linea follows standardized data conversion modsels including a data audit, data fix and reconciliation, and data balancing and verification. This process will start early and should be completed as testing activities are ramping up.
ISR-5.2 | Data Conversion | Provide a Data Conversion Plan, including identification of roles and responsibilities for Bidder and NPERS staff, and policies and procedures to ensure controls are in place in accordance with NPERS rules and regulations. This deliverable includes documentation of detail mappings from source to target data fields. The Plan will include (at a minimum): - Description of conversion methodology (e.g., processes to extract data, processes to validate data, documentation of data). - Number of mock runs that will be conducted (a mock run is an exercise of data conversion using the agreed upon mapping and transformation rules). - Description of manual conversion processes that cannot be automated. - Milestones, targets. - How much history is converted out of PeopleSoft / external tables and into NPRIS and the NPERS’ SQL tables. - List of data to not convert. - Manual data entry and error correction after conversion. - Plan for testing and validating converted data. | X |  | The objectives of the data conversion plan include: • Develop and Publish Data Migration/Conversion Directives • Analyze and Define Data • Develop and Publish Data Cleansing Directives • Conduct Data Cleansing Analysis • Establish Milestones for Conversion and Clean-up • Complete Data Cleansing/Corrections and Test • Work with developers to map data to NPRIS • Extract and Transform Data for use in NPRIS • Develop an On-going Strategy for Data Validation/Reconciliation and Cleansing to validate and reconcile during Data Migration Project Activities
ISR-5.3 | Data Conversion | Execute the approved Data Conversion Plan. | X |  | Upon approval of the data conversion plan, Linea has allocated two technical/data resources to execute on the plan to migrate data.
ISR-5.4 | Data Conversion | Specify, provide and install necessary tools for data mapping and conversion activities. This includes: - Extract, Transform, and Load (ETL) tools. - Tool for obfuscation of data. - Tool for automated comparison of financial accounting calculation results between OPS PeopleSoft and NPRIS. | X |  | Linea has a knowledge of and experience with a variety of ETL, obfiscation and security, and automated tools for assisting with the data conversion process. The data lead will work with OSERS and NPERS SMEs to install these tools in anticipation of conversion.
ISR-5.5 | Data Conversion | Assist with installation and configuration of ETL tools (e.g. legacy environments). |  | X
ISR-5.6 | Data Conversion | Execute Data Mapping– Map OPS PeopleSoft and External Table data to the appropriate NPRIS MS SQL tables, as well as execute conversion. | X |  | Data mapping is a central requirements and process of data conversion and will be performed by our data lead.
ISR-5.7 | Data Conversion | Create data conversion extracts from legacy/existing data files in a format specified by the Data Conversion Plan. | X |  | Linea will create data extracts consistent with the data mapping document as gathered during the audit and planning process
ISR-5.8 | Data Conversion | Provide coding of automated data conversion extracts from legacy/existing data files, using techniques that are consistent with the development standards. | X |  | Our data lead will work with our developers on such extracts. Linea has included a complete set of coding standards in the propoosal as part of our response
ISR-5.9 | Data Conversion | Extract legacy data for purposes of transformation and loading into the target application files structures. | X | X
ISR-5.10 | Data Conversion | Transform and load cleansed legacy data. | X |  | This is a standard component of a data conversion and will occur as part of the implementation
ISR-5.11 | Data Conversion | Review the data and the data cleansing metrics as delineated in Data Conversion Plan. |  | X
ISR-5.12 | Data Conversion | Perform manual data cleansing (cleansing of data that cannot be cleansed automatically). | X | X
ISR-5.13 | Data Conversion | Coordinate and execute manual data loads if required. | X |  | We anticipate some manual data loads and will coordinate with NPERS/OSERS as necessary. We will attempt to determine the extent of this activity in the first two months of the project so that we can adjust the schedule without causing delays or backup.
ISR-5.14 | Data Conversion | Provide converted legacy data for transactional testing during integration, end to end, parallel, user acceptance, etc. | X |  | All data will be provide from our lead data analyst and data conversion resource. Data Masking will be performed as appropriate as a security measure.
ISR-5.15 | Data Conversion | Perform Data Conversion from the source system(s) to the target NPRIS system, by electronic or manual methods and track data conversion status and notifications. | X |  | This is a standard component of a data conversion and will occur as part of the implementation
ISR-6.1 | Letters, Forms & Reports | Specify how all reports, letters, and forms will be modified to accommodate the OPS plan in NPRIS, including (but not limited to): - Data merged letters, correspondences, and forms. - Standardized and parameterized reports. | X |  | Clarety has 3 different capabilities to create documents, SSRS, SQR, and java i.e. .rtf / .pdf. We have experience utilizing Visual Studio for SSRS, SQR development tools, and the output tool .pdf Adobe Reader and .rtf Microsoft Word. All documents have standard templates that support the different business functions, we will leverage the existing templates, merge, modify, or create new as needed along with input from business stakeholders to ensure all documents meet NPIRS/OPS standard.
ISR-6.2 | Letters, Forms & Reports | Create the Letters, Forms, and Report Specification Document, to include the following design specifications (at a minimum): - Identify report fields and parameters (as applicable). - Mapping database fields to report fields. - Document required ad-hoc query and reporting functionality. | X |  | Clarety has 3 different capabilities to create documents, SSRS, SQR, and java i.e. .rtf / .pdf. We have experience utilizing Visual Studio for SSRS, SQR development tools, and the output tool .pdf Adobe Reader and .rtf Microsoft Word. All documents have standard templates that support the different business functions, we will leverage the existing templates, merge, modify, or create new as needed along with input from business stakeholders to ensure all documents meet NPIRS/OPS standard.
ISR-6.3 | Letters, Forms & Reports | Develop and/or modify all reports – execute report development and unit testing. | X |  | Clarety has 3 different capabilities to create documents, SSRS, SQR, and java i.e. .rtf / .pdf. We have experience utilizing Visual Studio for SSRS, SQR development tools, and the output tool .pdf Adobe Reader and .rtf Microsoft Word. All documents have standard templates that support the different business functions, we will leverage the existing templates, merge, modify, or create new as needed along with input from business stakeholders to ensure all documents meet NPIRS/OPS standard.
ISR-6.4 | Letters, Forms & Reports | Develop and document custom reports (as required to provide and implement functional and technical requirements). | X |  | Clarety has 3 different capabilities to create documents, SSRS, SQR, and java i.e. .rtf / .pdf. We have experience utilizing Visual Studio for SSRS, SQR development tools, and the output tool .pdf Adobe Reader and .rtf Microsoft Word. All documents have standard templates that support the different business functions, we will leverage the existing templates, merge, modify, or create new as needed along with input from business stakeholders to ensure all documents meet NPIRS/OPS standard.
ISR-7.1 | Testing | Develop a Test Management Strategy deliverable that lists all test events, entrance and exit criteria for each test event, roles and responsibilities, defect management processes, high-level data requirements for each test event, tools used for each test event, including User Acceptance Testing. | X |  | Testing Management includes all forms of testing forms of testing (system, regression, verification, validation, UAT, automated testing, etc.) and entrance/exit criteria for testing. Linea is bringing on a testing specialist in month 5 of the initiative to develop all test plans. Because this is an Agile-Hybrid project, testing will occur with each sprint, and then UAT will occur before cutover. The assigned development team will ship responsibilities to testing as more of the development is completed.
ISR-7.2 | Testing | Provide a Test Plan that covers each test event and provides the detailed approach that shall be taken to fully test all components of the system including test control and approval processes, test participants, how testing will interface with the configuration management process, and test documentation expectations for the following test types: unit, system, security / intrusion, regression, stress/performance, and user acceptance. The Test Plan must include the following at a minimum: - Security / Intrusion testing. - Regression testing. - Test Data Creation approach, including data refresh processes. - Stress / performance testing, including pass criteria that can handle the batch transaction load data. - Automated Test Usage (optional, but preferred by NPERS). - User Acceptance testing scripts and support. - Defect remediation release strategy and regression testing. | X |  | The test plan and execution strategy includes the following: Test types – A definition of each planned testing type. Examples of test types include system, integration, validation, regression, performance, vulnerability and penetration, user acceptance and backup/recovery testing. Entry and exit criteria – Clear entry and exit criteria will be defined for initiating and completing all testing types included in the test plans for both validation and acceptance tests. The client will determine the exit criteria with our input. Test cycles – The number of test cycles will be defined by test type. For example, validation testing may require multiple cycles to identify critical defects with some workarounds. Additional cycles may be required to identify other defects and remove gaps in the test scripts. Conversely, acceptance testing may require fewer cycles. Defect management (and Issue Management) – The tracking and reporting of defects identified during testing will follow an iterative process. Defects will be tracked and linked to scripts with severity and status. Defect management is not just about collecting information and reporting on it; it involves ensuring any reported issues and defects are reported appropriately Test metrics – Test benchmarks will be established, and test metrics will be captured to measure test progress and quality (defects).
ISR-7.3 | Testing | Maintain the Test Management Strategy and all Test Plans. | X |  | Our testing lead will maintain all test plans.
ISR-7.4 | Testing | Manage and execute the agreed upon Test Management Strategy and approved Test Plan, including regression testing, and creating and maintaining the required test data during the testing period. | X |  | Linea has assigned a test lead who will enter the project in month five and will manage the strategy and test plan.
ISR-7.5 | Testing | Provide automated testing tools and procedures for testing including UAT, system, regression, performance, stress, etc. | X |  | We are familiar with various automated tools. If automated tools are used, they may only be needed very late in the project once the build is much more stable. The downside of automated tools is the amount of time required to reset the automated tests every time the build changes. In our experience in pre-implementation testing, it has not been cost effective to automate many of the tests because of so many changing parts during Validation and UAT, requiring adjustments to the automation tool configuration each time. One area where automated tools are more useful in a pre-implementation period is regression testing, where certain build functions become static.
ISR-7.6 | Testing | Document/create standards and procedures for the use of the tools that support all testing activities. | X |  | Linea will create documentation for each test type and lead the test design process, which consists of: Confirming requirement understanding Mapping requirements to test scenarios Preparation of test cases SME/Peer review Incorporating review comments in test cases
ISR-7.7 | Testing | Install, configure, and implement the testing application software, hardware, data, desktops, etc. | X |  | Linea and NeuOrbis are versed in many testing applications such as JIRA and can also assist in training NPERS staff as necessary with such applications.
ISR-7.8 | Testing | Create Test Scripts, Test Cases, and Test Data, aligned to functional and technical requirements; and perform all appropriate testing events as agreed to in the approved Test Plan. | X |  | Linea will create test scripts and lead the entire testing process. Linea's test execution includes the following: Execute each of the test steps in test case Mark status as pass/fail in test management tools Raise defects for the failed test cases Send the daily status report to test lead Participate in defect triage cycle and explain the defects Complete the test execution of all the test cases
ISR-7.9 | Testing | Assist with testing (i.e. integration, regression, system, performance) and provide input to scripts and perform user acceptance testing. |  | X
ISR-7.10 | Testing | Configure Hardware Environments (testing) to test and/or demonstrate the functionality has been satisfied. |  | X
ISR-7.11 | Testing | Configure Hardware Environments (testing) Documentation, including specification of hardware, network, storage, utilities, licensees, and other required infrastructure. |  | X
ISR-7.12 | Testing | Provide documentation of System, Regression, Performance/Stress, and Security/Intrusion Test Results that describe the following (at a minimum): - Date scenario was executed. - Person who executed the scenario. - Test result status (pass/fail). - Defects discovered. - Retest dates and results. - Justification for exiting Test stage, including performance testing success. | X |  | Test results documentation is a standard component of Linea's test activities. Test tools used often allow for automated or easily accessible summary and detailed level reporting on test outcomes, including all information requested by NPERS. Linea will work with NPERS to establish details and frequency of such reports, and the degree to which they will guide decisions regarding project risks and issues, ability to cutover, and scope of remaining work.
ISR-7.13 | Testing | Validate the system for compliance with the Security Plan. | X |  | Linea's Technical and Cybersecurity leads will validate the system for compliance with the Security Plan. We use NIST 800-53 as our security standards for all pension systems.
ISR-7.14 | Testing | Correct defects found as a result of testing efforts. | X |  | Defects will be logged by priority and complexity and will be addressed by NeuOrbis developers. This will occur as part of Agile-Hybrid during validation testing, and will increase during UAT.
ISR-7.15 | Testing | Review testing results for compliance with policies, procedures, plans, and test criteria and metrics (e.g. defect rates, progress against schedule). |  | X
ISR-7.16 | Testing | Coordinate the scheduling of user acceptance testing (e.g. gain user involvement, establish, and define acceptance criteria, set high-level test objectives, establish high-level test scenarios). |  | X
ISR-7.17 | Testing | Facilitate and support user acceptance test as prescribed by NPERS, including: establishing adequate test environment based on user acceptance criteria; preparing data to support test scenarios within modified system as well as managing the relationship with all interfaced systems necessary to conduct test; troubleshooting; supporting users to progress through scenarios; simulating interfaces or working with integrated systems to conduct end-to-end tests; supporting batch processing; exercising functionality; converting production data, and reporting results. | X |  | We will work with NPERS to establish detailed plans for UAT, which will include full business process testing to ensure that the system is ready for deployment to production. UAT will include full end-to-end testing of system functionality, including the generation of documents, reports, batch updates, and input/output data interfaces from/to internal and external systems. UAT is conducted with converted data. UAT will have defined test scenarios and test scripts, built from the knowledge Linea gathered through user stories during the requirements gathering phase, and then translated into scripts to validate system functionality and any new business processes. The result of the UAT phase will be the acceptance or rejection of the Rollout.
ISR-7.18 | Testing | Conduct user acceptance testing. |  | X
ISR-7.19 | Testing | Use a Defect Tracking System (provided by the Bidder) for purposes of allowing NPERS to initiate, track, and report all testing defects (e.g. integration, end to end, parallel, and user acceptance testing). |  | X
ISR-7.20 | Testing | Correct defects found as a result of testing efforts. | X |  | Linea will organize and correct defects, typically with the aid of a test management tool. It is important to note, that not all defects will be fixed upon cutover. Linea will work to categorize defects properly so that it is understand by all parties which defects are critical prior to cutover.
ISR-7.21 | Testing | Provide documentation of satisfying agreed upon exit success criteria for User Acceptance Testing in the User Acceptance Test Results Report. | X |  | Linea has a set of exit criteria standards we use with many pension clients during UAT of modernizations, integrations, and implementations. These will be customized with NPERS, but we have included some example exit criteria: 1) All test scripts have been executed and test results indicate the system functionality is working as documented in the functional specifications and requirements. Clients typically require nearly 100% resolutions for all critical and most high priority issues/defects to proceed. 2) NPERS will review the medium priority issues/defects. The NPERS Steering Committee will make a final decision regarding whether or not any of the medium priority items need to be resolved in order to proceed to UAT. 3) Updated documentation has been created that accurately and completely describes the delivered system functionality and reflects any decisions made for items that differ from the original requirements specifications.
ISR-8.1 | Deployment | Provide detailed Final Technical Documentation including the technical and architectural documents, diagrams, and specifications. | X |  | All documentation will be stored in the clients Content Management system. Through each phase of delivery these documents will be updated appropriately. Assumptions: client has SharePoint or a similar Content Management platform we can use. If NPRIS does not use a Content Management platform, the source code repository will be used.
ISR-8.2 | Deployment | Provide updated Artifacts from the Implementation for Production, including functional, technical specifications, operational documentation (e.g. batch schedule, runtime procedures). | X |  | All documentation will be stored in the clients Content Management system. Through each phase of delivery these documents will be updated appropriately. Assumptions: client has SharePoint or a similar Content Management platform we can use. If NPRIS does not use a Content Management platform, the source code repository will be used.
ISR-8.3 | Deployment | Provide Final As-Built Configuration Documentation of each of the delivered environments, including the results of smoke tests of those environments. Bidder will provide documentation specific to the Agency’s implementation. | X |  | All documentation will be stored in the clients Content Management system. Through each phase of delivery these documents will be updated appropriately. Assumptions: client has SharePoint or a similar Content Management platform we can use. If NPRIS does not use a Content Management platform, the source code repository will be used.
ISR-8.4 | Deployment | Provide updated and Final Cutover Plan and Cutover Schedule. | X |  | The Linea functional lead and training specialist will work together to build the cutover plan and schedule. This will begin to occur during the UAT and will be finalized in the month before cutover.
ISR-8.5 | Deployment | Provide the Configured Hardware Environments (production and disaster recovery). |  | X | Linea will work with NPERS to ensure all hardware environments have been properly configured ahead of Go-Live. Disaster recovery falls under the perview of our cybersecurity lead, who will ensure NIST-800 53 standards are followed.
ISR-8.6 | Deployment | Provide Configured Hardware Environments (production and disaster recovery) Documentation, including specification of hardware, network, storage, utilities, licensees, and other required infrastructure. |  | X | Linea will review and assist with updating documentation as necessary. Linea follows NIST security controls in regards to disaster recovery.
ISR-8.7 | Deployment | Provide Readiness Report to confirm the overall readiness of NPRIS to support the transferred components / modified functionality in production. This will inform the Go/No-Go decision. | X |  | Linea will produce a functional and technical readiness report prior to go-live. Linea will verify that requirements have been delivered and testing in the RTM and that contract terms have been satisfied.
ISR-8.8 | Deployment | Conduct Go/No-go Meeting. | X |  | Linea will confirm with NPERS' project lead and stakeholders that all preparations have been made and all systems are ready for go-live during the Go/No-go meeting. If NPERS decides not to proceed with go-live, Linea will have prepared contingency options.
ISR-8.9 | Deployment | Perform deployment and support activities as directed by NPERS Project Manager. | X |  | We will provide automation and training to support build and deployment activities including automation jobs that have role based restrictions (RBAC) or with manual approval steps. Where Jenkins is used these jobs can be run securely and easily from a web browser, even from a Mobile Phone connected to the network. We can run these jobs via schedule, on request, or we can host a meeting and monitor along with NPRIS operations resources
ISR-8.10 | Deployment | Provide recommended operations and administration procedures related to the deployment. | X |  | All documentation will be stored in the clients Content Management system. Through each phase of delivery these documents will be updated appropriately. Assumptions: client has SharePoint or a similar Content Management platform we can use. If NPRIS does not use a Content Management platform, the source code repository will be used.
ISR-8.11 | Deployment | Approve production deployment go/no-go decisions. |  | X | Linea will allow adequate time for NPERS to approve deployment decisions.
ISR-8.12 | Deployment | Deploy application into production. | X |  | We will provide automation and training to support build and deployment activities including automation jobs that have role based restrictions (RBAC) or with manual approval steps. Where Jenkins is used these jobs can be run securely and easily from a web browser, even from a Mobile Phone connected to the network. We can run these jobs via schedule, on request, or we can host a meeting and monitor along with NPRIS operations resources
ISR-8.13 | Deployment | Track deployment status and notification. | X |  | Jenkins is used for automation jobs including build and deployment. As a standard practice we develop Jenkins jobs so they keep a log of status steps and email a group of a job's status when completed.
ISR-8.14 | Deployment | Provide Cutover Completion Report deliverable that validates the full transition of modified functionality into production. | X |  | Linea will produce multiple reports upon go-live that validate the transition in addition to reports to prepare for post production stabilization (defect status report, bug fix plan, QA summary report, etc.)
ISR-8.15 | Deployment | Provide the configuration and customization documentation and readable source code and object (executable) code for the system in the configuration management system. | X |  | All documentation will be stored in the clients Content Management system. Through each phase of delivery these documents will be updated appropriately. Source Code will be maintained in the code repository. Automation will leverage exisiting Clarety processes and procedures, if those processes do not already store the executable code within the repository, we can add that feature. Assumptions: client has SharePoint or a similar Content Management platform we can use. If NPRIS does not use a Content Management platform, the source code repository will be used.
ISR-9.1 | Transition & Post-Implementation Stabilization Support | Perform an Implementation Phase Closeout including system tuning activities, assessment of knowledge transfer tasks, transfer Project artifacts to Project repository, lessons learned document, update design documents, and transition support to NPERS as appropriate. Document completed Phase Closeout activities in a Project Closeout Report. | X |  | It is important to understand that not everything will be done at go-live. Bug fixing will be required, there may be some or many non-critical features or functionality that may need to be adjusted, and NPERS will need to perform all yearly cycle activity to confirm all functionality is working properly. Linea's post-implementation report and planning will lay the groundwork for the activities required in the year after go-live to fully stabilize the system.
ISR-9.2 | Transition & Post-Implementation Stabilization Support | Provide Monthly Stabilization Support Reports – Bidder will create initial templates of monthly stabilization support reports for NPERS to verify that the reports are sufficient and accurate before the project closes; Reports will include the following: - Maintenance / Stabilization services completed per period. - Maintenance / Stabilization services in progress per period. - Maintenance / Stabilization services planned next period. - Risks and issues. | X |  | Project oversight activities, including risk and issue management, will continue to occur in the year after go-live and regular reports will be created to inform NPERS of upcoming tasks, successful (and unsuccesfful) stabilization efforts, and potential risks. This will managed by Linea's functional lead.
ISR-9.3 | Transition & Post-Implementation Stabilization Support | Escalate and assist with the resolution of issues with Bidder post-production support team. |  | X
ISR-9.4 | Transition & Post-Implementation Stabilization Support | Provide 12 months of system stabilization support. | X |  | Provide 24/7 system support working any incidents in accordance with agreed upon timelines and procedures for each level of problem severity, will correct any errors introduced during the conversion phase, and will provide any solutions to NPERS and test those solutions for the area of concern.
ISR-9.5 | Transition & Post-Implementation Stabilization Support | Provide Level 1 Help Desk—simple (with coordination of user support activities including “how to” support) and user account and password administration. |  | X
ISR-9.6 | Transition & Post-Implementation Stabilization Support | Provide Level 2 and 3 Help Desk for the system-related incidents and problems. | X |  | Provide 24/7 system support working any incidents in accordance with agreed upon timelines and procedures for each level of problem severity, will correct any errors introduced during the conversion phase, and will provide any solutions to NPERS and test those solutions for the area of concern.
ISR-9.7 | Transition & Post-Implementation Stabilization Support | Provide support organization to advise and assist business end-users and staff in the use of systems and NPERS-specific policies. |  | X
ISR-9.8 | Transition & Post-Implementation Stabilization Support | Respond to escalated trouble ticket items in accordance with established procedures. | X |  | Provide 24/7 system support working any incidents in accordance with agreed upon timelines and procedures for each level of problem severity, will correct any errors introduced during the conversion phase, and will provide any solutions to NPERS and test those solutions for the area of concern.
ISR-9.9 | Transition & Post-Implementation Stabilization Support | Establish priority of trouble ticket items / service requests. |  | X
ISR-9.10 | Transition & Post-Implementation Stabilization Support | Maintain “end state” system architecture documentation. | X |  | Linea and NeuOrbis will work with NPERS IT department to build a version of these documents that are clean and understandable to the SMEs who will be maintaining the system moving forward. Because this is a component that begins as part of to-be technical analysis, the final system architecture document is more a matter of adjustments and updates rather than a new deliverable during post implementation support.
ISR-9.11 | Transition & Post-Implementation Stabilization Support | Provide maintenance and repair policies and procedures. | X |  | Maintenance/Repair policies and documents will begin prior to post-implementation support and are usually part of technical readiness activitities late during implementation. However, they will be further fleshed out during post-implementation, including policies to match each of the annual activities.
ISR-9.12 | Transition & Post-Implementation Stabilization Support | Provide technical and functional support to NPERS IT staff and other groups as directed by NPERS. | X |  | Linea has more than two decades providing a wide array of services to pension systems, and a staff of nearly 100 consultants who can be utilized to assist NPERS with additional requests. This includes further BPI or BPR efforts, additional modernization analysis and support, the development of an improved cybersecurity posture or vCISO services, or even staff augmentation as desired.
ISR-9.13 | Transition & Post-Implementation Stabilization Support | Provide processes and procedures for tracking and reporting the status of all post-implementation support and stabilization services. | X |  | Linea follows standard PMBOK procedures for tracking stabilization. We will also provide updates regarding change management and adoption of the new system.
ISR-9.14 | Transition & Post-Implementation Stabilization Support | Perform system fixes for problems that the Bidder was responsible for providing. | X |  | Provide 24/7 system support working any incidents in accordance with agreed upon timelines and procedures for each level of problem severity, will correct any errors introduced during the conversion phase, and will provide any solutions to NPERS and test those solutions for the area of concern.
ISR-9.15 | Transition & Post-Implementation Stabilization Support | Perform data fixes for errors that the Bidder was responsible for, including but not limited to improperly converted files or data. | X |  | Provide 24/7 system support working any incidents in accordance with agreed upon timelines and procedures for each level of problem severity, will correct any errors introduced during the conversion phase, and will provide any solutions to NPERS and test those solutions for the area of concern.
ISR-9.16 | Transition & Post-Implementation Stabilization Support | Regression test the system to ensure that no errors are introduced. | X |  | Provide 24/7 system support working any incidents in accordance with agreed upon timelines and procedures for each level of problem severity, will correct any errors introduced during the conversion phase, and will provide any solutions to NPERS and test those solutions for the area of concern.
ISR-9.17 | Transition & Post-Implementation Stabilization Support | Approve all post-implementation support and stabilization service fixes with formal sign-off. |  | X
ISR-9.18 | Transition & Post-Implementation Stabilization Support | Update all documentation and related files/Deliverables associated with post-implementation support services. | X |  | There is a risk of creating "shelf ballast" with process documents after an integration or modernization of any kind. Linea will regularly review relevant documents to ensure updates are occuring, changes to processes are tracked, and that there is proper governance in place to transition maintenance duties to NPERS toward the end of the year of stabilization.
ISR-9.19 | Transition & Post-Implementation Stabilization Support | Test remediated code or configurations (and regression test the entire solution) to verify that no errors are introduced. | X |  | Provide 24/7 system support working any incidents in accordance with agreed upon timelines and procedures for each level of problem severity, will correct any errors introduced during the conversion phase, and will provide any solutions to NPERS and test those solutions for the area of concern.
ISR-9.20 | Transition & Post-Implementation Stabilization Support | Update all appropriate documentation to reflect defect corrections. | X |  | In the final two months of stabilization, Linea will perform a "content sweep" to ensure documents are current, no errors remain, and that NPERS SME understand the hand-off process and future ownership of all documentation.
ISR-9.21 | Transition & Post-Implementation Stabilization Support | Provide Final Acceptance Document deliverable that includes a checklist of all Project closeout activities and validates that support has been provided for the duration of the Minimum Support Period (i.e., 12 months). | X |  | Linea will submit a final summary report of all project activity. This report will include any recommendations moving forward for regular maintenance. This final report will signify the end of this project, though Linea always encourages a continued client relationship should additional assistance be needed for future enhancement or modernization efforts.