## Instructions
Project Index
General: | This document is a consolidated view and is replacement of the following documents: Project-specific Development Case Exhibit 6 - Data and Property Management Plan Stakeholder Involvement Plan The contents of all of these artifacts has been merged into an artifact-centric view for the entire project.
Column | Instructions | Value
Discipline | Identify which Unisys Discipline that controls this Artifact. | Analysis and Design Configuration Management Environment Implementation M&A (Measurements and Analysis) Project Management Requirements Test
Artifact | The Unisys name of the Artifact | Artifact Name
Artifact Identified for Project | Indicate, on a per project basis, if this artifact will be produced and maintained through lifecycle of this project. | Yes or No (Artifacts marked as other will indicated the artifact will be created and maintained by another team)
Phase Created | Indicate in which Unisys phase the Artifact is created. Note: For the difference component (COTS/GOTS products), any GAP will follow the Unisys phases for implementation. | ALL Inception Elaboration Construction Transition AS REQUIRED N/A
Notes and non-compliance justification | Additional explanation of artifact and reasons why artifact is not used by the project | Free form text
Review Formality | The project uses the following review levels: • Formal • Informal • None | Formal: A meeting will be required to conduct the review Informal: Will not necessaily require a meeting None: No review required
Media Type | Identify the Media type of this artifact. | Not limited to but including: MS Excel, MS Word, MS Project, PDF, Paper, Visio
Version Control | Indicate the controlling system of this artifact. | Not limited to but including: SharePoint, TFS, File Server directory
Security | Indicate what type of document security this artifact is controlled. The value indicated is that recommended value however each project may set this per their own security requirements. | Unisys Only Unisys Team (and subs) Unisys - Nebraska State Patrol (NSP) Unisys - Public (Stakeholders)
Path | For this project, indicate where this artifact is stored. | A relative path to the file. Refer also to Storage Server
Data retention period | Mention how long the data is required to be retained. | Express in days, weeks, months, years following the closeout of the project. If appropriate, retention expiration can be expressed as a specific date.
Stakeholder Involvement | Indicate which classes of stakeholder are involved with the creation, review and approval of the artifact | c = Creator or contributor to creation of the artifact r = Reviewer of the artifact a = approver of the artifact i = user of the artifact as information The field should be any relevant combination of these values.
Stakeholder Notes | Provide further explanation of stakeholder involvement where it helps to understand who is involved and what is to be done | Free form text
Note on A10: Mark with Yes, this is an artifact specifically used for this Project. Otherwise leave blank.
Note on A11: ALL Inception Elaboration Construction Transition AS REQUIRED N/A

## Dev Case and Stakeholder
Discipline | Artifact | Artifact Identified for Project | Phase Created | Notes and non-compliance justification | Review Formality | Media Type | Version Control | Security | Path | Data Rention Period | Unisys Team - PMO | Nevada DPS - PMO | Nevada DPS - RCCD | Unisys Team - Project Manager | Unisys Team - Software Architect | Unisys Team - Security Lead | Unisys Team - Functional Lead | Unisys Team - Testing Lead | Unisys Team - Data Conversion Lead | Diverse Computing Lead | Analysts International Lead | Tailored Solutions Lead | DataWorks Plus Lead | Peak Performance Lead | Stakeholder Notes
Project Management | [DEL-01] Project Management Plan (PMP) | YES | All |  | Formal | MS Word | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\PMP\ | TBD
Requirements | [DEL-02] Solutions Requirements Specifications (SRS) | YES | Incep |  | Formal | MS Word | SharePoint |  | [SharePoint]\03 - Requirements\SRS\ | TBD
Project Management | [DEL-03] Integrated Master Schedule (IMS) | YES | All |  | Formal | MS Project | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\02 - Schedule\ | TBD
Testing | [DEL-04] Test and Evaluation Master Plan (TEMP) | YES | Incep |  | Formal | MS Word | SharePoint |  | [SharePoint]\06 - Testing\MasterPlan\ | TBD
Deployment | [DEL-05] Solution Migration Plan | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\07 - Deployment\Data Migration\Master Plan | TBD
Testing | [DEL-06] Test Report | YES | Const |  | Formal | MS Word | SharePoint |  | [SharePoint]\06 - Testing\System Testing\Execution Results\ | TBD
Project Management | [DEL-07] Meeting Agenda | YES | All |  | Informal | MS Word | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\Meeting Agendas | TBD
Project Management | [DEL-08] Presentation Materials | YES | All |  | Informal | MS Word/PowerPoint | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\Presentation Materials | TBD
Project Management | [DEL-09] Meeting Minutes | YES | All |  | Informal | MS Word | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\Meeting Minutes | TBD
Environment | [DEL-10] In-Plant Security Plan | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\10 - Environment\In-Plant Security Plan\ | TBD
Deployment | [DEL-11] User Manuals | YES | Trans |  | Formal | TBD | TBD |  | TBD | TBD
Analysis & Design | [DEL-12] Database Design Document | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\04 - Analysis-Design\Database\Master Design\ | TBD
Analysis & Design | [DEL-13] Interface Design Document | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\04 - Analysis-Design\Interfaces\ | TBD
Analysis & Design | [DEL-14] System Design Document | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\04 - Analysis-Design\Architecture\ | TBD
Environment | [DEL-15] Bill of Materials | YES | Elab |  | Formal | MS Excel | SharePoint |  | [SharePoint]\10 - Environment\BoM\ | TBD
Environment | [DEL-16] Installation Plan | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\07 - Deployment\Installation Plan\ | TBD
Deployment | [DEL-17] Training Plan | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\09 - Training\Master Plan\ | TBD
Deployment | [DEL-18] Installation Drawings | YES | Elab |  | Formal | MS Excel/Visio | SharePoint |  | [SharePoint]\07 - Deployment\Installation Plan\Drawings\ | TBD
Deployment | [DEL-19] Training Materials | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\09 - Training\[product]\Materials\ | TBD
Project Management | [DEL-20] Technical Report | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\Technical Report | TBD
Testing | [DEL-21] Test Procedures (FAT, SAT, UAT) | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\06 - Testing\Test Procedures\ | TBD
Environment | [DEL-22] Continuity of Operations (COOP) Plan (FAT, SAT, UAT) | YES | Incep |  | Formal | MS Word | SharePoint |  | [SharePoint]\10 - Environment\Operations Plan\ | TBD
Environment | [DEL-23] System Hardware | YES | Incep |  | Formal | MS Word | SharePoint |  | [SharePoint]\10 - Environment\System Hardware\ | TBD
Environment | [DEL-24] Software Licenses | YES | Incep |  | Formal | MS Word | SharePoint |  | [SharePoint]\10 - Environment\Software Licenses\ | TBD
Deployment | [DEL-25] System Data | YES | Trans |  | Formal | MS Word/Excel | SharePoint |  | [SharePoint]\07 - Deployment\Data Migration\System Data | TBD
Environment | [DEL-26] Version Description Document | YES | Incep |  | Formal | MS Word | SharePoint |  | [SharePoint]\10 - Environment\Version Description\ | TBD
Environment | [DEL-27] Installation Survey Report | YES | Const |  | Formal | MS Word | SharePoint |  | [SharePoint]\10 - Environment\Survey Report\ | TBD
Testing | [DEL-28] Test Plan (FAT, SAT, UAT) | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\09 - Training\Test Plan\ | TBD
Config Mgmt | [DEL-29] Configuration Management Plan | YES | Elab |  | Formal | MS Word | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\00 - PMP\ | TBD
Requirements | [DEL-30] Requirements Verification and Traceability Matrix (RVTM) | YES | Incep |  | Formal | MS Excel | SharePoint |  | [SharePoint]\03 - Requirements\RTM\ | TBD
Testing | [DEL-31] Solution Performance Report | YES | Trans |  | Formal | MS Word/Excel | SharePoint |  | [SharePoint]\06 - Testing\Peformance Testing\Execution Results\ | TBD
Project Management | [DEL-32] Data and Property Management Plan | YES | All |  | Formal | MS Excel | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\00 - PMP\Development Case\ | TBD
Project Management | [DEL-33] Service Level Plan (SLP) | YES | Trans |  | Formal | MS Word | SharePoint |  | [SharePoint]\08 - Mgt - Project Mgt\00 - Supplier\SLP\ | TBD
Deployment | [DEL-34] Data Conversion Plan | YES | Elab |  | Formal | MS Word/Excel | SharePoint |  | [SharePoint]\04 - Analysis-Design\Data Conversion\Master Plan\ | TBD
Note - This will be a living document throughout project.
Note - Will elaborate during Project Initiation; illustrating format used.
Note on K1: Pgm+1 year Retain for 1 year after the UMV program is sunset

## Role-Responsibility-Comm
Roles, Responsibilities and Communication
Member Information |  |  |  | Roles and Responsibilities | [20 empty] | Subscribed Communications and Information Access
Name | Org | Phone | E-mail |  | NSP - Executive Sponsor | NSP - Technology Sponsor | NSP - Advisory Workgroup | NSP - Project Mgr | NSP - Information Security Officer | NSP - Senior Technical Mgr | NSP - Technical Mgr (Infrastructure) | NSP - Systems Analyst | Unisys Team - Client Executive | Unisys Team - Project Director | Unisys Team - Project Mgr | Unisys Team - Software Architect | Unisys Team - Security Lead | Unisys Team - Functional Lead | Unisys Team - Testing Lead | Unisys Team - Data Conversion Lead | Diverse Computing Mgr/Lead | Peak Performance Mgr/Lead | Stakeholder Notes | Weekly Project Status Meetings | Monthly Steering Committee Meetings | Weekly Risks Reviews | Weekly Issues Reviews | Deliverable/Milestone Reviews | Functional COTS GAP Review | SharePoint Repository Access | Notes
TBD |  |  |  |  | X | [17 empty] | Executive Sponsor
TBD | [5 empty] | X | [16 empty] | Technology Sponsor
TBD | [6 empty] | X | [15 empty] | Advisory Workgroup
TBD | [7 empty] | X | [14 empty] | Project Manager
TBD | [8 empty] | X | [13 empty] | Information Security Officer
TBD | [9 empty] | X | [12 empty] | Senior Technical Manager
[11 empty] | X | [11 empty] | Technical Manager (Infrastructure)
TBD | [11 empty] | X | [10 empty] | Systems Analyst
TBD | [12 empty] | X | [9 empty] | Client Executive / Business Development Manager
TBD | [13 empty] | X | [8 empty] | Justice and Public Safety Project Director
TBD | [14 empty] | X | [7 empty] | Senior Project Manager (PMP)
TBD | [15 empty] | X | [6 empty] | Senior Software Architect
TBD | [16 empty] | X | [5 empty] | Security Compliance Officer
TBD | [17 empty] | X |  |  |  |  | Project Mgr / SME Expert
TBD | [18 empty] | X |  |  |  | Test Manager Lead
TBD | [19 empty] | X |  |  | Data Conversion Specialist
TBD | [20 empty] | X |  | Project Manager / Team Lead
TBD | [21 empty] | X | Project Manager / Team Lead

## Change History
Revision History
Approvers
Date | Version | Artifact Changed | Description of Change | Author | TBD | TBD
TBD | 0.1 | Dev Case | Initial draft | Unisys Team