## Report Data
Booking Start Date | Booking Title | Date Range (scheduled) | Column1 | Hours
Sample Project Plan
May 2024
Week Of | Task |  | Onsite or Remote
2024-05-27 08:00 | Create VMs per Server Spec Sheet | 2.4 | Remote | 12
June 2024
Week Of | Task |  | Onsite or Remote
2024-06-17 08:00 | Establish VPN Access | 0.2 | Remote | 1
2024-06-17 08:00 | Interface Review/Documentation | 1.6 | Remote | 8
2024-06-24 08:00 | Complete Server as-built Documentation | 2 | Remote | 10
September 2024
Week Of | Task |  | Onsite or Remote
2024-09-02 | Write Up Selected Vendor Interface ICD's |  | Remote | 24
2024-09-09 | Complete Selected Vendor Interface ICD's and Review with Customer |  | Remote | 16
2024-09-16 | Review and Address Redlines for Selected Vendor Interface ICD's |  | Remote | 4
2024-09-16 08:00 | Data Conversion Scope Review | 2.8 | Remote | 14
October 2024
Week Of | Task |  | Onsite or Remote
2024-10-07 | Development: Set ups Selected Vendor Interfaces |  | Remote | 32
2024-10-14 | Development: Data conversion work |  | Remote | 32
2024-10-28 08:00 | CAD Server Staging | 2.4 | Remote | 12
November 2024
Week Of | Task |  | Onsite or Remote
2024-11-04 08:00 | Map Build 1 | 8 | Remote | 40
2024-11-18 08:00 | Prep System Build 1 | 1.6 | Remote | 8
2024-11-18 08:00 | Map Data Analysis and Report | 4.8 | Remote | 24
2024-11-25 08:00 | Map Data Analysis and Report | 5.33 | Remote | 26.65
December 2024
Week Of | Task |  | Onsite or Remote
2024-12-02 08:00 | System Build 1 (Onsite) | 6.4 | Onsite | 32
2024-12-02 08:00 | Development: interfaces |  | Remote | 16
2024-12-16 08:00 | Map Build 2 | 8 | Remote | 40
2024-12-16 08:00 | Ticket Resolution | 1.6 | Remote | 8
2024-12-23 08:00 | Prep System Build 2 | 4 | Remote | 20
January 2025
Week Of | Task |  | Onsite or Remote
2025-01-06 08:00 | System Build 2 (Onsite) | 6.4 | Onsite | 32
2025-01-27 08:00 | Prep System Build 3 | 1.6 | Remote | 8
February 2025
Week Of | Task |  | Onsite or Remote
2025-02-03 08:00 | System Build 3 (Onsite) | 6.4 | Onsite | 32
2025-02-10 08:00 | COTS Interface Installation - Production Environment | 6.4 | Remote | 32
2025-02-10 08:00 | Data conversion load and validation testing | 0.8 | Remote | 4
March 2025
Week Of | Task |  | Onsite or Remote
2025-03-03 08:00 | Tech Lead Health Check | 1.6 | Remote | 8
2025-03-03 08:00 | COTS Interface Installation - DR Environment | 4 | Remote | 20
2025-03-03 08:00 | COTS Interface Installation - Test Environment | 4 | Remote | 20
2025-03-10 | SysAdmin Intro Workshop (Onsite) | 4.8 | Onsite | 24
2025-03-17 | SysAdmin Core 1 Workshop (Onsite) | 4.8 | Onsite | 24
2025-03-24 08:00 | System Configuration Workshop 1 (Onsite) | 6.4 | Onsite | 32
2025-03-31 08:00 | Data conversion load 2 and validation testing | 7.5 | Remote | 37.5
April 2025
Week Of | Task |  | Onsite or Remote
2025-04-07 08:00 | Config 1 Follow-up Wk2 | 4.8 | Remote | 24
2025-04-07 08:00 | Install/Setup ProQA | 1.6 | Remote | 8
2025-04-07 08:00 | Analytics Initial Install Follow-up/Prep for Training | 3.2 | Remote | 16
2025-04-14 08:00 | System Configuration Workshop 2(Onsite) | 6.4 | Onsite | 32
2025-04-21 08:00 | Config 2 Follow-up Wk1 | 4.8 | Remote | 24
2025-04-28 08:00 | Prep Mobile Law Config Workshop 1 | 0.4 | Remote | 2
2025-04-28 08:00 | Install/Initial Config Mobile | 3.2 | Remote | 16
May 2025
Week Of | Task |  | Onsite or Remote
2025-05-05 08:00 | System Configuration Workshop 3 (Onsite) | 6.4 | Onsite | 32
2025-05-05 08:00 | Mobile Law Config Workshop 1 (Onsite) | 4.8 | Onsite | 24
2025-05-12 08:00 | Map Build 2 Follow-up | 1.6 | Remote | 8
2025-05-19 08:00 | Config 3 Follow-up Wk1 | 4.8 | Remote | 24
2025-05-19 08:00 | Mobile Law Workshop 1 Follow-up/Initial Delivery | 8 | Remote | 40
2025-05-26 08:00 | Config 3 Follow-up Wk2 | 6 | Remote | 30
2025-05-26 08:00 | Prep Mobile Law Config Workshop 2 | 0.5 | Remote | 2.5
June 2025
Week Of | Task |  | Onsite or Remote
2025-06-02 08:00 | Mobile Law Config Workshop 2 (Onsite) | 4.8 | Onsite | 24
2025-06-02 08:00 | Ticket Resolution | 1.6 | Remote | 8
2025-06-02 08:00 | Map Build 3 | 8 | Remote | 40
2025-06-09 08:00 | Mobile Law Workshop 2 Follow-up/Final Delivery | 8 | Remote | 40
2025-06-23 08:00 | Site Config Doc | 1.6 | Remote | 8
2025-06-30 08:00 | Internal Selected Vendor Testing | 6 | Remote | 30
July 2025
Week Of | Task |  | Onsite or Remote
2025-07-07 08:00 | Onsite Customer Functional Testing Wk1 | 8 | Onsite | 40
2025-07-07 08:00 | Stage DR Servers | 6.4 | Remote | 32
2025-07-14 08:00 | Onsite Customer Functional Testing Wk2 | 8 | Onsite | 40
2025-07-21 08:00 | Address Blocker Defects | 6.4 | Remote | 32
2025-07-28 08:00 | Prep/Alignment for TTT | 0.8 | Remote | 4
2025-07-28 08:00 | Analytics SysAdmin and User Training | 1.6 | Remote | 8
August 2025
Week Of | Task |  | Onsite or Remote
2025-08-04 08:00 | Data Refresh Training | 3.2 | Remote | 16
2025-08-04 08:00 | Mobile TTT Law (Onsite) | 6.4 | Onsite | 32
2025-08-11 08:00 | 4 weeks End Users Training (Onsite) | 8 | Onsite | 40
September 2025
Week Of | Task |  | Onsite or Remote
2025-09-15 08:00 | Readiness Review Checklist Creation | 1.6 | Remote | 8
2025-09-29 08:00 | Customer Readiness Review | 0.4 | Remote | 2
October 2025
Week Of | Task |  | Onsite or Remote
2025-10-06 08:00 | Onsite Cutover | 8 | Onsite | 40
2025-10-13 08:00 | Post Customer Support Wk1 | 8 | Remote | 40
2025-10-20 08:00 | Post Cutover Support Wk2 (Remote) | 6.4 | Remote | 32
2025-10-27 08:00 | 30 Day Reliability Support (Wk3) | 8 | Remote | 40
November 2025
Week Of | Task |  | Onsite or Remote
2025-11-03 08:00 | 30 Day Reliability Support (Wk4) | 8 | Remote | 40
2025-11-10 08:00 | Finalize Site Config/Handoff to Customer Support | 1.8 | Remote | 9
2025-11-10 08:00 | Finalize Site Config/Handoff to Customer Support | 1.8 | Remote | 9